## Data Return
High Needs Provision Capital Allocations - Assurance Data Return
LAs should return this completed template to the department by 1st October 2022 by emailing the completed template to: capital.allocations@education.gov.uk. For more information on how to complete this form, please see the included Guidance Sheet.
We will ask LAs to subsequently revisit and update this template over Summer 2023, to ensure it reflects any updated delivery plans, before providing an updated version of their return to the same Capital Allocations mailbox, no later than 1st October 2023.
| LOCAL AUTHORITY | Leicestershire | [6 empty] | Date Template Completed | 2023-11-07
| LA Number | 855
| 2021-22 HNPCA Grant | 3641554.5
2022-23 and 2023-24 HNPCA total funding
| 2022-23 HNPCA Grant | 7607222.45 | [6 empty] | Total 2022-23 HNPCA funding committed | 7607222.45
| 2023-24 HNPCA Grant | 8900273.26 | [6 empty] | Total 2023-24 HNPCA funding committed | 24882.49
[9 empty] | Total funding committed | 7632104.94
[9 empty] | Total uncommitted funding | 8875390.77
Project Information
[6 empty] | Places |  |  | Types of Need |  |  | Indicative/Provisional Funding |  |  |  |  | Local Consultation
Name of School or Institution | URN (If known) | School or Institution Address | Institution Type | Ofsted Judgement | Age Range | Initial number of new HN places operational upon completion | Total number of new HN places the project will deliver once at capacity | Number of reprovided HN places | What is the primary type of need this project will address? | In addition to the primary type of need, will the project address any other types of need? | What is the main purpose of the project? | How much 2021-22 HNPCA funding will the project use? | How much 2022-23 HNPCA funding will the project use? | How much 2023-24 HNPCA funding will the project use? | In addition to HNPCA, how much additional funding from housing developer contributions (s106 and CIL) will the project use? | If the project will use any other additional funding, how much funding will this be? | Have you consulted locally regarding this project? | Please give more details about what you have done as part of the consultation process | Which academic year do you anticipate the project being completed and the places being in use? | Brief Description of Project Please briefly set out any further details of the project
Foxfields Academy | 148029 | Hospital Lane, Blaby, Leicestershire, LE8 4FE | Academy/free school - Special | This institution is open, but has not yet been inspected by Ofsted | Primary and secondary |  | 30 |  | Social, Emotional and Mental Health | No - The project will only address its primary type of need | Expansion of existing provision (on existing site) | 0 | 3944808 | 0 | TBC | TBC | Consultation completed | Academy has submitted a significant change application currently being reviewed by DfE | AY 2023/24 | The project consists of a standalone block providing 2x additional classrooms. Due to delay delivering Bowman Academy will also need to refurb coachhouse to take interim pupils for 1 year current cost 12 months old and will increase.
Ashmount School | 120352 | Thorpe Hill, Loughborough, Leicestershire, LE11 4SQ | Maintained Special school | Outstanding | Primary, secondary and post-16 |  | 15 |  | Severe Learning Difficulty | No - The project will only address its primary type of need | Expansion of existing provision (on existing site) | 0 | 1083282 | 0 | TBC | TBC | Consultation completed | Head Teacher notified parents via news letter and perspective parents site visits | AY 2022/23 | A new 2 classroom block is currently being constructed expected to complete March 2023. Temporaily using conference space.
Forest Way School | 137905 | Warren Hills Road, Coalville, Leicestershire, LE67 4UU | Academy/free school - Special | Outstanding | Primary, secondary and post-16 |  | 20 |  | Severe Learning Difficulty | Yes - Profound & Multiple Learning Difficulty | Expansion of existing provision (on existing site) | 0 | 761335 | 0 | 103963 | TBC | Consultation completed | Head Teacher notified parents via news letter and perspective parents site visits | AY 2022/23 | 2x classroom block currently submitted for planning permission anticipated to be completed summer 2023 temporarily using spare classroom at Hastings Primary School Ashby whilst it incrementaly fills.
Birch Wood (Melton Area Special School) | 134640 | Grange Drive, Melton Mowbray, Leicestershire, LE13 1HA | Maintained Special school | Good | Primary, secondary and post-16 |  | 15 |  | Severe Learning Difficulty | Yes - Profound & Multiple Learning Difficulty | Expansion of existing provision (on existing site) | 0 | 486653 | 0 | 30370 | TBC | Consultation completed | Head Teacher notified parents via news letter and perspective parents site visits | AY 2022/23 | Conversion of staffroom and soft play area into new EYFS base with freeflow into internal courtyard works completed. New soft play base currently under construction expected completed Dec 2022.
Dorothy Goodman School | 138156 | Stoke Road, Hinckley, Leicestershire, LE10 0EA | Academy/free school - Special | Outstanding | Primary, secondary and post-16 |  | 24 |  | Severe Learning Difficulty | Yes - Profound & Multiple Learning Difficulty | Expansion of existing provision (on satellite site) | 0 | 194430 | 0 | TBC | TBC | Consultation completed | Head Teacher notified parents via news letter and perspective parents site visits | AY 2022/23 | DG operating a satelitte site at Lubbesthorpe primary. Project remodelling work to provide external play, sensory space, access to other teaching areas works completed.
Dorothy Goodman School | 138156 | Stoke Road, Hinckley, Leicestershire, LE10 0EA | Academy/free school - Special | Outstanding | Primary, secondary and post-16 |  | 10 |  | Severe Learning Difficulty | Yes - Profound & Multiple Learning Difficulty | Improvement of an existing provision | 0 | 600000 | 0 | 172374 | TBC | N/A |  | AY 2023/24 | Dorothy Goodman Reception Remodel to provide additional teaching space for additional pupils scheme to be agreed expected delivery September 2023.
Dorothy Goodman School | 138156 | Stoke Road, Hinckley, Leicestershire, LE10 0EA | Academy/free school - Special | Outstanding | Primary, secondary and post-16 |  |  | 24 | Severe Learning Difficulty | Yes - Profound & Multiple Learning Difficulty | Improvement of an existing provision | 283509 | 27755 | 0 | TBC | TBC | N/A |  | AY 2022/23 | Redmoor Academy served notice on DG to vacate 2 of their classrooms occupied by DG students. LCC relocated a modular building onto the campus to enable DG students to remain in this locality.
Maplewell Hall School | 120348 | Maplewell Road, Woodhouse Eaves, Loughborough, Leicestershire, LE12 8QY | Maintained Special school | Good | Primary, secondary and post-16 |  | 12 |  | Moderate Learning Difficulty | No - The project will only address its primary type of need | Expansion of existing provision (on existing site) | 0 | 65000 | 0 | TBC | TBC | N/A |  | AY 2022/23 | Passported funding to school to deliver a single teaching base project completed.
Robert Smyth Academy | 137161 | Burnmill Road, Market Harborough, Leicestershire, LE16 7JG | Academy/free school - Mainstream | Good | Secondary |  | 15 |  | Autistic Spectrum Disorder | No - The project will only address its primary type of need | Entirely new SEN unit within a school | 600000 | 0 | 0 | TBC | TBC | Consultation completed | School consulted with local community as part of significant change process and submission approved Jan 2022 | AY 2022/23 | Project on site to construct new teaching bases for pupils with C&I currently on site expected to be completed April 2023. Funding passported to Trust to deliver project.
All Saints Church of England Primary School | 145973 | Long Street, Wigston, Leicestershire, LE18 2AH | Academy/free school - Mainstream | This institution is open, but has not yet been inspected by Ofsted | Primary | 10 | 20 |  | Autistic Spectrum Disorder | No - The project will only address its primary type of need | Expansion of existing provision (on existing site) | 23263 | 0 | 0 | TBC | TBC | Consultation completed | School consulted with local community as part of significant change process and submission approved June 2022 | AY 2022/23 | Refurbishment of internal space to expand current C&I provision project completed.
The Cedars Academy | 140787 | Wanlip Lane, Birstall, Leicester, Leicestershire, LE4 4GH | Academy/free school - Mainstream | Good | Secondary |  | 15 |  | Social, Emotional and Mental Health | No - The project will only address its primary type of need | Entirely new SEN unit within a school | 385460 | 0 | 0 | TBC | TBC | Consultation completed | School consulted with local community as part of significant change process and submission approved September 2020 | AY 2022/23 | New standalone building constructed on former Youth block site project completed April 2022. Funding passported to Academy Trust to deliver project.
Birch Wood (Melton Area Special School) | 134640 | Grange Drive, Melton Mowbray, Leicestershire, LE13 1HA | Maintained Special school | Good | Primary, secondary and post-16 |  | 8 |  | Profound & Multiple Learning Difficulty | Yes - The project will address a range of other needs | Expansion of existing provision (on satellite site) | 0 | 0 | 0 | 90000 |  | N/A |  | AY 2022/23 | Install mezzanine floor to create space for Art Studio - The current staffroom will be converted to an additional classroom and the former Art room will become the staff room.
Westfield Junior School | 119928 | Westfield Road, Hinckley, Leicestershire. LE10 0LT | Maintained school | Requires Improvement | Other category in 0-25 age-range (please specify in project description) |  | 0 | 25 | Speech, Language and Communication | No - The project will only address its primary type of need | Improvement of an existing provision | 0 | 78000 | 0 | 0 | 0 | N/A |  | AY 2022/23 | Install stud wall to exisiting classroom to create a corridor as currently the end class have to walk through the middle classroom to access WCs which is distracting and disruptive. The toilet block needs to be reconfigured to include wash down space - exisitng WC accessible toilet not fit for purpose and being replaced.
Wreake Valley | 137983 | Parkstone Road, Syston, Leicestershire. LE7 1LY | Academy/free school - Mainstream | Good | Secondary | 15 | 45 |  | Speech, Language and Communication | No - The project will only address its primary type of need | Expansion of existing provision (on existing site) | 0 | 243452 | 0 | 0 | 0 | Consultation completed | RSC approved proposal after public consultation with local community as part of SCA | AY 2022/23 | Refurbishment of exsiting building to provide 6 classrooms, staff area and support spaces. Funding passported to the Academy Trust to deliver project.
Lutterworth John Wycliffe School | 144111 | Moorbarns Lane, Lutterworth, Leicestershire LE17 4QJ | Academy/free school - Mainstream | Good | Primary | 5 | 12 |  | Autistic Spectrum Disorder | Yes - The project will address a range of other needs | Entirely new SEN unit within a school | 0 | 80000 | 0 | 0 | 0 | N/A |  | AY 2022/23 | The LA is currently exploring other options to address its growing demand for specialist places, particularly in its Area Special Schools. It is currently working with a Strategic Partner to further understand this. Additionally the Delivering Better Value Programme and SEND Review will impact the way in which the LA approaches this issue. The remainder of the HNPCA grant will be utilised alongside the LA's own resources to address these requirements
Hinckley Hollycroft Primary school | 149749 | Greenfinch Road, Hinckley. LE10 3GL | Academy/free school - Mainstream | This institution is open, but has not yet been inspected by Ofsted | Primary | 10 |  |  | Autistic Spectrum Disorder | No - The project will only address its primary type of need | Other (please provide details in project description) | 0 | 42507.45 | 24882.49 | 0 | 0 | N/A |  | AY 2022/23 | Adaptation works included access control for doors, sensory room equipment, foundation play changes, external play equipment, specialist Teaching room.
Bowman Academy |  | Butthole Lane, Shepshed, Loughborough LE12 9BN | Academy/free school - Special | This institution is not yet open | Primary and secondary |  | 50 |  | Social, Emotional and Mental Health | No - The project will only address its primary type of need | Entirely new school | 200000 | 0 | TBC | 0 | 0 | N/A | LA successful in bidding for a new SEMH School | AY 2024/25 | DfE constructed School 12 month delay due to agreeing costing. LA funded abnormals costs as detailed in MOU
Farley Way Quorn |  | Farley Way Quorn Leicestershire | Academy/free school - Special | This institution is not yet open | Primary and secondary |  | 80 |  | Speech, Language and Communication | No - The project will only address its primary type of need | Entirely new school | 0 | 0 | TBC | 0 | 0 | N/A | LA successful in bidding for a new C&I School | After AY 2025/26 | Required allocation to meet abnormals - DfE driven scheme expected opening Sept 2026
TBC | TBC | TBC | [10 empty] | TBC | TBC | TBC | TBC |  |  |  | The LA is currently exploring other options to address its growing demand for specialist places, particularly in its Area Special Schools. It is currently working with a Strategic Partner to further understand this. Additionally the Delivering Better Value Programme and SEND Review will impact the way in which the LA approaches this issue. The remainder of the HNPCA grant will be utilised alongside the LA's own resources to address these requirements
If you require additional rows added to the table, select the bottom row of the table, and right click > insert row.
Note on D21: For new projects, the address of the site may not yet be confirmed. If there is a proposed/likely site address, please use this. If not, this column may be left blank.
Note on J21: Reprovided places refer to existing places that will continue to be delivered and will benefit from the project.
Note on M21: More details/examples: - Entirely new SEN unit within a school - Entirely new SEN unit within a school - Expansion of existing provision (e.g. additional places created through a new classroom) - Improvement of an existing provision (e.g. new equipment) - New facility within an existing provision (e.g. sensory room or changing facility) - Adapting existing provision to meet different needs - Accessibility - Other (please provide details in project description)
Note on N20: Where final costings are not yet known, you may choose to provide indicative figures in the funding columns. Recording information on this form does not signal or create a final commitment, but we do ask that LAs return the template to the best of their ability.
Note on R21: This does not include housing developer contribitions (which can be added to column Q). Additional funding sources may include Basic Need funding, council reserves, borrowing etc.