## Maintenance Programme of Works
Maintenance Programme of Works |  |  |  |  | Financial year |  | Financial year
Work type group | Work type | Name | Town | District | Start | Q | End | Q | Duration (Days) | Traffic Management | Other traffic management details | Length (m) | Estimated Area (m²) | USRN
Carriageway scheme | Resurfacing | A50 Markfield Road | Groby | Blaby | 2025/2026 | Q3 | 2025/2026 | Q3 | 19 | ROAD CLOSURE |  | 400
Carriageway scheme | Resurfacing | B676 from Buckminster Rd to Coston Rd | Buckminster | Melton | 2025/2026 | Q4 | 2025/2026 | Q4 | tbc | ROAD CLOSURE |  | 1100
Carriageway scheme | Resurfacing | A511 Bardon Road | Bardon | NWL | 2025/2026 | Q3 | 2025/2026 | Q3 | 17 | ROAD CLOSURE |  | 1200
Carriageway scheme | Resurfacing | A5460 Junction 21 Approach | Braunstone | Blaby | 2025/2027 | Q1 | 2025/2026 | Q1 | 29 | ROAD CLOSURE |  | 2100
Carriageway scheme | Resurfacing | A5199 Bull Head Street | Wigston | Oadby & Wigston | 2025/2026 | Q3 | 2025/2026 | Q3 | 18 | ROAD CLOSURE |  | 1100
Carriageway scheme | Retexturing | Cuckoo Hill & Stapleford Road | Freeby | Melton | 2025/2026 | Q4 | 2025/2026 | Q4 | TBC | TBC |  | TBC | TBC
Carriageway scheme | Retexturing | Atherstone Road | Ratcliffe Culey | Hinckley & Bosworth | 2025/2026 | Q4 | 2025/2026 | Q4 | TBC | TBC |  | TBC | TBC
Carriageway scheme | Retexturing | Keyham Lane East | Scraptoft | Harborough | 2025/2026 | Q4 | 2025/2026 | Q4 | TBC | TBC |  | TBC | TBC
Carriageway scheme | Retexturing | B4114 Coventry Road | Narborough & Cosby | Harborough | 2025/2026 | Q4 | 2025/2026 | Q4 | TBC | TBC |  | TBC | TBC
Carriageway scheme | Retexturing | B4114 King Edward Avenue & Coventry Road | Narborough | Harborough | 2025/2026 | Q4 | 2025/2026 | Q4 | TBC | TBC |  | TBC | TBC
Carriageway scheme | Retexturing | A607 Grantham Road | Waltham | Melton | 2025/2026 | Q4 | 2025/2026 | Q4 | TBC | TBC |  | TBC | TBC
Carriageway scheme | Retexturing | Manor Road | Medbourne | Harborough | 2025/2026 | Q4 | 2025/2026 | Q4 | TBC | TBC |  | TBC | TBC
Carriageway scheme | Retexturing | Rogues Lane | Hinckley | Hinckley & Bosworth | 2025/2026 | Q4 | 2025/2026 | Q4 | TBC | TBC |  | TBC | TBC
Carriageway scheme | Retexturing | B4116 Twycross Road | Snarestone | NWL | 2025/2026 | Q4 | 2025/2026 | Q4 | TBC | TBC |  | TBC | TBC
Carriageway scheme | Retexturing | Hoby Road | Thrussington | Charnwood | 2025/2026 | Q4 | 2025/2026 | Q4 | TBC | TBC |  | TBC | TBC
Carriageway scheme | Retexturing | Mountsorrel Lane | Sileby | Charnwood | 2025/2026 | Q4 | 2025/2026 | Q4 | TBC | TBC |  | TBC | TBC
Carriageway scheme | Retexturing | Bowden Road | Thorpe Langton | Harborough | 2025/2026 | Q4 | 2025/2026 | Q4 | TBC | TBC |  | TBC | TBC
Carriageway scheme | Retexturing | Rearsby Road | Rearsby | Charnwood | 2025/2026 | Q4 | 2025/2026 | Q4 | TBC | TBC |  | TBC | TBC
Carriageway scheme | Retexturing | Willesley Lane | Ashby | NWL | 2025/2026 | Q4 | 2025/2026 | Q4 | TBC | TBC |  | TBC | TBC
Carriageway scheme | Micro asphalt preservation | Chapel Fields | Swinford | Harborough | TBC | TBC | TBC | TBC | TBC | TBC |  | TBC | TBC
Carriageway scheme | Micro asphalt preservation | Willow Close | Moira | NWL | TBC | TBC | TBC | TBC | TBC | TBC |  | TBC | TBC
Carriageway scheme | Micro asphalt preservation | Somerset Close | Melton Mowbray | Melton | TBC | TBC | TBC | TBC | TBC | TBC |  | TBC | TBC
Carriageway scheme | Micro asphalt preservation | Hazelwood Crescent | Asfordby | Melton | TBC | TBC | TBC | TBC | TBC | TBC |  | TBC | TBC
Carriageway scheme | Micro asphalt preservation | The Woodlands | Market Harborough | Harborough | TBC | TBC | TBC | TBC | TBC | TBC |  | TBC | TBC
Carriageway scheme | Micro asphalt preservation | Frith Close | Glenfield | Blaby | TBC | TBC | TBC | TBC | TBC | TBC |  | TBC | TBC
Carriageway scheme | Micro asphalt preservation | Chatsworth Drive | Syston | Charnwood | TBC | TBC | TBC | TBC | TBC | TBC |  | TBC | TBC
Carriageway scheme | Micro asphalt preservation | Cranmer Drive | Syston | Charnwood | TBC | TBC | TBC | TBC | TBC | TBC |  | TBC | TBC
Carriageway scheme | Micro asphalt preservation | Dorset Drive | Melton Mowbray | Melton | TBC | TBC | TBC | TBC | TBC | TBC |  | TBC | TBC
Carriageway scheme | Micro asphalt preservation | Abbotts Close | Syston | Charnwood | TBC | TBC | TBC | TBC | TBC | TBC |  | TBC | TBC
Carriageway scheme | Micro asphalt preservation | Haddon Close | Syston | Charnwood | TBC | TBC | TBC | TBC | TBC | TBC |  | TBC | TBC
Carriageway scheme | Micro asphalt preservation | Swan Close | Melton Mowbray | Melton | TBC | TBC | TBC | TBC | TBC | TBC |  | TBC | TBC
Carriageway scheme | Micro asphalt preservation | Farriers Way | East Goscote | Charnwood | TBC | TBC | TBC | TBC | TBC | TBC |  | TBC | TBC
Major Structures | Bridge maintenance | Cosby Road | Broughton Astley | Harborough | TBC | TBC | TBC | TBC | TBC | TBC |  | N/A
Major Structures | Bridge maintenance | Brookside | Hinckley | Hinckley & Bosworth | TBC | TBC | TBC | TBC | TBC | TBC |  | N/A
Major Structures | Bridge maintenance | Park Hill Lane | Seagrave | Charnwood | TBC | TBC | TBC | TBC | TBC | TBC |  | N/A
Major Structures | Minor Bridge Repairs | Critical safety repairs as needed | Various | Various | TBC | TBC | TBC | TBC | TBC | TBC |  | N/A
Carriageway scheme | Surface dressing | EAST ROAD from Orchard Way - SD joint on west side of Wysall Lane | Wymeswold | Charnwood | TBC | TBC | TBC | TBC | TBC | TBC |  | 240 | 1472 | 6500539
Carriageway scheme | Surface dressing | LOUGHBOROUGH ROAD from near jnc Woodhouse Road to High Street incl bitmac speed humps | Quorn | Charnwood | TBC | TBC | TBC | TBC | TBC | TBC |  | 496 | 4730 | 6501014
Carriageway scheme | Surface dressing | HIGH STREET from Loughborough Road to surfacing joint at jnc Station Road incl most bitmac speed humps | Quorn | Charnwood | TBC | TBC | TBC | TBC | TBC | TBC |  | 332 | 2537 | 6500790
Carriageway scheme | Surface dressing | LEICESTER ROAD from Loughborough Road, Mountsorrel - Wood Road Roundabout | Quorn | Charnwood | TBC | TBC | TBC | TBC | TBC | TBC |  | 540 | 3348 | 6500946
Carriageway scheme | Surface dressing | LOUGHBOROUGH ROAD from HRA surfacing joint near One Ash House - One Ash rndbt at jnc A6 | Quorn | Charnwood | TBC | TBC | TBC | TBC | TBC | TBC |  | 252 | 2898 | 6501014
Carriageway scheme | Surface dressing | LOUGHBOROUGH ROAD from SD joint at Quorn Business Quarter near Granite Way Rbt - Leicester Road, Quorn | Mountsorrel | Charnwood | TBC | TBC | TBC | TBC | TBC | TBC |  | 307 | 1842 | 6501015
Carriageway scheme | Surface dressing | THE DRIFT from Stamford Road to SD joint near jnc Fosse Lane & The Drift Road | Sewstern | Melton | TBC | TBC | TBC | TBC | TBC | TBC |  | 2900 | 17110 | 24901385
Carriageway scheme | Surface dressing | BACK LANE from Main Street to The Drift | Sewstern | Melton | TBC | TBC | TBC | TBC | TBC | TBC |  | 870 | 2784 | 24901340
Carriageway scheme | Surface dressing | BESCABY LANE from jnc High Street to Mary Lane, Sproxton | Waltham | Melton | TBC | TBC | TBC | TBC | TBC | TBC |  | 590 | 2842 | 24900055
Carriageway scheme | Surface dressing | ROTHERBY LANE from new surfacing joint approx 50m North of Pasture Lane - Gaddesby Lane, Rotherby | Gaddesby | Melton | TBC | TBC | TBC | TBC | TBC | TBC |  | 1490 | 5215 | 24900635
Carriageway scheme | Surface dressing | LAYBY OFF A607 NR SPRING COTTAGES | Croxton Kerrial | Melton | TBC | TBC | TBC | TBC | TBC | TBC |  | 100 | 610 | 24902779
Carriageway scheme | Surface dressing | HARBOROUGH ROAD from Harborough Road, Billesdon to SD joint at New Inn village sign | Rolleston | Harborough | TBC | TBC | TBC | TBC | TBC | TBC |  | 1720 | 10664 | 16402341
Carriageway scheme | Surface dressing | COVENTRY ROAD from near jnc B114 to Broughton Way | Broughton Astley | Harborough | TBC | TBC | TBC | TBC | TBC | TBC |  | 720 | 5760 | 16400270
Carriageway scheme | Surface dressing | LEICESTER ROAD from joint near Hall Lane to joint near Bill Crane Way | Lutterworth | Harborough | TBC | TBC | TBC | TBC | TBC | TBC |  | 1460 | 10658 | 16400677
Carriageway scheme | Surface dressing | LUTTERWORTH ROAD from Kilworth Road to High Street | North Kilworth | Harborough | TBC | TBC | TBC | TBC | TBC | TBC |  | 865 | 5623 | 16400732
Carriageway scheme | Surface dressing | STATION ROAD from High Street to Elmcroft Road | North Kilworth | Harborough | TBC | TBC | TBC | TBC | TBC | TBC |  | 135 | 877 | 16401142
Carriageway scheme | Surface dressing | BROUGHTON WAY from Coventry Road to jnc Cosby Road | Broughton Astley | Harborough | TBC | TBC | TBC | TBC | TBC | TBC |  | 1330 | 10374 | 16400142
Carriageway scheme | Surface dressing | HARBOROUGH ROAD from near jnc A47 to Harborough Road, Rolleston | Billesdon | Harborough | TBC | TBC | TBC | TBC | TBC | TBC |  | 1320 | 7920 | 16402390
Carriageway scheme | Surface dressing | KETTERING ROAD from new surfacing joint east of Gores Lane to RS joint near Davidsons Rbt | Market Harborough | Harborough | TBC | TBC | TBC | TBC | TBC | TBC |  | 790 | 7900 | 16400622
Carriageway scheme | Surface dressing | LUBENHAM HILL from splitter island at crossing point near jnc Welland Park Road to splitter island just before rndbt at jnc Harvest Road | Market Harborough | Harborough | TBC | TBC | TBC | TBC | TBC | TBC |  | 490 | 3675 | 16400724
Carriageway scheme | Surface dressing | MAIN STREET from Peatling Road to Countesthorpe Road | Peatling Magna | Harborough | TBC | TBC | TBC | TBC | TBC | TBC |  | 1040 | 4992 | 16400771
Carriageway scheme | Surface dressing | MOWSLEY ROAD from Taylors Lane to Theddingworth Road, Mowsley | Theddingworth | Harborough | TBC | TBC | TBC | TBC | TBC | TBC |  | 2360 | 10148 | 16400882
Carriageway scheme | Surface dressing | ILLSTON LANE from jnc B6047 New Inn Lane to Ashlands Road, Illston | Illston on the Hill | Harborough | TBC | TBC | TBC | TBC | TBC | TBC |  | 1560 | 8112 | 16400605
Carriageway scheme | Surface dressing | THEDDINGWORTH ROAD from Mowsley Road, Theddingworth to Leicester Road | Mowsley | Harborough | TBC | TBC | TBC | TBC | TBC | TBC |  | 1480 | 7400 | 16401253
Carriageway scheme | Surface dressing | LUTTERWORTH ROAD from SD joint o/s Hillcrest near Palmers Garden Centre to Main Street | Ullesthorpe | Harborough | TBC | TBC | TBC | TBC | TBC | TBC |  | 1200 | 6600 | 16402071
Carriageway scheme | Surface dressing | GAULBY LANE from watercourse to 30mph signs in Kings Norton | Kings Norton | Harborough | TBC | TBC | TBC | TBC | TBC | TBC |  | 470 | 2350 | 16402396
Carriageway scheme | Surface dressing | GAULBY LANE from Burton Overy Road to watercourse past Gaulby Lodge Farm | Gaulby | Harborough | TBC | TBC | TBC | TBC | TBC | TBC |  | 980 | 3920 | 16402396
Carriageway scheme | Surface dressing | KILBY ROAD from jnc High Street to Fleckney Road, Kilby | Fleckney | Harborough | TBC | TBC | TBC | TBC | TBC | TBC |  | 2060 | 10094 | 16400631
Carriageway scheme | Surface dressing | CROSS ROADS from jnc B6047 New Inn Lane to Noseley Road, Illston on the Hill | Illston on the Hill | Harborough | TBC | TBC | TBC | TBC | TBC | TBC |  | 300 | 1000 | 16400290
Carriageway scheme | Surface dressing | NOSELEY ROAD from Cross Roads to Illston Lane near Illston | Illston on the Hill | Harborough | TBC | TBC | TBC | TBC | TBC | TBC |  | 760 | 2400 | 16400913
Carriageway scheme | Surface dressing | FROM LUTTERWORTH ROAD TO SWINFORD ROAD from jnc Lutterworth Road to jnc Swinford Road at Swinford Corner | Shawell | Harborough | TBC | TBC | TBC | TBC | TBC | TBC |  | 1780 | 7832 | 16401502
Carriageway scheme | Surface dressing | LUTTERWORTH ROAD from jnc Swinford Road to From Lutterworth Road to Swinford Road | Shawell | Harborough | TBC | TBC | TBC | TBC | TBC | TBC |  | 860 | 4300 | 16400739
Carriageway scheme | Surface dressing | STATION ROAD from jnc A4304 Kilworth Road to jnc Welford Road | Husbands Bosworth | Harborough | TBC | TBC | TBC | TBC | TBC | TBC |  | 1773 | 10684 | 16402150
Carriageway scheme | Surface dressing | MAIN STREET from SD joint at Meadow Farm - SD joint neat Top House | Thorpe Langton | Harborough | TBC | TBC | TBC | TBC | TBC | TBC |  | 169 | 1014 | 16402399
Carriageway scheme | Surface dressing | WALTON ROAD from Kimcote Road, Walton to Lutterworth Road, Kimcote | Kimcote | Harborough | TBC | TBC | TBC | TBC | TBC | TBC |  | 490 | 2450 | 16402123
Carriageway scheme | Surface dressing | KIMCOTE ROAD from 30mph Walton to Walton Road, Kimcote | Walton | Harborough | TBC | TBC | TBC | TBC | TBC | TBC |  | 480 | 2400 | 16400637
Carriageway scheme | Surface dressing | BELLFIELDS LANE from Kettering Road to Scotland Road incl speed humps | Market Harborough (Little Bowden) | Harborough | TBC | TBC | TBC | TBC | TBC | TBC |  | 155 | 883 | 16400088
Carriageway scheme | Surface dressing | MANOR ROAD from Main Street to Langton Road | Great Bowden | Harborough | TBC | TBC | TBC | TBC | TBC | TBC |  | 170 | 976 | 16400803
Carriageway scheme | Surface dressing | OAKS ROAD from Great Glen Road, Kings Norton to SD joint near jnc Washbrook Lane | Burton Overy | Harborough | TBC | TBC | TBC | TBC | TBC | TBC |  | 1300 | 7150 | 16401555
Carriageway scheme | Surface dressing | GREAT GLEN ROAD fron jnc Stretton Road to Oaks Road, Burton Overy | Kings Norton | Harborough | TBC | TBC | TBC | TBC | TBC | TBC |  | 1200 | 6600 | 16402397
Carriageway scheme | Surface dressing | FAIRFIELD ROAD from 20mph signs near jnc Leicester Road to splitter near jnc Goward Street incl bitmac speed humps | Market Harborough | Harborough | TBC | TBC | TBC | TBC | TBC | TBC |  | 620 | 4030 | 16400362
Carriageway scheme | Surface dressing | GOWARD STREET from jnc Fairfield Road to far end of speed hump at jnc Nelson Street | Market Harborough | Harborough | TBC | TBC | TBC | TBC | TBC | TBC |  | 110 | 660 | 16400451
Carriageway scheme | Surface dressing | MAIN STREET from joint near Coxs Lane / Middle Street - jnc Whatborough Road | Owston | Harborough | TBC | TBC | TBC | TBC | TBC | TBC |  | 359 | 1436 | 16400760
Carriageway scheme | Surface dressing | FARNDALE VIEW from jnc Lubenham Hill to road end incl bitmac speed humps | Market Harborough | Harborough | TBC | TBC | TBC | TBC | TBC | TBC |  | 500 | 3000 | 16402232
Carriageway scheme | Surface dressing | NEWTON LANE from near jnc A5199 Welford Road to S278 full width surfacing joint at new dvpt near Guthlaxton Way | Wigston | Oadby & Wigston | TBC | TBC | TBC | TBC | TBC | TBC |  | 690 | 4278 | 29200468
Carriageway scheme | Surface dressing | WIGSTON ROAD from joint near Garden Close - Joint near Rosemead Drive | Oadby | Oadby & Wigston | TBC | TBC | TBC | TBC | TBC | TBC |  | 298 | 2086 | 29200685
Carriageway scheme | Surface dressing | FENWICK ROAD from Florence Wragg Way to James Gavin Way | Oadby | Oadby & Wigston | TBC | TBC | TBC | TBC | TBC | TBC |  | 70 | 420 | 29200236
Carriageway scheme | Surface dressing | HAWKER ROAD from Wright Lane - end | Oadby | Oadby & Wigston | TBC | TBC | TBC | TBC | TBC | TBC |  | 186 | 1023 | 29200305
Carriageway scheme | Surface dressing | JAMES GAVIN WAY from Holbrook - Turning head near house No 6 | Oadby | Oadby & Wigston | TBC | TBC | TBC | TBC | TBC | TBC |  | 175 | 1005 | 29200347
Carriageway scheme | Surface dressing | PIPISTRELLE WAY from HRA joint at 2nd entrance to The Pastures - end | Oadby | Oadby & Wigston | TBC | TBC | TBC | TBC | TBC | TBC |  | 190 | 1064 | 29200890
Carriageway scheme | Surface dressing | SMORE SLADE HILLS from Florence Wragg Way - Turning head near house No 57 | Oadby | Oadby & Wigston | TBC | TBC | TBC | TBC | TBC | TBC |  | 323 | 1744 | 29200813
Carriageway scheme | Surface dressing | BOULTON COURT from Smore Slade Hills - end at house No 19 | Oadby | Oadby & Wigston | TBC | TBC | TBC | TBC | TBC | TBC |  | 68 | 374 | 29200786
Carriageway scheme | Surface dressing | RAWLINGS COURT from Smore Slade Hills - turning head near house No 3 | Oadby | Oadby & Wigston | TBC | TBC | TBC | TBC | TBC | TBC |  | 41 | 226 | 29200812
Carriageway scheme | Surface dressing | DEVONIA ROAD from Harker Road - End | Oadby | Oadby & Wigston | TBC | TBC | TBC | TBC | TBC | TBC |  | 234 | 1444 | 29200191
Carriageway scheme | Surface dressing | THE PASTURES from Pipistrelle Way - Pipistrelle Way, including all side roads up to blocks | Oadby | Oadby & Wigston | TBC | TBC | TBC | TBC | TBC | TBC |  | 254 | 1397 | 29200891
Carriageway scheme | Surface dressing | PALMERSTONE WAY from City boundary to splitter for A6 rbt | Oadby | Oadby & Wigston | TBC | TBC | TBC | TBC | TBC | TBC |  | 305 | 2990 | 29200796
Carriageway scheme | Surface dressing | MEADOWCOURT ROAD from Stoughton Drive South to before TH | Oadby | Oadby & Wigston | TBC | TBC | TBC | TBC | TBC | TBC |  | 430 | 4130 | 29200435
Carriageway scheme | Surface dressing | KNIGHTON GRANGE ROAD from Stoughton Drive South to City boundary | Oadby | Oadby & Wigston | TBC | TBC | TBC | TBC | TBC | TBC |  | 585 | 5325 | 29200371
Carriageway scheme | Surface dressing | GLEBE ROAD from Knighton Grange Road to just before A6 junction | Oadby | Oadby & Wigston | TBC | TBC | TBC | TBC | TBC | TBC |  | 480 | 4050 | 29200267
Carriageway scheme | Surface dressing | GLEBE CLOSE from Glebe Road to end (highway extents only) | Oadby | Oadby & Wigston | TBC | TBC | TBC | TBC | TBC | TBC |  | 85 | 480 | 29200265
Carriageway scheme | Surface dressing | ST ANDREWS DRIVE from Stoughton Drive South to just before TH | Oadby | Oadby & Wigston | TBC | TBC | TBC | TBC | TBC | TBC |  | 172 | 1307 | 29200550
Carriageway scheme | Surface dressing | THE FAIRWAY from Gartree Road to Ringers Spinney | Oadby | Oadby & Wigston | TBC | TBC | TBC | TBC | TBC | TBC |  | 980 | 7350 | 29200618
Carriageway scheme | Surface dressing | RINGERS SPINNEY from The Fairway to The Fairway | Oadby | Oadby & Wigston | TBC | TBC | TBC | TBC | TBC | TBC |  | 415 | 3110 | 29200538
Carriageway scheme | Surface dressing | OAKS WAY from The Fairway to end | Oadby | Oadby & Wigston | TBC | TBC | TBC | TBC | TBC | TBC |  | 130 | 740 | 29200663
Carriageway scheme | Surface dressing | MANOR ROAD from Soughton Drive South to Stoughton Road | Oadby | Oadby & Wigston | TBC | TBC | TBC | TBC | TBC | TBC |  | 1150 | 10925 | 29200421
Carriageway scheme | Surface dressing | COSBY ROAD from jnc Willoughby Road to Station Road (Remedials to 2023 dressing) | Countesthorpe | Blaby | TBC | TBC | TBC | TBC | TBC | TBC |  | 75 | 474 | 2800259
Carriageway scheme | Surface dressing | STATION ROAD from Cosby Road to HRA joint near jnc Green Lane incl bitmac speed humps (Remedials to 2023 dressing) | Countesthorpe | Blaby | TBC | TBC | TBC | TBC | TBC | TBC |  | 184 | 1135 | 2801022
Carriageway scheme | Surface dressing | HOSPITAL LANE from near mini-rndbt at jnc Welford Road to near traffic lights at jnc Leicester Road, Countesthorpe (Remedial to 2023 dressing) | Blaby | Blaby | TBC | TBC | TBC | TBC | TBC | TBC |  | 466 | 2840 | 2800562
Carriageway scheme | Surface dressing | WILLOUGHBY ROAD From 30mph Countesthorpe - Willoughby Road, Whetstone at Bambury Lane Jct | Countesthorpe | Blaby | TBC | TBC | TBC | TBC | TBC | TBC |  | 370 | 1887 | 2801195
Carriageway scheme | Surface dressing | WILLOUGHBY ROAD from Willoughby Road, Countesthorpe at Bambury Lane Jct to Countesthorpe Road, Willoughby Waterlys | Whetstone | Blaby | TBC | TBC | TBC | TBC | TBC | TBC |  | 1102 | 5620 | 2801549
Carriageway scheme | Surface dressing | COVENTRY ROAD from SD joint near 30mph - Joint near Butler Close | Sharnford | Blaby | TBC | TBC | TBC | TBC | TBC | TBC |  | 66 | 429 | 2800271
Carriageway scheme | Surface dressing | LEICESTER ROAD from Joint at Sharnford Village Hall - joint at River Bridge | Sharnford | Blaby | TBC | TBC | TBC | TBC | TBC | TBC |  | 138 | 1173 | 2800658
Carriageway scheme | Surface dressing | STATION ROAD from New Road Roundabout - Stanton Road, Elmesthorpe | Stoney Stanton | Blaby | TBC | TBC | TBC | TBC | TBC | TBC |  | 1273 | 9038 | 2801018
Carriageway scheme | Surface dressing | STANTON ROAD from Station Road, Stoney Stanton - Full width surfacing joint on east side of M69 Bridge | Elmesthorpe | Blaby | TBC | TBC | TBC | TBC | TBC | TBC |  | 351 | 2270 | 2801011
Carriageway scheme | Surface dressing | NEW ROAD from Long Street Mini-Rbt - Hinckley Road Mini-Rbt | Stoney Stanton | Blaby | TBC | TBC | TBC | TBC | TBC | TBC |  | 173 | 1038 | 2800797
Carriageway scheme | Surface dressing | NARBOROUGH ROAD SOUTH (Northbound) from north of jnc Narborough Road South West Service Road at traffic lights - Start of new HRA approaching traffic lights near Leics City boundary at jnc Braunstone Lane (Both Lanes) | Braunstone | Blaby | TBC | TBC | TBC | TBC | TBC | TBC |  | 1500 | 10875 | 2800789
Carriageway scheme | Surface dressing | NARBOROUGH ROAD SOUTH (Southbound) from End of HRA at Braunstone Lane Signals - start of HFS at Braunstone village sign near traffic lights at jnc Narborough Road South West Service Road (Both Lanes) | Braunstone | Blaby | TBC | TBC | TBC | TBC | TBC | TBC |  | 1500 | 10875 | 2800789
Carriageway scheme | Surface dressing | BROUGHTON ROAD from HGV entrance to Cobley Transport nearest to B4114 Coventry Road - Long Street Mini-Roundabout | Stoney Stanton | Blaby | TBC | TBC | TBC | TBC | TBC | TBC |  | 1850 | 13875 | 2800136
Carriageway scheme | Surface dressing | SAPCOTE ROAD from Long Street to Grace Road, Sapcote | Stoney Stanton | Blaby | TBC | TBC | TBC | TBC | TBC | TBC |  | 765 | 4781 | 2800944
Carriageway scheme | Surface dressing | LONG STREET from mini-rndbt at jnc New Road to Sapcote Road | Stoney Stanton | Blaby | TBC | TBC | TBC | TBC | TBC | TBC |  | 88 | 629 | 2800687
Carriageway scheme | Surface dressing | GRACE ROAD from Sapcote Road, Stoney Stanton to jnc Leicester Road, Sapcote | Sapcote | Blaby | TBC | TBC | TBC | TBC | TBC | TBC |  | 646 | 4038 | 2800433
Carriageway scheme | Surface dressing | SHARNFORD ROAD from Leicester Road - SD joint at Pougher Close | Sapcote | Blaby | TBC | TBC | TBC | TBC | TBC | TBC |  | 371 | 2170 | 2800961
Carriageway scheme | Surface dressing | LEICESTER ROAD from HRA / SD joint near 30/50 signs at Earl Shilton - Splitter for A47 Roundabout | Earl Shilton | Hinckley & Bosworth | TBC | TBC | TBC | TBC | TBC | TBC |  | 1261 | 10004 | 17401863
Carriageway scheme | Surface dressing | NORMANDY WAY, Stoke Road (Morrisons) Roundabout - Wykin Road Roundabout | Hinckley | Hinckley & Bosworth | TBC | TBC | TBC | TBC | TBC | TBC |  | 726 | 8422 | 17401768
Carriageway scheme | Surface dressing | WELLSBOROUGH ROAD from Bosworth Road - splitter for Pipistrelle Drive Roundabout | Market Bosworth | Hinckley & Bosworth | TBC | TBC | TBC | TBC | TBC | TBC |  | 978 | 5575 | 17401368
Carriageway scheme | Surface dressing | TWYCROSS ROAD from Main Road (including spur road) - Twycross Lane, Bilstone | Shackerstone (Bilstone) | Hinckley & Bosworth | TBC | TBC | TBC | TBC | TBC | TBC |  | 310 | 1281 | 17401324
Carriageway scheme | Surface dressing | ATHERSTONE ROAD from SD joint at 50mph north of jnc Upton Lane to Atherstone Road, Sheepy (Sibson) | Witherley (Fenny Drayton) | Hinckley & Bosworth | TBC | TBC | TBC | TBC | TBC | TBC |  | 443 | 3323 | 17400055
Carriageway scheme | Surface dressing | TWYCROSS LANE from 30mph Bilstone to Bilstone Road, Twycross incl passing bays | Shackerstone (Bilstone) | Hinckley & Bosworth | TBC | TBC | TBC | TBC | TBC | TBC |  | 940 | 4324 | 17401320
Carriageway scheme | Surface dressing | BILSTONE ROAD from Twycross Lane, Bilstone to jnc B4116 Ashby Road incl passing bays | Twycross | Hinckley & Bosworth | TBC | TBC | TBC | TBC | TBC | TBC |  | 1580 | 7426 | 17400146
Carriageway scheme | Surface dressing | NORMANDY WAY, from end if new HRA for Greenfinch Road roundabout - Roston Drive (Triumph) roundabout | Hinckley | Hinckley & Bosworth | TBC | TBC | TBC | TBC | TBC | TBC |  | 588 | 5802 | 17401768
Carriageway scheme | Surface dressing | SHARNFORD ROAD from Lychgate Lane Jct for 100m eastbound towards Sharnford (remedial to 2023 dressing) | Aston Flamville | Hinckley & Bosworth | TBC | TBC | TBC | TBC | TBC | TBC |  | 100 | 560 | 2800960
Carriageway scheme | Surface dressing | RATBY LANE from 1st Property 'Hill View' - Thornton Lane, Markfield (remedial to 2023 surface dressing) | Markfield | Hinckley & Bosworth | TBC | TBC | TBC | TBC | TBC | TBC |  | 392 | 2835 | 17401039
Carriageway scheme | Surface dressing | THORNTON LANE from Ratby Lane, Markfield - M1 Bridge (remedial to 2023 surface dressing) | Markfield | Hinckley & Bosworth | TBC | TBC | TBC | TBC | TBC | TBC |  | 600 | 4060 | 17401909
Carriageway scheme | Surface dressing | SHEEPY ROAD from Flax Lane to Cow warning sign at start HRA surface (remedials from 2023 dressing) | Twycross | Hinckley & Bosworth | TBC | TBC | TBC | TBC | TBC | TBC |  | 147 | 893 | 17401138
Carriageway scheme | Surface dressing | MELBOURNE ROAD from Nottingham Road - SD joint south of Hill Top Cottage | Staunton Harold | NWL | TBC | TBC | TBC | TBC | TBC | TBC |  | 1062 | 7115 | 28501805
Carriageway scheme | Surface dressing | BREEDON LANE from Worthington Lane, Breedon - 30mph Worthington | Worthington | NWL | TBC | TBC | TBC | TBC | TBC | TBC |  | 1066 | 4690 | 28500147
Carriageway scheme | Surface dressing | BREEDON LANE from 30mph Worthington - Long Hedge Lane Crossroads | Worthington | NWL | TBC | TBC | TBC | TBC | TBC | TBC |  | 80 | 380 | 28500147
Carriageway scheme | Surface dressing | NEWBOLD LANE - SD recent surfacing between cemetery & jnc Main Street | Worthington | NWL | TBC | TBC | TBC | TBC | TBC | TBC |  | 160 | 688 | 28500714
Carriageway scheme | Surface dressing | ABBOTTS OAK DRIVE from Greenhill Road to Meadow Lane | Coalville | NWL | TBC | TBC | TBC | TBC | TBC | TBC |  | 665 | 3790 | 28500005
Carriageway scheme | Surface dressing | CASTLE ROCK DRIVE from Abbotts Oak Drive to Oakham Drive including road and turning head area down to house No 61 | Coalville | NWL | TBC | TBC | TBC | TBC | TBC | TBC |  | 810 | 4615 | 28500198
Carriageway scheme | Surface dressing | ST DAVIDS CRECENT from Castle Rock Drive to Abbotts Oak Drive | Coalville | NWL | TBC | TBC | TBC | TBC | TBC | TBC |  | 570 | 3135 | 28500879
Carriageway scheme | Surface dressing | THIRLMERE from St Davids Crescent to end or just before turning head at house No 3. | Coalville | NWL | TBC | TBC | TBC | TBC | TBC | TBC |  | 90 | 540 | 28501080
Carriageway scheme | Surface dressing | GRASMERE from St Davids Crescent to end including turning head | Coalville | NWL | TBC | TBC | TBC | TBC | TBC | TBC |  | 120 | 700 | 28500403
Carriageway scheme | Surface dressing | OAKHAM DRIVE from Castle Road Drive to Greenhill Road | Coalville | NWL | TBC | TBC | TBC | TBC | TBC | TBC |  | 728 | 4004 | 28500740
Carriageway scheme | Surface dressing | WILLOW GREEN from Oakham Drive to end including roundabout and turning head | Coalville | NWL | TBC | TBC | TBC | TBC | TBC | TBC |  | 222 | 1100 | 28501178
Carriageway scheme | Surface dressing | STAMFORD DRIVE from Oakham Drive to Greenhill Road, including spur road and turning head covering houses 9 - 39 | Coalville | NWL | TBC | TBC | TBC | TBC | TBC | TBC |  | 485 | 2715 | 28500971
Carriageway scheme | Surface dressing | LANCASTER CLOSE from Stamford Drive to end including turning head | Coalville | NWL | TBC | TBC | TBC | TBC | TBC | TBC |  | 85 | 498 | 28500540
Carriageway scheme | Surface dressing | YORK PLACE from Stamford Drive to just before turning heads at house No 20 | Coalville | NWL | TBC | TBC | TBC | TBC | TBC | TBC |  | 128 | 705 | 28501210
Carriageway scheme | Surface dressing | ROCHDALE CRESCENT from Stamford Drive to Stamford Drive | Coalville | NWL | TBC | TBC | TBC | TBC | TBC | TBC |  | 260 | 1430 | 28500851
Carriageway scheme | Surface dressing | BELGRAVE CLOSE from Rochdale Crescent to end including turning head | Coalville | NWL | TBC | TBC | TBC | TBC | TBC | TBC |  | 97 | 505 | 28500101
Carriageway scheme | Surface dressing | SEAGRAVE CLOSE from Rochdale Crescent to end including turning head | Coalville | NWL | TBC | TBC | TBC | TBC | TBC | TBC |  | 70 | 630 | 28500914
Carriageway scheme | Surface dressing | STRETTON DRIVE from Oakham Drive to just before turning heads at house No 22 | Coalville | NWL | TBC | TBC | TBC | TBC | TBC | TBC |  | 150 | 750 | 28500103
Carriageway scheme | Surface dressing | TWYFORD CLOSE from Oakham Drive to end including turning head | Coalville | NWL | TBC | TBC | TBC | TBC | TBC | TBC |  | 53 | 265 | 28501111
Carriageway scheme | Surface dressing | BELTON CLOSE from Oakham Drive to end including turning head | Coalville | NWL | TBC | TBC | TBC | TBC | TBC | TBC |  | 56 | 310 | 28500103
Carriageway scheme | Roadmender | Various reactive works | Various | Various | TBC | TBC | TBC | TBC | TBC | TBC |  | TBC | TBC
Environmental | Flood alleviation | Market Harborough, Welland Park Road | Market Harborough | Harborough | TBC | TBC | TBC | TBC | TBC | TBC |  | TBC | TBC
Environmental | Flood alleviation | Paddys Lane B676 Six Hills/Melton Road | Melton | Melton | TBC | TBC | TBC | TBC | TBC | TBC |  | TBC | TBC
Environmental | Flood alleviation | London Road, Great Glen | Great Glen | Harborough | TBC | TBC | TBC | TBC | TBC | TBC |  | TBC | TBC
Environmental | Flood alleviation | Whetstone Warwick Road | Whetstone | Blaby | TBC | TBC | TBC | TBC | TBC | TBC |  | TBC | TBC
Environmental | Flood alleviation | Enderby Leicester Road | Enderby | Blaby | TBC | TBC | TBC | TBC | TBC | TBC |  | TBC | TBC
Environmental | Flood alleviation | Packington Babelake Street | Packington | NWL | TBC | TBC | TBC | TBC | TBC | TBC |  | TBC | TBC
Environmental | Flood alleviation | Burton Overy Town Street | Burton Overy | Harborough | TBC | TBC | TBC | TBC | TBC | TBC |  | TBC | TBC
Environmental | Flood alleviation | Shenton, Shenton Lane/Fenn Lanes | Shenton | Hinckley & Bosworth | TBC | TBC | TBC | TBC | TBC | TBC |  | TBC | TBC
Environmental | Culverts | Blackfordby Main Street | Blackfordby | NWL | TBC | TBC | TBC | TBC | TBC | TBC |  | TBC | TBC
Environmental | Culverts | Newton Burgoland Snarestone Road | Newton Burgoland | NWL | TBC | TBC | TBC | TBC | TBC | TBC |  | TBC | TBC
Environmental | Culverts | Redmile Wood Lane | Redmile | Melton | TBC | TBC | TBC | TBC | TBC | TBC |  | TBC | TBC
Environmental | Culverts | Osbaston Lount Road | Osbaston | Hinckley & Bosworth | TBC | TBC | TBC | TBC | TBC | TBC |  | TBC | TBC
Environmental | Culverts | Kibworth New Road | Kibworth | Harborough | TBC | TBC | TBC | TBC | TBC | TBC |  | TBC | TBC
Street lighting | Street lighting | Market Harborough flood light replacement | Market Harborough | Harborough | TBC | TBC | TBC | TBC | TBC | TBC |  | N/A | N/A
Street lighting | Street lighting | Lubbersthorpe Way | Braunstone | Blaby | TBC | TBC | TBC | TBC | TBC | TBC |  | N/A | N/A
Street lighting | Street lighting | Known cable faults | various | Various | TBC | TBC | TBC | TBC | TBC | TBC |  | N/A | N/A
Street lighting | Street lighting | Replacement of heritage lanterns | Various | Various | TBC | TBC | TBC | TBC | TBC | TBC |  | N/A | N/A
Street lighting | Street lighting | Structural testing replacement | Various | Various | TBC | TBC | TBC | TBC | TBC | TBC |  | N/A | N/A
Street lighting | Street lighting | Son developer lanter replacement | Various | Various | TBC | TBC | TBC | TBC | TBC | TBC |  | N/A | N/A
Traffic Signals | Traffic Signals Renewal | High Street/King Street | Sileby | Charnwood | 2025/2026 | Q2 | 2025/2026 | Q2 | 5 | TBC |  | N/A | N/A
Traffic Signals | Traffic Signals Renewal | High Street/Belvoir Road | Coalville | NWL | 2025/2026 | Q2 | 2025/2026 | Q2 | 3 | TBC |  | N/A | N/A
Traffic Signals | Traffic Signals Renewal | Market Street, Melton | Melton | Melton | 2025/2026 | Q1 | 2025/2026 | Q1 | 10 | TBC |  | N/A | N/A
Traffic Signals | Traffic Signals Renewal | London Road/Forest Road | Hinckley | Hinckley & Bosworth | 2025/2026 | Q3 | 2025/2026 | Q3 | 7 | TBC |  | N/A | N/A
Traffic Signals | Traffic Signals Renewal | Ashby Road junction | Loughborough | Charnwood | 2025/2026 | Q1 | 2025/2026 | Q1 | 8 | TBC |  | N/A | N/A
Traffic Signals | Traffic Signals Renewal | Shelthorpe Road | Loughborough | Charnwood | 2025/2026 | Q1 | 2025/2026 | Q1 | 4 | TBC |  | N/A | N/A
Traffic Signals | Traffic Signals Renewal | Coventry Road, Sport Centre Access | Lutterworth | Harborough | 2025/2026 | Q2 | 2025/2026 | Q2 | 10 | TBC |  | N/A | N/A
Traffic Signals | Traffic Signals Renewal | Barkby Lane, Duck Pond Lane | Syston | Charnwood | 2025/2026 | Q2 | 2025/2026 | Q2 | 10 | TBC |  | N/A | N/A
Carriageway scheme | Patching | Barrow Road | Quorn - RF (MH) | Charnwood | 2025/2026 | Q1 | 2025/2026 | Q1 | 4 | ROAD CLOSURE | off peak (9-3) cones,(t'lights ( 1st day) | TBC | TBC
Carriageway scheme | Patching | Barrow Road | Barrow Upon Soar | Charnwood | 2025/2026 | Q1 | 2025/2026 | Q1 | 4 | ROAD CLOSURE | off peak (9-3) cones,(t'lights ( 1st day) | TBC | TBC
Carriageway scheme | Patching | Bridge Street | Barrow Upon Soar | Charnwood | 2025/2026 | Q1 | 2025/2026 | Q1 | 4 | ROAD CLOSURE | off peak (9-3) cones,(t'lights ( 1st day) | TBC | TBC
Carriageway scheme | Patching | Park Road | Loughborough - AK (JD) | Charnwood | 2025/2026 | Q1 | 2025/2026 | Q1 | 3 | ROAD CLOSURE | Nights, cones | TBC | TBC
Carriageway scheme | Patching | Access Rd from Prk Rd | Loughborough | Charnwood | 2025/2026 | Q1 | 2025/2026 | Q1 | 3 | ROAD CLOSURE | Nights, cones | TBC | TBC
Carriageway scheme | Patching | Belton Road | Loughborough - RF (JD) | Charnwood | 2025/2026 | Q1 | 2025/2026 | Q1 | 1 | ROAD CLOSURE | Nights | TBC | TBC
Carriageway scheme | Patching | Woodmarket | Lutterworth - TP (SG) | Harborough | 2025/2026 | Q1 | 2025/2026 | Q1 | 10 | ROAD CLOSURE | Sch hols, cones | TBC | TBC
Carriageway scheme | Patching | Stoney Hollow | Lutterworth | Harborough | 2025/2026 | Q1 | 2025/2026 | Q1 | 10 | ROAD CLOSURE | Sch hols, cones | TBC | TBC
Carriageway scheme | Patching | Woodway Road | Lutterworth | Harborough | 2025/2026 | Q1 | 2025/2026 | Q1 | 10 | ROAD CLOSURE | Sch hols, cones | TBC | TBC
Carriageway scheme | Patching | Spring close | Lutterworth | Harborough | 2025/2026 | Q1 | 2025/2026 | Q1 | 10 | ROAD CLOSURE | Sch hols, cones | TBC | TBC
Carriageway scheme | Patching | Orchard Road | Lutterworth | Harborough | 2025/2026 | Q1 | 2025/2026 | Q1 | 10 | ROAD CLOSURE | Sch hols, cones | TBC | TBC
Carriageway scheme | Patching | Moorbarns | Lutterworth | Harborough | 2025/2026 | Q1 | 2025/2026 | Q1 | 10 | ROAD CLOSURE | Sch hols, cones | TBC | TBC
Carriageway scheme | Patching | Ryderway | Lutterworth | Harborough | 2025/2026 | Q1 | 2025/2026 | Q1 | 10 | ROAD CLOSURE | Sch hols, cones | TBC | TBC
Carriageway scheme | Patching | Merton Way | Lutterworth | Harborough | 2025/2026 | Q1 | 2025/2026 | Q1 | 10 | ROAD CLOSURE | Sch hols, cones | TBC | TBC
Carriageway scheme | Patching | De Verdon Road | Lutterworth | Harborough | 2025/2026 | Q1 | 2025/2026 | Q1 | 10 | ROAD CLOSURE | Sch hols, cones | TBC | TBC
Carriageway scheme | Patching | Rugby Road | Cotesbach | Harborough | 2025/2026 | Q1 | 2025/2026 | Q1 | 1 | 2 WAY LIGHTS |  | TBC | TBC
Carriageway scheme | Patching | A46 Slip Road | Wanlip | Charnwood | 2025/2026 | Q1 | 2025/2026 | Q1 | 1 | ROAD CLOSURE |  | TBC | TBC
Carriageway scheme | Patching | Leicester Road | Anstey | Charnwood | 2025/2026 | Q1 | 2025/2026 | Q1 | 1 | LANE CLOSURE |  | TBC | TBC
Carriageway scheme | Patching | Leicester Road | Loughborough - AK (MH) | Charnwood | 2025/2026 | Q1 | 2025/2026 | Q1 | 11 | ROAD CLOSURE | cones - Nights | TBC | TBC
Carriageway scheme | Patching | Southfield Road | Loughborough | Charnwood | 2025/2026 | Q1 | 2025/2026 | Q1 | 10 | ROAD CLOSURE | cones - Nights | TBC | TBC
Carriageway scheme | Patching | Shelthorpe Road | Loughborough | Charnwood | 2025/2026 | Q1 | 2025/2026 | Q1 | 11 | ROAD CLOSURE | cones - Nights | TBC | TBC
Carriageway scheme | Patching | Beech Road | Loughborough | Charnwood | 2025/2026 | Q1 | 2025/2026 | Q1 | 10 | ROAD CLOSURE | cones - Nights | TBC | TBC
Carriageway scheme | Patching | Barrow Street | Loughborough | Charnwood | 2025/2026 | Q1 | 2025/2026 | Q1 | 10 | ROAD CLOSURE | cones - Nights | TBC | TBC
Carriageway scheme | Patching | Sage Cross St | Melton Mowbray - RF (GS) | Melton | 2025/2026 | Q1 | 2025/2026 | Q1 | 2 | ROAD CLOSURE | cones -NIGHTS | TBC | TBC
Carriageway scheme | Patching | King Street | Melton Mowbray | Melton | 2025/2026 | Q1 | 2025/2026 | Q1 | 2 | ROAD CLOSURE | cones -NIGHTS | TBC | TBC
Carriageway scheme | Patching | Chapel Street | Melton Mowbray - RF (GS) | Melton | 2025/2026 | Q1 | 2025/2026 | Q1 | 1 | ROAD CLOSURE | cones -NIGHTS | TBC | TBC
Carriageway scheme | Patching | King Street | Melton Mowbray | Melton | 2025/2026 | Q1 | 2025/2026 | Q1 | 1 | ROAD CLOSURE | cones -NIGHTS | TBC | TBC
Carriageway scheme | Patching | Mill Street | Melton Mowbray - RF (GS) | Melton | 2025/2026 | Q1 | 2025/2026 | Q1 | 2 | ROAD CLOSURE | NIGHTS | TBC | TBC
Carriageway scheme | Patching | Regent Street | Melton Mowbray | Melton | 2025/2026 | Q1 | 2025/2026 | Q1 | 2 | ROAD CLOSURE | NIGHTS | TBC | TBC
Carriageway scheme | Patching | Brook Street | Melton Mowbray | Melton | 2025/2026 | Q1 | 2025/2026 | Q1 | 2 | ROAD CLOSURE | NIGHTS | TBC | TBC
Carriageway scheme | Patching | Whaddon Drive | Loughborough | Charnwood | 2025/2026 | Q1 | 2025/2026 | Q1 | 1 | GIVE/TAKE |  | TBC | TBC
Carriageway scheme | Patching | Rugby Road | Burbage - TP (WS) | Hinckley & Bosworth | 2025/2026 | Q1 | 2025/2026 | Q1 | 7 | ROAD CLOSURE | Nights, Lane Closure | TBC | TBC
Carriageway scheme | Patching | Roundabout Rugby Rd | Burbage | Hinckley & Bosworth | 2025/2026 | Q1 | 2025/2026 | Q1 | 5 | ROAD CLOSURE | Nights, Lane Closure | TBC | TBC
Carriageway scheme | Patching | Canberra Way | Burbage | Hinckley & Bosworth | 2025/2026 | Q1 | 2025/2026 | Q1 | 5 | ROAD CLOSURE | Nights, Lane Closure | TBC | TBC
Carriageway scheme | Patching | Lutterworth Road | Arnesby - TP (SG) | Harborough | 2025/2026 | Q1 | 2025/2026 | Q1 | 4 | ROAD CLOSURE | lights, cones | TBC | TBC
Carriageway scheme | Patching | Leicester Road | Loughborough | Charnwood | 2025/2026 | Q1 | 2025/2026 | Q1 | 1 | STOP/GO |  | TBC | TBC
Carriageway scheme | Patching | Richmond Road | Ibstock - RF (MH) | NWL | 2025/2026 | Q1 | 2025/2026 | Q1 | 3 | ROAD CLOSURE | 2 way lights. | TBC | TBC
Carriageway scheme | Patching | Richmond Road | Donington le Heath | NWL | 2025/2026 | Q1 | 2025/2026 | Q1 | 3 | ROAD CLOSURE | 2 way lights. | TBC | TBC
Carriageway scheme | Patching | Breakback Road | Woodhouse Eaves AK- (MH) | Charnwood | 2025/2026 | Q1 | 2025/2026 | Q1 | 2 | ROAD CLOSURE |  | TBC | TBC
Carriageway scheme | Patching | Woodhouse Lane | Loughborough | Charnwood | 2025/2026 | Q1 | 2025/2026 | Q1 | 2 | ROAD CLOSURE |  | TBC | TBC
Carriageway scheme | Patching | Grove Road | Whetstone - TP (JD) | Blaby | 2025/2026 | Q1 | 2025/2026 | Q1 | 2 | ROAD CLOSURE | 2 x weekends | TBC | TBC
Carriageway scheme | Patching | Roundabout junction with Brook St | Whetsone | Blaby | 2025/2026 | Q1 | 2025/2026 | Q1 | 2 | ROAD CLOSURE | 2 x weekends | TBC | TBC
Carriageway scheme | Patching | Broughton Way | Sutton in the Elms | Harborough | 2025/2026 | Q1 | 2025/2026 | Q1 | 1 | MULTIWAY LIGHTS | Nights | TBC | TBC
Carriageway scheme | Patching | Ashby Road | Hinckley | Hinckley & Bosworth | 2025/2026 | Q1 | 2025/2026 | Q1 | 1 | MOBILE LANE | Closure | TBC | TBC
Carriageway scheme | Patching | Normandy Way | Hinckley | Hinckley & Bosworth | 2025/2026 | Q1 | 2025/2026 | Q1 | 1 | MOBILE LANE | Closure | TBC | TBC
Carriageway scheme | Patching | Station Road | Bagworth - TP (SG) | Hinckley & Bosworth | 2025/2026 | Q1 | 2025/2026 | Q1 | 16 | ROAD CLOSURE | Off Peak, | TBC | TBC
Carriageway scheme | Patching | Northfield | Bagworth | Hinckley & Bosworth | 2025/2026 | Q1 | 2025/2026 | Q1 | 16 | ROAD CLOSURE | e) | TBC | TBC
Carriageway scheme | Patching | Station Terrace | Bagworth | Hinckley & Bosworth | 2025/2026 | Q1 | 2025/2026 | Q1 | 16 | ROAD CLOSURE | e) | TBC | TBC
Carriageway scheme | Patching | Durham Close | Bagworth | Hinckley & Bosworth | 2025/2026 | Q1 | 2025/2026 | Q1 | 16 | ROAD CLOSURE |  | TBC | TBC
Carriageway scheme | Patching | Lime Grove | Bagworth | Hinckley & Bosworth | 2025/2026 | Q1 | 2025/2026 | Q1 | 16 | ROAD CLOSURE |  | TBC | TBC
Carriageway scheme | Patching | Barlestone Road | Bagworth | Hinckley & Bosworth | 2025/2026 | Q1 | 2025/2026 | Q1 | 16 | ROAD CLOSURE |  | TBC | TBC
Carriageway scheme | Patching | Main Street | Bagworth | Hinckley & Bosworth | 2025/2026 | Q1 | 2025/2026 | Q1 | 16 | ROAD CLOSURE |  | TBC | TBC
Carriageway scheme | Patching | Quorn Mountsorrel By Pass | Barrow Upon Soar | Charnwood | 2025/2026 | Q1 | 2025/2026 | Q1 | 1 | MOBILE LANE | closure 09.00 - 15.00 | TBC | TBC
Carriageway scheme | Patching | Quorn Mountsorrel By Pass | Mountsorrel | Charnwood | 2025/2026 | Q1 | 2025/2026 | Q1 | 1 | MOBILE LANE | closure 09.00 - 15.00 | TBC | TBC
Carriageway scheme | Patching | Quorn Mountsorrel By Pass | Rothley | Charnwood | 2025/2026 | Q1 | 2025/2026 | Q1 | 1 | MOBILE LANE | closure 09.00 - 15.00 | TBC | TBC
Carriageway scheme | Patching | Loughborough Road | Quorn | Charnwood | 2025/2026 | Q1 | 2025/2026 | Q1 | 1 | MOBILE LANE | closure 09.00 - 15.00 | TBC | TBC
Carriageway scheme | Patching | Stapleford Road | Stapleford - RF (MH) | Melton | 2025/2026 | Q2 | 2025/2026 | Q2 | 2 | ROAD CLOSURE | (normal working) Stop/Go (off peak) | TBC | TBC
Carriageway scheme | Patching | Bradgate Road | Anstey - AK (SG) | Charnwood | 2025/2026 | Q2 | 2025/2026 | Q2 | 3 | ROAD CLOSURE | cones,NIGHTS | TBC | TBC
Carriageway scheme | Patching | The Nook | Anstey | Charnwood | 2025/2026 | Q2 | 2025/2026 | Q2 | 3 | ROAD CLOSURE | cones,NIGHTS | TBC | TBC
Carriageway scheme | Patching | Stadon Road | Anstey | Charnwood | 2025/2026 | Q2 | 2025/2026 | Q2 | 3 | ROAD CLOSURE | (cone off parking bay) | TBC | TBC
Carriageway scheme | Patching | Leicester Road | Anstey | Charnwood | 2025/2026 | Q2 | 2025/2026 | Q2 | 3 | ROAD CLOSURE |  | TBC | TBC
Carriageway scheme | Patching | Cropston Road | Anstey | Charnwood | 2025/2026 | Q2 | 2025/2026 | Q2 | 3 | ROAD CLOSURE |  | TBC | TBC
Carriageway scheme | Patching | Layby A426 | Dunton Bassett - TP (SG) | Harborough | 2025/2026 | Q2 | 2025/2026 | Q2 | 2 | ROAD CLOSURE | cones, 2 way lights | TBC | TBC
Carriageway scheme | Patching | Fleckney Road | Kibworth Beauchamp - TP (SG) | Harborough | 2025/2026 | Q2 | 2025/2026 | Q2 | 1 | ROAD CLOSURE | cones, start @ 9am | TBC | TBC
Carriageway scheme | Patching | Rosebery Avenue | Kibworth Beauchamp | Harborough | 2025/2026 | Q2 | 2025/2026 | Q2 | 1 | ROAD CLOSURE | cones, start @ 9am | TBC | TBC
Carriageway scheme | Patching | King Street | Sileby - AK (MH) | Charnwood | 2025/2026 | Q2 | 2025/2026 | Q2 | 2 | ROAD CLOSURE | cones, sch hols | TBC | TBC
Carriageway scheme | Patching | Seagrave | Sileby | Charnwood | 2025/2026 | Q2 | 2025/2026 | Q2 | 2 | ROAD CLOSURE | cones, sch hols | TBC | TBC
Carriageway scheme | Patching | Main Street | Newbold Verdon - TP (SG) | Hinckley & Bosworth | 2025/2026 | Q2 | 2025/2026 | Q2 | 19 | ROAD CLOSURE | cones | TBC | TBC
Carriageway scheme | Patching | Brascote Lane | Newbold Verdon | Hinckley & Bosworth | 2025/2026 | Q2 | 2025/2026 | Q2 | 19 | ROAD CLOSURE | cones | TBC | TBC
Carriageway scheme | Patching | Mill Lane | Newbold Verdon | Hinckley & Bosworth | 2025/2026 | Q2 | 2025/2026 | Q2 | 19 | ROAD CLOSURE | cones | TBC | TBC
Carriageway scheme | Patching | Sparkenhoe | Newbold Verdon | Hinckley & Bosworth | 2025/2026 | Q2 | 2025/2026 | Q2 | 19 | ROAD CLOSURE | cones | TBC | TBC
Carriageway scheme | Patching | Arnold Crescent | Newbold Verdon | Hinckley & Bosworth | 2025/2026 | Q2 | 2025/2026 | Q2 | 19 | ROAD CLOSURE | cones | TBC | TBC
Carriageway scheme | Patching | Hunts Lane | Newbold Verdon | Hinckley & Bosworth | 2025/2026 | Q2 | 2025/2026 | Q2 | 19 | ROAD CLOSURE | cones | TBC | TBC
Carriageway scheme | Patching | Hornbeam road | Newbold Verdon | Hinckley & Bosworth | 2025/2026 | Q2 | 2025/2026 | Q2 | 19 | ROAD CLOSURE | cones | TBC | TBC
Carriageway scheme | Patching | Kirkby Lane | Newbold Verdon | Hinckley & Bosworth | 2025/2026 | Q2 | 2025/2026 | Q2 | 19 | ROAD CLOSURE | cones | TBC | TBC
Carriageway scheme | Patching | Desford Road | Newbold Verdon | Hinckley & Bosworth | 2025/2026 | Q2 | 2025/2026 | Q2 | 19 | ROAD CLOSURE | cones | TBC | TBC
Carriageway scheme | Patching | Woodhouse Road | Quorn | Charnwood | 2025/2026 | Q2 | 2025/2026 | Q2 | 1 | MOBILE LANE | closure 09.30 - 15.00 | TBC | TBC
Carriageway scheme | Patching | Loughborough Road | Quorn | Charnwood | 2025/2026 | Q2 | 2025/2026 | Q2 | 1 | MOBILE LANE | closure 09.30 - 15.00 | TBC | TBC
Carriageway scheme | Patching | Farley Way | Quorn | Charnwood | 2025/2026 | Q2 | 2025/2026 | Q2 | 1 | MOBILE LANE | closure 09.30 - 15.00 | TBC | TBC
Carriageway scheme | Patching | Brand Hill | Woodhouse Eaves - AK | Charnwood | 2025/2026 | Q2 | 2025/2026 | Q2 | 1 | ROAD CLOSURE | 2 way lights | TBC | TBC
Carriageway scheme | Patching | Brand Lane | Woodhouse Eaves | Charnwood | 2025/2026 | Q2 | 2025/2026 | Q2 | 1 | ROAD CLOSURE | 2 way lights | TBC | TBC
Carriageway scheme | Patching | Church Hill | Woodhouse Eaves | Charnwood | 2025/2026 | Q2 | 2025/2026 | Q2 | 1 | ROAD CLOSURE | 2 way lights | TBC | TBC
Carriageway scheme | Patching | Bath Lane | Moira - AK | NWL | 2025/2026 | Q2 | 2025/2026 | Q2 | 1 | ROAD CLOSURE |  | TBC | TBC
Carriageway scheme | Patching | Willesley Road | Ashby - AK | NWL | 2025/2026 | Q2 | 2025/2026 | Q2 | 2 | ROAD CLOSURE | sch hols | TBC | TBC
Carriageway scheme | Patching | Willesley Lane | Ashby | NWL | 2025/2026 | Q2 | 2025/2026 | Q2 | 2 | ROAD CLOSURE | sch hols | TBC | TBC
Carriageway scheme | Patching | Ashby Road | Belton - AK | NWL | 2025/2026 | Q2 | 2025/2026 | Q2 | 1 | ROAD CLOSURE |  | TBC | TBC
Carriageway scheme | Patching | Rempstone Road | Belton | NWL | 2025/2026 | Q2 | 2025/2026 | Q2 | 1 | ROAD CLOSURE |  | TBC | TBC
Carriageway scheme | Patching | Ashby Road | Osgathorpe | NWL | 2025/2026 | Q2 | 2025/2026 | Q2 | 1 | ROAD CLOSURE |  | TBC | TBC
Carriageway scheme | Patching | Knighthorpe Road | Loughborough | Charnwood | 2025/2026 | Q2 | 2025/2026 | Q2 | 2 | ROAD CLOSURE | cones | TBC | TBC
Carriageway scheme | Patching | Huntingdon Way | Measam | NWL | 2025/2026 | Q2 | 2025/2026 | Q2 | 3 | ROAD CLOSURE | nights, cones | TBC | TBC
Carriageway scheme | Patching | Repton Road | Measam | NWL | 2025/2026 | Q2 | 2025/2026 | Q2 | 3 | ROAD CLOSURE | nights, cones | TBC | TBC
Carriageway scheme | Patching | Atherstone Road | Measham | NWL | 2025/2026 | Q2 | 2025/2026 | Q2 | 4 | ROAD CLOSURE | cones,check psv with CM | TBC | TBC
Carriageway scheme | Patching | Benscliffe Road | Newtown Linford - AK | Charnwood | 2025/2026 | Q2 | 2025/2026 | Q2 | 1 | ROAD CLOSURE |  | TBC | TBC
Carriageway scheme | Patching | Sharpley Hill | Newtown Linford | Charnwood | 2025/2026 | Q2 | 2025/2026 | Q2 | 1 | ROAD CLOSURE |  | TBC | TBC
Carriageway scheme | Patching | Warren Hill | Newtown Linford | Charnwood | 2025/2026 | Q2 | 2025/2026 | Q2 | 1 | ROAD CLOSURE |  | TBC | TBC
Carriageway scheme | Patching | Keyham Lane | Beeby | Charnwood | 2025/2026 | Q2 | 2025/2026 | Q2 | 1 | ROAD CLOSURE | 2 way lights | TBC | TBC
Carriageway scheme | Patching | High Street | Measham | NWL | 2025/2026 | Q2 | 2025/2026 | Q2 | 6 | ROAD CLOSURE | cones, days & nights | TBC | TBC
Carriageway scheme | Patching | Bosworth Road | Measham | NWL | 2025/2026 | Q2 | 2025/2026 | Q2 | 6 | ROAD CLOSURE | cones, days & nights | TBC | TBC
Carriageway scheme | Patching | Leicester Road | Measham | NWL | 2025/2026 | Q2 | 2025/2026 | Q2 | 6 | ROAD CLOSURE | cones, days & nights | TBC | TBC
Carriageway scheme | Patching | Mill Road | Thurcaston | Charnwood | 2025/2026 | Q2 | 2025/2026 | Q2 | 1 | MULTIWAY STOP/GO | 07.00 AM START | TBC | TBC
Carriageway scheme | Patching | Leiceter Road | Thurcaston | Charnwood | 2025/2026 | Q2 | 2025/2026 | Q2 | 1 | MULTIWAY STOP/GO | 07.00 AM START | TBC | TBC
Carriageway scheme | Patching | High Street | Quorn | Charnwood | 2025/2026 | Q2 | 2025/2026 | Q2 | 1 | MULTIWAY STOP/GO | 07.00 AM START | TBC | TBC
Carriageway scheme | Patching | High Street | Coalville | NWL | 2025/2026 | Q2 | 2025/2026 | Q2 | 1 | MOBILE LANE | Closure 07.00 AM START | TBC | TBC
Carriageway scheme | Patching | Belvoir Road | Coalville | NWL | 2025/2026 | Q2 | 2025/2026 | Q2 | 1 | MOBILE LANE | Closure 07.00 AM START | TBC | TBC
Carriageway scheme | Patching | Ashby Road | Coalville | NWL | 2025/2026 | Q2 | 2025/2026 | Q2 | 1 | MOBILE LANE | Closure 07.00 AM START | TBC | TBC
Carriageway scheme | Patching | Memorial Square | Coalville | NWL | 2025/2026 | Q2 | 2025/2026 | Q2 | 1 | MOBILE LANE | Closure 07.00 AM START | TBC | TBC
Carriageway scheme | Patching | Market Street | Coalville | NWL | 2025/2026 | Q2 | 2025/2026 | Q2 | 1 | MOBILE LANE | Closure 07.00 AM START | TBC | TBC
Carriageway scheme | Patching | Ashby Road | Hinckley | Hinckley & Bosworth | 2025/2026 | Q2 | 2025/2026 | Q2 | 6 | ROAD CLOSURE |  | TBC | TBC
Carriageway scheme | Patching | Normandy Way | Hinckley | Hinckley & Bosworth | 2025/2026 | Q2 | 2025/2026 | Q2 | 6 | ROAD CLOSURE |  | TBC | TBC
Carriageway scheme | Patching | Old Forge Road | Fenny Drayton | Hinckley & Bosworth | 2025/2026 | Q2 | 2025/2026 | Q2 | 5 | ROAD CLOSURE |  | TBC | TBC
Carriageway scheme | Patching | Church Lane | Fenny Drayton | Hinckley & Bosworth | 2025/2026 | Q2 | 2025/2026 | Q2 | 5 | ROAD CLOSURE |  | TBC | TBC
Carriageway scheme | Patching | Drayton Lane | Fenny Drayton | Hinckley & Bosworth | 2025/2026 | Q2 | 2025/2026 | Q2 | 5 | ROAD CLOSURE |  | TBC | TBC
Carriageway scheme | Patching | Quaker Close | Fenny Drayton | Hinckley & Bosworth | 2025/2026 | Q2 | 2025/2026 | Q2 | 5 | ROAD CLOSURE |  | TBC | TBC
Carriageway scheme | Patching | Main Road | Claybrook Parva | Harborough | 2025/2026 | Q2 | 2025/2026 | Q2 | 2 | ROAD CLOSURE |  | TBC | TBC
Carriageway scheme | Patching | Woodway Road | Claybrook Parva | Harborough | 2025/2026 | Q2 | 2025/2026 | Q2 | 2 | ROAD CLOSURE |  | TBC | TBC
Carriageway scheme | Patching | Belle Vue | Earl Shilton | Hinckley & Bosworth | 2025/2026 | Q2 | 2025/2026 | Q2 | 2 | ROAD CLOSURE | cones, Stop/Go | TBC | TBC
Carriageway scheme | Patching | Moore Road | Earl Shilton | Hinckley & Bosworth | 2025/2026 | Q2 | 2025/2026 | Q2 | 2 | ROAD CLOSURE | cones, Stop/Go | TBC | TBC
Carriageway scheme | Patching | Norton Road | Earl Shilton | Hinckley & Bosworth | 2025/2026 | Q2 | 2025/2026 | Q2 | 2 | ROAD CLOSURE | cones, Stop/Go | TBC | TBC
Carriageway scheme | Patching | Stoke Road | Hinckley - TP (SG) | Hinckley & Bosworth | 2025/2026 | Q2 | 2025/2026 | Q2 | 3 | ROAD CLOSURE | cones,sch hols | TBC | TBC
Carriageway scheme | Patching | Tudor Road | Hinckley | Hinckley & Bosworth | 2025/2026 | Q2 | 2025/2026 | Q2 | 3 | ROAD CLOSURE | cones,sch hols | TBC | TBC
Carriageway scheme | Patching | Towers Drive | Hinckley | Hinckley & Bosworth | 2025/2026 | Q2 | 2025/2026 | Q2 | 3 | ROAD CLOSURE |  | TBC | TBC
Carriageway scheme | Patching | Stanley Road | Hinckley | Hinckley & Bosworth | 2025/2026 | Q2 | 2025/2026 | Q2 | 3 | ROAD CLOSURE |  | TBC | TBC
Carriageway scheme | Patching | Hollycroft | Hinckley | Hinckley & Bosworth | 2025/2026 | Q2 | 2025/2026 | Q2 | 3 | ROAD CLOSURE |  | TBC | TBC
Carriageway scheme | Patching | Hinckley Road | Burbage | Hinckley & Bosworth | 2025/2026 | Q2 | 2025/2026 | Q2 | 5 | ROAD CLOSURE | nights cones | TBC | TBC
Carriageway scheme | Patching | Woodland Avenue | Burbage | Hinckley & Bosworth | 2025/2026 | Q2 | 2025/2026 | Q2 | 5 | ROAD CLOSURE | nights cones | TBC | TBC
Carriageway scheme | Patching | Church Street | Burbage | Hinckley & Bosworth | 2025/2026 | Q2 | 2025/2026 | Q2 | 5 | ROAD CLOSURE | nights cones | TBC | TBC
Carriageway scheme | Patching | Belvoir Road | Coalvile | NWL | 2025/2026 | Q2 | 2025/2026 | Q2 | 4 | ROAD CLOSURE | nights/days, cones | TBC | TBC
Carriageway scheme | Patching | Avenue Road | Coalvile | NWL | 2025/2026 | Q2 | 2025/2026 | Q2 | 4 | ROAD CLOSURE | nights/days, cones | TBC | TBC
Carriageway scheme | Patching | Berrisford Street | Coalvile | NWL | 2025/2026 | Q2 | 2025/2026 | Q2 | 4 | ROAD CLOSURE | nights/days, cones | TBC | TBC
Carriageway scheme | Patching | James Street | Coalvile | NWL | 2025/2026 | Q2 | 2025/2026 | Q2 | 4 | ROAD CLOSURE | nights/days, cones | TBC | TBC
Carriageway scheme | Patching | Melbourne Street | Coalvile | NWL | 2025/2026 | Q2 | 2025/2026 | Q2 | 4 | ROAD CLOSURE | nights/days, cones | TBC | TBC
Carriageway scheme | Patching | Vaughan Street | Coalvile | NWL | 2025/2026 | Q2 | 2025/2026 | Q2 | 4 | SUSPENSION OF ONE WAY | & cones | TBC | TBC
Carriageway scheme | Patching | Owen Street | Coalville | NWL | 2025/2026 | Q2 | 2025/2026 | Q2 | 2 | ROAD CLOSURE | nights, cones | TBC | TBC
Carriageway scheme | Patching | Loughborough Rd | Quorn | Charnwood | 2025/2026 | Q2 | 2025/2026 | Q2 | 1 | ROAD CLOSURE | nights | TBC | TBC
Carriageway scheme | Patching | Ratby Lane | LFE | Blaby | 2025/2026 | Q2 | 2025/2026 | Q2 | 1 | ROAD CLOSURE | nights, | TBC | TBC
Carriageway scheme | Patching | Ratby Lane | Kirby Muxloe | Blaby | 2025/2026 | Q2 | 2025/2026 | Q2 | 1 | ROAD CLOSURE | nights, | TBC | TBC
Carriageway scheme | Patching | Broom Leys | Coalville | NWL | 2025/2026 | Q2 | 2025/2026 | Q2 | 5 | ROAD CLOSURE | (cemetary) | TBC | TBC
Carriageway scheme | Patching | Meadow Lane | Coalville | NWL | 2025/2026 | Q2 | 2025/2026 | Q2 | 5 | ROAD CLOSURE | (cemetary) | TBC | TBC
Carriageway scheme | Patching | Blackwood | Coalville | NWL | 2025/2026 | Q2 | 2025/2026 | Q2 | 5 | ROAD CLOSURE | (cemetary) | TBC | TBC
Carriageway scheme | Patching | Hall Lane | Coalville | NWL | 2025/2026 | Q2 | 2025/2026 | Q2 | 5 | ROAD CLOSURE | (cemetary) | TBC | TBC
Carriageway scheme | Patching | Green hill | Coalville | NWL | 2025/2026 | Q2 | 2025/2026 | Q2 | 5 | ROAD CLOSURE | (cemetary) | TBC | TBC
Carriageway scheme | Patching | Burton Road | Ashby De La Zouch | NWL | 2025/2026 | Q2 | 2025/2026 | Q2 | 2 | ROAD CLOSURE | lights | TBC | TBC
Carriageway scheme | Patching | Ashby Road | Ashby De La Zouch | NWL | 2025/2026 | Q2 | 2025/2026 | Q2 | 2 | ROAD CLOSURE | lights | TBC | TBC
Carriageway scheme | Patching | Jennys Lane | Ravenstone | NWL | 2025/2026 | Q2 | 2025/2026 | Q2 | 1 | ROAD CLOSURE | lights, | TBC | TBC
Carriageway scheme | Patching | Woodhouse Road | Quorn | Charnwood | 2025/2026 | Q2 | 2025/2026 | Q2 | 2 | ROAD CLOSURE | off peak | TBC | TBC
Carriageway scheme | Patching | Loughborough Raod | Quorn | Charnwood | 2025/2026 | Q2 | 2025/2026 | Q2 | 2 | ROAD CLOSURE | off peak | TBC | TBC
Carriageway scheme | Patching | Farley Way | Quorn | Charnwood | 2025/2026 | Q2 | 2025/2026 | Q2 | 2 | ROAD CLOSURE | off peak | TBC | TBC
Carriageway scheme | Patching | Hothorpe Road | Theddingworth | Harborough | 2025/2026 | Q2 | 2025/2026 | Q2 | 2 | ROAD CLOSURE | 2 way lights | TBC | TBC
Carriageway scheme | Patching | Main Street | Laughton | Harborough | 2025/2026 | Q2 | 2025/2026 | Q2 | 2 | ROAD CLOSURE |  | TBC | TBC
Carriageway scheme | Patching | Gumley Road | Laughton | Harborough | 2025/2026 | Q2 | 2025/2026 | Q2 | 2 | ROAD CLOSURE |  | TBC | TBC
Carriageway scheme | Patching | Gumley Road | Gumley | Harborough | 2025/2026 | Q2 | 2025/2026 | Q2 | 2 | ROAD CLOSURE |  | TBC | TBC
Carriageway scheme | Patching | Hall Road | Buckminster | Melton | 2025/2026 | Q2 | 2025/2026 | Q2 | 1 | ROAD CLOSURE | start 9am | TBC | TBC
Carriageway scheme | Patching | Eastwell Road | Scalford | Melton | 2025/2026 | Q2 | 2025/2026 | Q2 | 1 | ROAD CLOSURE | cones | TBC | TBC
Carriageway scheme | Patching | King Street | Scalford | Melton | 2025/2026 | Q2 | 2025/2026 | Q2 | 1 | ROAD CLOSURE | cones | TBC | TBC
Carriageway scheme | Patching | Pasture Lane | Gaddesby | Melton | 2025/2026 | Q2 | 2025/2026 | Q2 | 3 | ROAD CLOSURE |  | TBC | TBC
Carriageway scheme | Patching | Pasture Lane North | Gaddesby | Melton | 2025/2026 | Q2 | 2025/2026 | Q2 | 3 | ROAD CLOSURE |  | TBC | TBC
Carriageway scheme | Patching | Gaddesby Lane | Kirkby Bellars | Melton | 2025/2026 | Q2 | 2025/2026 | Q2 | 3 | ROAD CLOSURE |  | TBC | TBC
Carriageway scheme | Patching | Nanpantan Road Xrds | Loughborough | Charnwood | 2025/2026 | Q2 | 2025/2026 | Q2 | 1 | ROAD CLOSURE |  | TBC | TBC
Carriageway scheme | Patching | Snells Nook Lane | Loughborough | Charnwood | 2025/2026 | Q2 | 2025/2026 | Q2 | 1 | ROAD CLOSURE |  | TBC | TBC
Carriageway scheme | Patching | Woodhouse Lane | Loughborough | Charnwood | 2025/2026 | Q2 | 2025/2026 | Q2 | 1 | ROAD CLOSURE |  | TBC | TBC
Carriageway scheme | Patching | Gaddesby Lane | Frisby on the Weake | Melton | 2025/2026 | Q2 | 2025/2026 | Q2 | 2 | ROAD CLOSURE |  | TBC | TBC
Carriageway scheme | Patching | Great Dalby Rd | Ashby Folville | Melton | 2025/2026 | Q2 | 2025/2026 | Q2 | 3 | ROAD CLOSURE |  | TBC | TBC
Carriageway scheme | Patching | Folville Street | Gaddesby | Melton | 2025/2026 | Q2 | 2025/2026 | Q2 | 3 | ROAD CLOSURE |  | TBC | TBC
Carriageway scheme | Patching | Ashby Road | Twyford | Melton | 2025/2026 | Q2 | 2025/2026 | Q2 | 3 | ROAD CLOSURE |  | TBC | TBC
Carriageway scheme | Patching | Tilton Road | Twyford | Melton | 2025/2026 | Q2 | 2025/2026 | Q2 | 2 | ROAD CLOSURE | Nights, | TBC | TBC
Carriageway scheme | Patching | Main Road | Twyford | Melton | 2025/2026 | Q2 | 2025/2026 | Q2 | 2 | ROAD CLOSURE | Nights, | TBC | TBC
Carriageway scheme | Patching | Main Street | Twyford | Melton | 2025/2026 | Q2 | 2025/2026 | Q2 | 2 | ROAD CLOSURE | Nights, | TBC | TBC
Carriageway scheme | Patching | A46 Slip | Wanlip | Charnwood | 2025/2026 | Q2 | 2025/2026 | Q2 | 2 | ROAD CLOSURE | Nights, | TBC | TBC
Carriageway scheme | Patching | Fillingate | Wanlip | Charnwood | 2025/2026 | Q2 | 2025/2026 | Q2 | 2 | ROAD CLOSURE | Nights, | TBC | TBC
Carriageway scheme | Patching | Leicester Road dual | Anstey | Charnwood | 2025/2026 | Q2 | 2025/2026 | Q2 | 1 | ROAD CLOSURE | Nights, | TBC | TBC
Carriageway scheme | Patching | Ashby Road | Castle Donnington | NWL | 2025/2026 | Q2 | 2025/2026 | Q2 | 1 | ROAD CLOSURE | Nights, | TBC | TBC
Carriageway scheme | Patching | Main Street | Normanton | Melton | 2025/2026 | Q2 | 2025/2026 | Q3 | 4 | ROAD CLOSURE |  | TBC | TBC
Carriageway scheme | Patching | Normanton Lane | Bottesford | Melton | 2025/2026 | Q2 | 2025/2026 | Q3 | 4 | ROAD CLOSURE |  | TBC | TBC
Carriageway scheme | Patching | Normanton Lane | Normanton | Melton | 2025/2026 | Q2 | 2025/2026 | Q3 | 4 | ROAD CLOSURE |  | TBC | TBC
Carriageway scheme | Patching | Enderby Road | Whetstone - TP | Blaby | 2025/2026 | Q2 | 2025/2026 | Q2 | 6 | ROAD CLOSURE |  | TBC | TBC
Carriageway scheme | Patching | Melton Road | East Langton - TP | Harborough | 2025/2026 | Q2 | 2025/2026 | Q2 | 4 | ROAD CLOSURE | nights, | TBC | TBC
Carriageway scheme | Patching | Melton Road | West Langton | Harborough | 2025/2026 | Q2 | 2025/2026 | Q2 | 4 | ROAD CLOSURE | nights, | TBC | TBC
Carriageway scheme | Patching | Wood Road | Nailstone - TP | Hinckley & Bosworth | 2025/2026 | Q2 | 2025/2026 | Q2 | 3 | ROAD CLOSURE | nights | TBC | TBC
Carriageway scheme | Patching | Bagworth Road | Nailstone | Hinckley & Bosworth | 2025/2026 | Q2 | 2025/2026 | Q2 | 3 | ROAD CLOSURE | nights | TBC | TBC
Carriageway scheme | Patching | Grange Lane | Nailstone | Hinckley & Bosworth | 2025/2026 | Q2 | 2025/2026 | Q2 | 3 | ROAD CLOSURE | nights | TBC | TBC
Carriageway scheme | Patching | Moor Lane | Tonge | NWL | 2025/2026 | Q2 | 2025/2026 | Q2 | 2 | ROAD CLOSURE | nights | TBC | TBC
Carriageway scheme | Patching | A453 from Moor Lane | Tonge | NWL | 2025/2026 | Q2 | 2025/2026 | Q2 | 2 | ROAD CLOSURE | nights | TBC | TBC
Carriageway scheme | Patching | Desford Road | Kiby Muxloe | Blaby | 2025/2026 | Q2 | 2025/2026 | Q2 | 1 | ROAD CLOSURE | nights | TBC | TBC
Carriageway scheme | Patching | High Street | Coalville | NWL | 2025/2026 | Q2 | 2025/2026 | Q2 | 4 | ROAD CLOSURE | nights | TBC | TBC
Carriageway scheme | Patching | Belvoir Road | Coalville | NWL | 2025/2026 | Q2 | 2025/2026 | Q2 | 4 | ROAD CLOSURE | nights | TBC | TBC
Carriageway scheme | Patching | Ashby Road | Coalville | NWL | 2025/2026 | Q2 | 2025/2026 | Q2 | 4 | ROAD CLOSURE | nights | TBC | TBC
Carriageway scheme | Patching | Memorial Square | Coalville | NWL | 2025/2026 | Q2 | 2025/2026 | Q2 | 4 | ROAD CLOSURE | nights | TBC | TBC
Carriageway scheme | Patching | Market Street | Coalville | NWL | 2025/2026 | Q2 | 2025/2026 | Q2 | 4 | ROAD CLOSURE | nights | TBC | TBC
Carriageway scheme | Patching | Bunker Hill | Lubenham - TP | Harborough | 2025/2026 | Q2 | 2025/2026 | Q3 | 3 | ROAD CLOSURE | normal | TBC | TBC
Carriageway scheme | Patching | Gumley Road | Theddingworth | Harborough | 2025/2026 | Q2 | 2025/2026 | Q3 | 3 | ROAD CLOSURE | normal | TBC | TBC
Carriageway scheme | Patching | Station Street | Kibworth Beauchamp - TP | Harborough | 2025/2026 | Q3 | 2025/2026 | Q3 | 1 | ROAD CLOSURE | cones, off peak | TBC | TBC
Carriageway scheme | Patching | Church Road | Kibworth Beauchamp | Harborough | 2025/2026 | Q3 | 2025/2026 | Q3 | 1 | ROAD CLOSURE | cones, off peak | TBC | TBC
Carriageway scheme | Patching | Breakback Road | Woodhouse Eaves AK- (MH) | Charnwood | 2025/2026 | Q3 | 2025/2026 | Q3 | 1 | ROAD CLOSURE |  | TBC | TBC
Carriageway scheme | Patching | Harby Lane | Plungar | Melton | 2025/2026 | Q3 | 2025/2026 | Q3 | 1 | ROAD CLOSURE | off peak, cones | TBC | TBC
Carriageway scheme | Patching | Barkerstone Lane | Plungar | Melton | 2025/2026 | Q3 | 2025/2026 | Q3 | 1 | ROAD CLOSURE | off peak, cones | TBC | TBC
Carriageway scheme | Patching | Plugar Lane | Barkestone | Melton | 2025/2026 | Q3 | 2025/2026 | Q3 | 1 | ROAD CLOSURE | off peak, cones | TBC | TBC
Carriageway scheme | Patching | Bevior Road | Redmile | Melton | 2025/2026 | Q3 | 2025/2026 | Q3 | 4 | ROAD CLOSURE |  | TBC | TBC
Carriageway scheme | Patching | Saxby Road | Saxby | Melton | 2025/2026 | Q3 | 2025/2026 | Q3 | 3 | ROAD CLOSURE | nights, | TBC | TBC
Carriageway scheme | Patching | Garthorpe Road | Saxby | Melton | 2025/2026 | Q3 | 2025/2026 | Q3 | 3 | ROAD CLOSURE | nights, | TBC | TBC
Carriageway scheme | Patching | Coston Road | Garthorpe | Melton | 2025/2026 | Q3 | 2025/2026 | Q3 | 3 | ROAD CLOSURE | nights, | TBC | TBC
Carriageway scheme | Patching | Garthorpe Rd to Coston Rd | Garthorpe | Melton | 2025/2026 | Q3 | 2025/2026 | Q3 | 3 | ROAD CLOSURE | nights, | TBC | TBC
Carriageway scheme | Patching | Lower Bond Street | Hinckley | Hinckley & Bosworth | 2025/2026 | Q3 | 2025/2026 | Q3 | 5 | ROAD CLOSURE | nights | TBC | TBC
Carriageway scheme | Patching | King Street | Hinckley | Hinckley & Bosworth | 2025/2026 | Q3 | 2025/2026 | Q3 | 5 | ROAD CLOSURE | nights | TBC | TBC
Carriageway scheme | Patching | Stockwell Head | Hinckley | Hinckley & Bosworth | 2025/2026 | Q3 | 2025/2026 | Q3 | 5 | ROAD CLOSURE | nights | TBC | TBC
Carriageway scheme | Patching | Upper Bond Street | Hinckley | Hinckley & Bosworth | 2025/2026 | Q3 | 2025/2026 | Q3 | 5 | ROAD CLOSURE | nights | TBC | TBC
Carriageway scheme | Patching | Trinity Lane | Hinckley | Hinckley & Bosworth | 2025/2026 | Q3 | 2025/2026 | Q3 | 5 | ROAD CLOSURE | nights | TBC | TBC
Carriageway scheme | Patching | The Borough | Hinckley | Hinckley & Bosworth | 2025/2026 | Q3 | 2025/2026 | Q3 | 5 | ROAD CLOSURE | nights | TBC | TBC
Carriageway scheme | Patching | Cranoe Road | Glooston | Harborough | 2025/2026 | Q3 | 2025/2026 | Q3 | 1 | ROAD CLOSURE | lights or stop/Go | TBC | TBC
Carriageway scheme | Patching | Loughborough Road | Hathern | Charnwood | 2025/2026 | Q3 | 2025/2026 | Q3 | 4 | ROAD CLOSURE | nights | TBC | TBC
Carriageway scheme | Patching | Quorn Mountsorrel Bypass | Barrow Upon Soar | Charnwood | 2025/2026 | Q3 | 2025/2026 | Q3 | 12 | ROAD CLOSURE | nights,lane closure | TBC | TBC
Carriageway scheme | Patching | Slip Rd A6 to Mountsorrel | Barrow Upon Soar | Charnwood | 2025/2026 | Q3 | 2025/2026 | Q3 | 12 | ROAD CLOSURE | nights,lane closure | TBC | TBC
Carriageway scheme | Patching | Slip Rd southbound A6 | Rothley | Charnwood | 2025/2026 | Q3 | 2025/2026 | Q3 | 12 | ROAD CLOSURE | nights,lane closure | TBC | TBC
Carriageway scheme | Patching | Slip Rd northbound A6 | Rothley | Charnwood | 2025/2026 | Q3 | 2025/2026 | Q3 | 12 | ROAD CLOSURE | nights,lane closure | TBC | TBC
Carriageway scheme | Patching | Slip Rd Loughborough Rd A6 | Rothley | Charnwood | 2025/2026 | Q3 | 2025/2026 | Q3 | 12 | ROAD CLOSURE | nights,lane closure | TBC | TBC
Carriageway scheme | Patching | Slip Rd Loughborough Rd A6 | Rothley | Charnwood | 2025/2026 | Q3 | 2025/2026 | Q3 | 12 | ROAD CLOSURE | nights,lane closure | TBC | TBC
Carriageway scheme | Patching | Quorn Mountsorrel Bypass | Rothley | Charnwood | 2025/2026 | Q3 | 2025/2026 | Q3 | 12 | ROAD CLOSURE | nights,lane closure | TBC | TBC
Carriageway scheme | Patching | Quorn Mountsorrel Bypass | Mountsorrel | Charnwood | 2025/2026 | Q3 | 2025/2026 | Q3 | 12 | ROAD CLOSURE | nights,lane closure | TBC | TBC
Carriageway scheme | Patching | Quorn Mountsorrel Bypass | Mountsorrel | Charnwood | 2025/2026 | Q3 | 2025/2026 | Q3 | 12 | ROAD CLOSURE | nights,lane closure | TBC | TBC
Carriageway scheme | Patching | Quorn Mountsorrel Bypass | Wanlip | Charnwood | 2025/2026 | Q3 | 2025/2026 | Q3 | 12 | ROAD CLOSURE | nights,lane closure | TBC | TBC
Carriageway scheme | Patching | Loughborough Road | Wanlip | Charnwood | 2025/2026 | Q3 | 2025/2026 | Q3 | 12 | ROAD CLOSURE | nights,lane closure | TBC | TBC
Carriageway scheme | Patching | Slip Rd Mountsorrel Lane | Barrow Upon Soar | Charnwood | 2025/2026 | Q3 | 2025/2026 | Q3 | 12 | ROAD CLOSURE | nights,lane closure | TBC | TBC
Carriageway scheme | Patching | Ashby Road | Ullesthorpe | Harborough | 2025/2026 | Q3 | 2025/2026 | Q3 | 4 | ROAD CLOSURE | cones, sch hols | TBC | TBC
Carriageway scheme | Patching | Ullesthorpe Road | Ashby Parva | Harborough | 2025/2026 | Q3 | 2025/2026 | Q3 | 4 | ROAD CLOSURE | cones, sch hols | TBC | TBC
Carriageway scheme | Patching | Roston Drive | Hinckley | Hinckley & Bosworth | 2025/2026 | Q3 | 2025/2026 | Q3 | 5 | ROAD CLOSURE | lane closure,cones | TBC | TBC
Carriageway scheme | Patching | North Street | Whitwick | NWL | 2025/2026 | Q3 | 2025/2026 | Q3 | 3 | ROAD CLOSURE | off peak tbc day | TBC | TBC
Carriageway scheme | Patching | Market Place | Whitwick | NWL | 2025/2026 | Q3 | 2025/2026 | Q3 | 3 | ROAD CLOSURE | off peak tbc day | TBC | TBC
Carriageway scheme | Patching | Churhc Lane | Whitwick | NWL | 2025/2026 | Q3 | 2025/2026 | Q3 | 3 | ROAD CLOSURE | off peak tbc day | TBC | TBC
Carriageway scheme | Patching | Burton Road | Melton | Melton | 2025/2026 | Q3 | 2025/2026 | Q3 | 3 | ROAD CLOSURE | wkend nights | TBC | TBC
Carriageway scheme | Patching | Burton Street | Melton | Melton | 2025/2026 | Q3 | 2025/2026 | Q3 | 3 | ROAD CLOSURE | wkend nights | TBC | TBC
Carriageway scheme | Patching | Leicester Road | Melton | Melton | 2025/2026 | Q3 | 2025/2026 | Q3 | 1 | ROAD CLOSURE | nights | TBC | TBC
Carriageway scheme | Patching | Derby Road | Loughborough | Charnwood | 2025/2026 | Q3 | 2025/2026 | Q3 | 4 | ROAD CLOSURE | nights | TBC | TBC
Carriageway scheme | Patching | Main Street | Stathern | Melton | 2025/2026 | Q3 | 2025/2026 | Q3 | 4 | ROAD CLOSURE | cones, off peak, lights 17/06 | TBC | TBC
Carriageway scheme | Patching | Mill Hill | Stathern | Melton | 2025/2026 | Q3 | 2025/2026 | Q3 | 4 | ROAD CLOSURE | cones, off peak, lights 17/07 | TBC | TBC
Carriageway scheme | Patching | Penn Lane | Stathern | Melton | 2025/2026 | Q3 | 2025/2026 | Q3 | 4 | ROAD CLOSURE | cones, off peak, lights 17/08 | TBC | TBC
Carriageway scheme | Patching | Iveshead Road | Shepshed | Charnwood | 2025/2026 | Q3 | 2025/2026 | Q3 | 1 | ROAD CLOSURE | off peak | TBC | TBC
Carriageway scheme | Patching | Atherstone Road | Twycross | Hinckley & Bosworth | 2025/2026 | Q3 | 2025/2026 | Q3 | 7 | ROAD CLOSURE | nights | TBC | TBC
Carriageway scheme | Patching | Atherstone Road | Appleby Magna | Hinckley & Bosworth | 2025/2026 | Q3 | 2025/2026 | Q3 | 7 | ROAD CLOSURE | nights | TBC | TBC
Carriageway scheme | Patching | Burton Road | Norton Juxta | Hinckley & Bosworth | 2025/2026 | Q3 | 2025/2026 | Q3 | 7 | ROAD CLOSURE | nights | TBC | TBC
Carriageway scheme | Patching | Smeeton Road | Gumley | Harborough | 2025/2026 | Q3 | 2025/2026 | Q3 | 4 | ROAD CLOSURE | cones | TBC | TBC
Carriageway scheme | Patching | Main Street | Gumley | Harborough | 2025/2026 | Q3 | 2025/2026 | Q3 | 4 | ROAD CLOSURE | cones | TBC | TBC
Carriageway scheme | Patching | Foxton Road | Gumley | Harborough | 2025/2026 | Q3 | 2025/2026 | Q3 | 4 | ROAD CLOSURE | cones | TBC | TBC
Carriageway scheme | Patching | Brookside | Burbage | Hinckley & Bosworth | 2025/2026 | Q3 | 2025/2026 | Q3 | 10 | ROAD CLOSURE | off peak,cones, lane closure | TBC | TBC
Carriageway scheme | Patching | Far Lash | Burbage | Hinckley & Bosworth | 2025/2026 | Q3 | 2025/2026 | Q3 | 10 | ROAD CLOSURE | off peak,cones, lane closure | TBC | TBC
Carriageway scheme | Patching | Leicester Road | Shepshed | Charnwood | 2025/2026 | Q4 | 2025/2026 | Q4 | 5 | ROAD CLOSURE | sch hols | TBC | TBC
Carriageway scheme | Patching | Cambridge Street | Shepshed | Charnwood | 2025/2026 | Q4 | 2025/2026 | Q4 | 5 | ROAD CLOSURE | sch hols | TBC | TBC
Carriageway scheme | Patching | Newland Avenue | Shepshed | Charnwood | 2025/2026 | Q4 | 2025/2026 | Q4 | 5 | ROAD CLOSURE | sch hols | TBC | TBC
Carriageway scheme | Patching | Forest Street | Shepshed | Charnwood | 2025/2026 | Q4 | 2025/2026 | Q4 | 5 | ROAD CLOSURE | sch hols | TBC | TBC
Carriageway scheme | Patching | Park Avenue | Shepshed | Charnwood | 2025/2026 | Q4 | 2025/2026 | Q4 | 5 | ROAD CLOSURE | sch hols | TBC | TBC
Carriageway scheme | Patching | Rugby Road | South Kilworth | Harborough | 2025/2026 | TBC | 2025/2026 | TBC | 15 | ROAD CLOSURE | cones | TBC | TBC
Carriageway scheme | Patching | South Kilworth Road | North Kilworth | Harborough | 2025/2026 | TBC | 2025/2026 | TBC | 15 | ROAD CLOSURE | cones | TBC | TBC
Carriageway scheme | Patching | North Road | South Kilworth | Harborough | 2025/2026 | TBC | 2025/2026 | TBC | 15 | ROAD CLOSURE | cones | TBC | TBC
Carriageway scheme | Patching | Dalby Road | Old Dalby | Melton | 2025/2026 | TBC | 2025/2026 | TBC | 5 | ROAD CLOSURE | nights? | TBC | TBC
Carriageway scheme | Patching | Station Road | Old Dalby | Melton | 2025/2026 | TBC | 2025/2026 | TBC | 5 | ROAD CLOSURE | nights? | TBC | TBC
Carriageway scheme | Patching | Waltham Road | Eastwell | Melton | 2025/2026 | TBC | 2025/2026 | TBC | 5 | ROAD CLOSURE | 3 way lights,works commence @9am | TBC | TBC
Carriageway scheme | Patching | Eastwell Road | Goadby | Melton | 2025/2026 | TBC | 2025/2026 | TBC | 5 | ROAD CLOSURE | 3 way lights,works commence @9am | TBC | TBC
Carriageway scheme | Patching | Eastwell Road | Waltham | Melton | 2025/2026 | TBC | 2025/2026 | TBC | 5 | ROAD CLOSURE | 3 way lights,works commence @9am | TBC | TBC
Carriageway scheme | Patching | Colby Drive | Thurmaston | Charnwood | 2025/2026 | TBC | 2025/2026 | TBC | 1 | ROAD CLOSURE |  | TBC | TBC
Carriageway scheme | Patching | Blout Road | Thurmaston | Charnwood | 2025/2026 | TBC | 2025/2026 | TBC | 1 | ROAD CLOSURE |  | TBC | TBC
Carriageway scheme | Patching | Griffin Close | Thurmaston | Charnwood | 2025/2026 | TBC | 2025/2026 | TBC | 1 | ROAD CLOSURE |  | TBC | TBC
Carriageway scheme | Patching | Hamilton Lane | Barkby Thorpe | Charnwood | 2025/2026 | TBC | 2025/2026 | TBC | 3 | ROAD CLOSURE | tlights | TBC | TBC
Carriageway scheme | Patching | King Street | Thurmaston | Charnwood | 2025/2026 | TBC | 2025/2026 | TBC | 3 | ROAD CLOSURE | tlights | TBC | TBC
Carriageway scheme | Patching | King Street | Barkby Thorpe | Charnwood | 2025/2026 | TBC | 2025/2026 | TBC | 3 | ROAD CLOSURE | tlights | TBC | TBC
Carriageway scheme | Patching | Mill Road | Thurcaston | Charnwood | 2025/2026 | TBC | 2025/2026 | TBC | 2 | ROAD CLOSURE | off peak | TBC | TBC
Carriageway scheme | Patching | Leicester Road | Thurcaston | Charnwood | 2025/2026 | TBC | 2025/2026 | TBC | 2 | ROAD CLOSURE | off peak | TBC | TBC
Carriageway scheme | Patching | High Street | Quorn | Charnwood | 2025/2026 | TBC | 2025/2026 | TBC | 1 | ROAD CLOSURE | Sunday | TBC | TBC
Environmental | Gully cleansing | Various | Various | Various | 2025/2026 | TBC | 2025/2026 | TBC | TBC | TBC |  | TBC | TBC
Note on C331: Julie X Wilkinson: usrn 16400481

## ss LTsheet for patching draft (hidden)
[10 empty] | 2025-04-01 | [29 empty] | 2025-05-01 | [30 empty] | 2025-06-01 | [29 empty] | 2025-07-01 | [30 empty] | 2025-08-01 | [30 empty] | 2025-09-01 | [29 empty] | 2025-10-01 | [30 empty] | 2025-11-01 | [29 empty] | 2025-12-01 | [30 empty] | 2026-01-01 | [30 empty] | 2026-02-01 | [27 empty] | 2026-03-01
[9 empty] | Mon | Tue | Wed | Thu | Fri | sat | sun | mon | tue | wed | thu | fri | sat | sun | mon | tue | wed | thu | fri | sat | sun | mon | tue | wed | thu | fri | sat | sun | mon | tue | wed | thu | fri | sat | sun | mon | tue | wed | thu | fri | sat | sun | mon | tue | wed | thu | fri | sat | sun | mon | tue | wed | thu | fri | sat | sun | mon | tue | wed | thu | fri | sat | sun | mon | tue | wed | thu | fri | sat | sun | mon | tue | wed | thu | fri | sat | sun | mon | tue | wed | thu | fri | sat | sun | mon | tue | wed | thu | fri | sat | sun | mon | tue | wed | thu | fri | sat | sun | mon | tue | wed | thu | fri | sat | sun | mon | tue | wed | thu | fri | sat | sun | mon | tue | wed | thu | fri | sat | sun | mon | tue | wed | thu | fri | sat | sun | mon | tue | wed | thu | fri | sat | sun | mon | tue | wed | thu | fri | sat | sun | mon | tue | wed | thu | fri | sat | sun | mon | tue | wed | thu | fri | sat | sun | mon | tue | wed | thu | fri | sat | sun | mon | tue | wed | thu | fri | sat | sun | mon | tue | wed | thu | fri | sat | sun | mon | tue | wed | thu | fri | sat | sun | mon | tue | wed | thu | fri | sat | sun | mon | tue | wed | thu | fri | sat | sun | mon | tue | wed | thu | fri | sat | sun | mon | tue | wed | thu | fri | sat | sun | mon | tue | wed | thu | fri | sat | sun | mon | tue | wed | thu | fri | sat | sun | mon | tue | wed | thu | fri | sat | sun | mon | tue | wed | thu | fri | sat | sun | mon | tue | wed | thu | fri | sat | sun | mon | tue | wed | thu | fri | sat | sun | mon | tue | wed | thu | fri | sat | sun | mon | tue | wed | thu | fri | sat | sun | mon | tue | wed | thu | fri | sat | sun | mon | tue | wed | thu | fri | sat | sun | mon | tue | wed | thu | fri | sat | sun | mon | tue | wed | thu | fri | sat | sun | mon | tue | wed | thu | fri | sat | sun | mon | tue | wed | thu | fri | sat | sun | mon | tue | wed | thu | fri | sat | sun | mon | tue | wed | thu | fri | sat | sun | mon | tue | wed | thu | fri | sat | sun | mon | tue | wed | thu | fri | sat | sun | mon | tue | wed | thu | fri | sat | sun | mon | tue | wed | thu | fri | sat | sun | mon | tue | wed | thu | fri | sat | sun | mon | tue | wed | thu | fri | sat | sun | mon | tue
Cost Code | District | Street | Village | Material & PSV | M2 | Marshals | give Take/stop lines | Traffic Man | 31st | 1st | 2nd | 3rd | 4th | 5th | 6th | 7th | 8th | 9th | 10th | 11th | 12th | 13th | 14th | 15th | 16th | 17th | 18th | 19th | 20th | 21st | 22nd | 23rd | 24th | 25th | 26th | 27th | 28th | 29th | 30th | 1st | 2nd | 3rd | 4th | 5th | 6th | 7th | 8th | 9th | 10th | 11th | 12th | 13th | 14th | 15th | 16th | 17th | 18th | 19th | 20th | 21st | 22nd | 23rd | 24th | 25th | 26th | 27th | 28th | 29th | 30th | 31st | 1st | 2nd | 3rd | 4th | 5th | 6th | 7th | 8th | 9th | 10th | 11th | 12th | 13th | 14th | 15th | 16th | 17th | 18th | 19th | 20th | 21st | 22nd | 23rd | 24th | 25th | 26th | 27th | 28th | 29th | 30th | 1st | 2nd | 3rd | 4th | 5th | 6th | 7th | 8th | 9th | 10th | 11th | 12th | 13th | 14th | 15th | 16th | 17th | 18th | 19th | 20th | 21st | 22nd | 23rd | 24th | 25th | 26th | 27th | 28th | 29th | 30th | 31st | 1st | 2nd | 3rd | 4th | 5th | 6th | 7th | 8th | 9th | 10th | 11th | 12th | 13th | 14th | 15th | 16th | 17th | 18th | 19th | 20th | 21st | 22nd | 23rd | 24th | 25th | 26th | 27th | 28th | 29th | 30th | 31st | 1st | 2nd | 3rd | 4th | 5th | 6th | 7th | 8th | 9th | 10th | 11th | 12th | 13th | 14th | 15th | 16th | 17th | 18th | 19th | 20th | 21st | 22nd | 23rd | 24th | 25th | 26th | 27th | 28th | 29th | 30th | 1st | 2nd | 3rd | 4th | 5th | 6th | 7th | 8th | 9th | 10th | 11th | 12th | 13th | 14th | 15th | 16th | 17th | 18th | 19th | 20th | 21st | 22nd | 23rd | 24th | 25th | 26th | 27th | 28th | 29th | 30th | 31st | 1st | 2nd | 3rd | 4th | 5th | 6th | 7th | 8th | 9th | 10th | 11th | 12th | 13th | 14th | 15th | 16th | 17th | 18th | 19th | 20th | 21st | 22nd | 23rd | 24th | 25th | 26th | 27th | 28th | 29th | 30th | 1st | 2nd | 3rd | 4th | 5th | 6th | 7th | 8th | 9th | 10th | 11th | 12th | 13th | 14th | 15th | 16th | 17th | 18th | 19th | 20th | 21st | 22nd | 23rd | 24th | 25th | 26th | 27th | 28th | 29th | 30th | 31st | 1st | 2nd | 3rd | 4th | 5th | 6th | 7th | 8th | 9th | 10th | 11th | 12th | 13th | 14th | 15th | 16th | 17th | 18th | 19th | 20th | 21st | 22nd | 23rd | 24th | 25th | 26th | 27th | 28th | 29th | 30th | 31st | 1st | 2nd | 3rd | 4th | 5th | 6th | 7th | 8th | 9th | 10th | 11th | 12th | 13th | 14th | 15th | 16th | 17th | 18th | 19th | 20th | 21st | 22nd | 23rd | 24th | 25th | 26th | 27th | 28th | 1st | 2nd | 3rd | 4th | 5th | 6th | 7th | 8th | 9th | 10th | 11th | 12th | 13th | 14th | 15th | 16th | 17th | 18th | 19th | 20th | 21st | 22nd | 23rd | 24th | 25th | 26th | 27th | 28th | 29th | 30th | 31st
2025-04-01
CW - SD | N- Charn | Barrow Road | Quorn - RF (MH) | Flex (55) | 2427 | 5 | yes | ROAD CLOSURE,off peak (9-3) cones,(t'lights ( 1st day) | 2025-04-01 mon 7th: PERMIT GRANTED
CW - SD | N- Charn | Barrow Road | Barrow Upon Soar | above | above | above | above | above | 2025-04-01 mon 7th: PERMIT GRANTED
CW - SD | N- Charn | Bridge Street | Barrow Upon Soar | Curve | above | above | above | above | 2025-04-01 mon 7th: PERMIT GRANTED
CW - PLAN | N- Charn | Park Road | Loughborough - AK (JD) | curve (60/65) | 1623 | 4 | yes | ROAD CLOSURE nights, cones | 2025-04-01 wed 9th: NIGHTS; 2025-04-01 sat 12th: PERMIT GRANTED
CW - PLAN | N- Charn | Access Rd from Prk Rd | Loughborough | above | above | above | above | above | 2025-04-01 wed 9th: NIGHTS; 2025-04-01 sat 12th: PERMIT GRANTED
CW - SD | N- Charn | Belton Road | Loughborough - RF (JD) | curve (65) | 739 | 5 | NO | ROAD CLOSURE nights | 2025-04-01 fri 11th: NIGHTS; 2025-04-01 sun 13th: PERMIT GRANTED
CW - Reactive | S-Harbor | Woodmarket | Lutterworth - TP (SG) | curve | 10876 | 4 | yes | ROAD CLOSURE sch hols, cones | 2025-04-01 mon 28th: PERMIT GRANTED
CW - Reactive | S-Harbor | Stoney Hollow | Lutterworth | above | above | above | above | above | 2025-04-01 mon 28th: PERMIT GRANTED
CW - Reactive | S-Harbor | Woodway Road | Lutterworth | above | above | above | above | above | 2025-04-01 mon 28th: PERMIT GRANTED
CW - Reactive | S-Harbor | Spring close | Lutterworth | above | above | above | above | above | 2025-04-01 mon 28th: PERMIT GRANTED
CW - Reactive | S-Harbor | Orchard Road | Lutterworth | above | above | above | above | above | 2025-04-01 mon 28th: PERMIT GRANTED
CW - Reactive | S-Harbor | Moorbarns | Lutterworth | above | above | above | above | above | 2025-04-01 mon 28th: PERMIT GRANTED
CW - Reactive | S-Harbor | Ryderway | Lutterworth | above | above | above | above | above | 2025-04-01 mon 28th: PERMIT GRANTED
CW - Reactive | S-Harbor | Merton Way | Lutterworth | above | above | above | above | above | 2025-04-01 mon 28th: PERMIT GRANTED
CW - Reactive | S-Harbor | De Verdon Road | Lutterworth | above | above | above | above | above | 2025-04-01 mon 28th: PERMIT GRANTED
CW - Reactive | S-Harbor | Rugby Road | Cotesbach | Paco | NA | NA | NA | 2 way lights | 2025-04-01 thu 24th: IMMEDIATE PERMIT GRANTED
CW - Reactive | N- Charn | A46 Slip Road | Wanlip | Coring | N/A | N/A | N/A | Road Closure National Highways APPROVED - ID117483 / NEMS 430489 | 2025-04-01 mon 28th: PERMIT GRANTED
CW - Reactive | N- Charn | Leicester Road | Anstey | Coring | N/A | N/A | N/A | Lane Closure | 2025-04-01 tue 29th: PERMIT GRANTED
CW - PLAN | N- Charn | Leicester Road | Loughborough - AK (MH) | curve (65) | 14316 | 7 | Yes | Road Closure, cones - Nights - Phasing confirmed | 2025-04-01 wed 30th: NIGHTS; 2025-05-01 wed 7th: NIGHTS; 2025-05-01 mon 12th: PERMIT GRANTED
CW - PLAN | N- Charn | Southfield Road | Loughborough | above | above | above | above | above | 2025-04-01 wed 30th: NIGHTS; 2025-05-01 wed 7th: NIGHTS; 2025-05-01 sun 11th: PERMIT GRANTED
CW - PLAN | N- Charn | Shelthorpe Road | Loughborough | above | above | above | above | above | 2025-04-01 wed 30th: NIGHTS; 2025-05-01 wed 7th: NIGHTS; 2025-05-01 mon 12th: PERMIT GRANTED
CW - PLAN | N- Charn | Beech Road | Loughborough | above | above | above | above | above | 2025-04-01 wed 30th: NIGHTS; 2025-05-01 wed 7th: NIGHTS; 2025-05-01 sun 11th: PERMIT GRANTED
CW - PLAN | N- Charn | Barrow Street | Loughborough | above | above | above | above | above | 2025-04-01 wed 30th: NIGHTS; 2025-05-01 wed 7th: NIGHTS; 2025-05-01 sun 11th: PERMIT GRANTED
2025-05-01
CW - PLAN | N- Melton | Sage Cross St | Melton Mowbray - RF (GS) | Flex (55) | 1528 | 4 | Yes | ROAD CLOSURE, cones -NIGHTS Comms made to businesses | 2025-05-01 mon 12th: NIGHTS; 2025-05-01 wed 14th: PERMIT GRANTED
CW - PLAN | N- Melton | King Street | Melton Mowbray | above | above | above | above | above | 2025-05-01 mon 12th: NIGHTS; 2025-05-01 wed 14th: PERMIT GRANTED
CW - PLAN | N- Melton | Chapel Street | Melton Mowbray - RF (GS) | Flex (55) | 1011 | 4 | No | ROAD CLOSURE, cones NIGHTS | 2025-05-01 wed 14th: NIGHTS; 2025-05-01 fri 16th: PERMIT GRANTED
CW - PLAN | N- Melton | King Street | Melton Mowbray | above | above | above | above | above | 2025-05-01 wed 14th: NIGHTS; 2025-05-01 fri 16th: PERMIT GRANTED
CW - PLAN | N- Melton | Mill Street | Melton Mowbray - RF (GS) | Flex (55) | 2458 | 4 | No | ROAD CLOSURE, NIGHTS Stop/Go 1st night | 2025-05-01 thu 15th: NIGHTS; 2025-05-01 sat 17th: PERMIT GRANTED
CW - PLAN | N- Melton | Regent Street | Melton Mowbray | above | above | above | above | above | 2025-05-01 thu 15th: NIGHTS; 2025-05-01 sat 17th: PERMIT GRANTED
CW - PLAN | N- Melton | Brook Street | Melton Mowbray | above | above | above | above | above | 2025-05-01 thu 15th: NIGHTS; 2025-05-01 sat 17th: PERMIT GRANTED
CW - PLAN | N- Charn | Whaddon Drive | Loughborough | Remedial | N/A | N/A | N/A | Give/Take | 2025-05-01 mon 19th: PERMIT GRANTED
CW - PLAN | S-H&B | Rugby Road | Burbage - TP (WS) | Curve | 6996 | TBC | No | ROAD CLOSURE -nights, Lane Closure, National Highways (Lane Closure) Approved - ID115338/NEMS 427033 | 2025-05-01 tue 20th: NIGHTS; 2025-05-01 sat 24th: PERMIT GRANTED
CW - PLAN | S-H&B | Roundabout Rugby Rd | Burbage | above | above | above | above | above | 2025-05-01 tue 20th: NIGHTS; 2025-05-01 sat 24th: PERMIT GRANTED
CW - PLAN | S-H&B | Canberra Way | Burbage | above | above | above | above | above | 2025-05-01 tue 20th: NIGHTS; 2025-05-01 sat 24th: PERMIT GRANTED
CW - Reactive | S-Harbor | Lutterworth Road | Arnesby - TP (SG) | Curve | 6003 | 5 | Yes | ROAD CLOSURE, lights, cones | 2025-06-01 sun 1st: PERMIT GRANTED
2025-06-01
CW - PLAN | N- Charn | Leicester Road | Loughborough | Remedial | N/A | N/A | N/A | Stop/Go | 2025-06-01 mon 2nd: PERMIT GRANTED
CW - PLAN | N- NWL | Richmond Road | Ibstock - RF (MH) | CG (55) | 4411 | 3 | No | ROAD CLOSURE, 2 way lights. | 2025-06-01 thu 5th: PERMIT GRANTED
CW - PLAN | N- NWL | Richmond Road | Donington le Heath | above | above | above | above | above | 2025-06-01 thu 5th: PERMIT GRANTED
CW - SD | N- Charn | Breakback Road | Woodhouse Eaves AK- (MH) | CG (55) | 1303 | 4 | No | ROAD CLOSURE | 2025-06-01 sat 7th: PERMIT GRANTED
CW - SD | N- Charn | Woodhouse Lane | Loughborough | above | above | above | above | above | 2025-06-01 sat 7th: PERMIT GRANTED
CW - Reactive | S- Blaby | Grove Road | Whetstone - TP (JD) | Curve | 2142 | 5 | Yes | ROAD CLOSURE, 2 x weekends | 2025-06-01 mon 9th: PERMIT GRANTED; 2025-06-01 mon 16th: PERMIT GRANTED
CW - Reactive | S- Blaby | Roundabout junction with Brook St | Whetsone | above | above | above | above | above | 2025-06-01 mon 9th: PERMIT GRANTED; 2025-06-01 mon 16th: PERMIT GRANTED
CW - Reactive | S-Harbor | Broughton Way | Sutton in the Elms | Remedial | N/A | N/A | N/A | Multiway lights, nights | 2025-06-01 sat 14th: PERMIT GRANTED
CW - Reactive | S-H&B | Ashby Road | Hinckley | Coring | N/A | N/A | N/A | Mobile Lane Closure | 2025-06-01 mon 23rd: PERMIT GRANTED
CW - Reactive | S-H&B | Normandy Way | Hinckley | Coring | N/A | N/A | N/A | Mobile Lane Closure | 2025-06-01 mon 23rd: PERMIT GRANTED
CW - Reactive | S-H&B | Station Road | Bagworth - TP (SG) | flex | 14979 | 5 |  | ROAD CLOSURE , Off Peak, | 2025-06-01 mon 30th: PERMIT GRANTED
CW - Reactive | S-H&B | Northfield | Bagworth | above | above | above | above | above (Private) | 2025-06-01 mon 30th: PRIVATE ROAD
CW - Reactive | S-H&B | Station Terrace | Bagworth | above | above | above | above | above (Private) | 2025-06-01 mon 30th: PRIVATE ROAD
CW - Reactive | S-H&B | Durham Close | Bagworth | above | above | above | above | above | 2025-06-01 mon 30th: PERMIT GRANTED
CW - Reactive | S-H&B | Lime Grove | Bagworth | above | above | above | above | above | 2025-06-01 mon 30th: PERMIT GRANTED
CW - Reactive | S-H&B | Barlestone Road | Bagworth | above | above | above | above | above | 2025-06-01 mon 30th: PERMIT GRANTED
CW - Reactive | S-H&B | Main Street | Bagworth | above | above | above | above | above | 2025-06-01 mon 30th: PERMIT GRANTED
CW - Reactive | N- Charn | Quorn Mountsorrel By Pass | Barrow Upon Soar | Coring | N/A | N/A | N/A | Mobile Lane Closure 09.00 - 15.00 | 2025-07-01 tue 1st: PERMIT PENDING
CW - Reactive | N- Charn | Quorn Mountsorrel By Pass | Mountsorrel | Coring | N/A | N/A | N/A | above | 2025-07-01 tue 1st: PERMIT PENDING
CW - Reactive | N- Charn | Quorn Mountsorrel By Pass | Rothley | Coring | N/A | N/A | N/A | above | 2025-07-01 tue 1st: PERMIT PENDING
CW - PLAN | N- Charn | Loughborough Road | Quorn | Coring | N/A | N/A | N/A | Mobile Lane Closure 09.00 - 15.00 | 2025-07-01 tue 1st: PERMIT PENDING
|  |  | 2025-07-01 | GANG 1
CW - SD | N- Melton | Stapleford Road | Stapleford - RF (MH) | CG (55) | 1393 | 3 | Yes | ROAD CLOSURE, (normal working) Stop/Go (off peak) | 2025-07-01 wed 2nd: PERMIT GRANTED
CW - PLAN | N- Charn | Bradgate Road | Anstey - AK (SG) | Prolay Curve (60) | 3775 | 4 | Yes | ROAD CLOSURE,cones,lights, NIGHTS /Leics City - approved/ National Highways (signage only) agreed | 2025-07-01 thu 3rd: NIGHTS; 2025-07-01 sat 5th: PERMIT GRANTED LCC SUPPLY IRON WORKS
CW - PLAN | N- Charn | The Nook | Anstey | above | above | above | above | above | 2025-07-01 thu 3rd: NIGHTS; 2025-07-01 sat 5th: PERMIT GRANTED
CW - PLAN | N- Charn | Stadon Road | Anstey | above | above | above | above | above (cone off parking bay) | 2025-07-01 thu 3rd: NIGHTS; 2025-07-01 sat 5th: PERMIT GRANTED
CW - PLAN | N- Charn | Leicester Road | Anstey | above | above | above | above | above | 2025-07-01 thu 3rd: NIGHTS; 2025-07-01 sat 5th: PERMIT GRANTED
CW - PLAN | N- Charn | Cropston Road | Anstey | above | above | above | above | above | 2025-07-01 thu 3rd: NIGHTS; 2025-07-01 sat 5th: PERMIT GRANTED
CW - Reactive | S-Harbor | Layby A426 | Dunton Bassett - TP (SG) | Flex | 2393 | 2 | Yes | ROAD CLOSURE,cones, 2 way lights | 2025-07-01 thu 10th: PERMIT GRANTED
CW - Reactive | S-Harbor | Fleckney Road | Kibworth Beauchamp - TP (SG) | Flex | 534 | 3 | Yes | ROAD CLOSURE,cones, start @ 9am | 2025-07-01 thu 10th: PERMIT GRANTED
CW - Reactive | S-Harbor | Rosebery Avenue | Kibworth Beauchamp | above | above | above | above | above | 2025-07-01 thu 10th: PERMIT GRANTED
CW - PLAN | N- Charn | King Street | Sileby - AK (MH) | Curve (65) | 1110 | 4 | Yes | ROAD CLOSURE, cones, sch hols | 2025-07-01 sat 12th: PERMIT GRANTED
CW - PLAN | N- Charn | Seagrave | Sileby | above | above | above | above | above | 2025-07-01 sat 12th: PERMIT GRANTED
CW - PLAN | S-H&B | Main Street | Newbold Verdon - TP (SG) | Prolay Flex | 13190 | 5 | No | ROAD CLOSURE, cones | 2025-08-01 sat 2nd: PERMIT GRANTED
CW - PLAN | S-H&B | Brascote Lane | Newbold Verdon | above | above | above | above | above | 2025-08-01 sat 2nd: PERMIT GRANTED
CW - PLAN | S-H&B | Mill Lane | Newbold Verdon | above | above | above | above | above | 2025-08-01 sat 2nd: PERMIT GRANTED
CW - PLAN | S-H&B | Sparkenhoe | Newbold Verdon | above | above | above | above | above | 2025-08-01 sat 2nd: PERMIT GRANTED
CW - PLAN | S-H&B | Arnold Crescent | Newbold Verdon | above | above | above | above | above | 2025-08-01 sat 2nd: PERMIT GRANTED
CW - PLAN | S-H&B | Hunts Lane | Newbold Verdon | above | above | above | above | above | 2025-08-01 sat 2nd: PERMIT GRANTED
CW - PLAN | S-H&B | Hornbeam road | Newbold Verdon | above | above | above | above | above | 2025-08-01 sat 2nd: PERMIT GRANTED
CW - PLAN | S-H&B | Kirkby Lane | Newbold Verdon | above | above | above | above | above | 2025-08-01 sat 2nd: PERMIT GRANTED
CW - PLAN | S-H&B | Desford Road | Newbold Verdon | above | above | above | above | above | 2025-08-01 sat 2nd: PERMIT GRANTED
CW - PLAN | N- Charn | Woodhouse Road | Quorn | Coring | N/A | N/A | N/A | Mobile Lane Closure 09.30 - 15.00 | 2025-07-01 fri 18th: PERMIT PENDING
CW - PLAN | N- Charn | Loughborough Road | Quorn | Coring | N/A | N/A | N/A | Mobile Lane Closure 09.30 - 15.00 | 2025-07-01 fri 18th: PERMIT PENDING
CW - PLAN | N- Charn | Farley Way | Quorn | Coring | N/A | N/A | N/A | Mobile Lane Closure 09.30 - 15.00 | 2025-07-01 fri 18th: PERMIT PENDING
|  |  | 2025-07-01 | GANG 2
CW - Reactive | N- Charn | Brand Hill | Woodhouse Eaves - AK | CG (55) | 1376 | 5 | yes | ROAD CLOSURE, 2 way lights | 2025-07-01 tue 8th: MODIFIED
CW - Reactive | N- Charn | Brand Lane | Woodhouse Eaves | above | above | above | above | above | 2025-07-01 tue 8th: MODIFIED
CW - Reactive | N- Charn | Church Hill | Woodhouse Eaves | above | above | above | above | above | 2025-07-01 tue 8th: MODIFIED
CW - SD | N- NWL | Bath Lane | Moira - AK | CG (60) | 663 | 6 | yes | ROAD CLOSURE Derby request | 2025-07-01 wed 9th: PERMIT GRANTED
CW - SD | N- NWL | Willesley Road | Ashby - AK | CG (60) | 1677 | 4 | no | ROAD CLOSURE, sch hols | 2025-07-01 fri 11th: PERMIT GRANTED
CW - SD | N- NWL | Willesley Lane | Ashby | above | above | above | above | above | 2025-07-01 fri 11th: PERMIT GRANTED
CW - SD | N- NWL | Ashby Road | Belton - AK | CG (60) | 1018 | 5 | NO | ROAD CLOSURE, National Highways - ID121880 NEMS Ref 437971 | 2025-07-01 sat 12th: PERMIT GRANTED
CW - SD | N- NWL | Rempstone Road | Belton | above | above | above | above | above | 2025-07-01 sat 12th: PERMIT GRANTED
CW - SD | N- NWL | Ashby Road | Osgathorpe | above | above | above | above | above | 2025-07-01 sat 12th: PERMIT GRANTED
CW - PLAN | N- Charn | Knighthorpe Road | Loughborough | Curve (60) | 1277 | 4 | yes | ROAD CLOSURE, cones | 2025-07-01 wed 16th: PERMIT GRANTED
CW - PLAN | N- NWL | Huntingdon Way | Measam | Curve (60) | 3560 | 4 | yes | ROAD CLOSURE, nights, cones | 2025-07-01 wed 16th: NIGHTS; 2025-07-01 sat 19th: PERMIT GRANTED LCC SUPPLY IRON WORKS
CW - PLAN | N- NWL | Repton Road | Measam | above | above | above | above | above | 2025-07-01 wed 16th: NIGHTS; 2025-07-01 sat 19th: PERMIT GRANTED
CW - PLAN | N- NWL | Atherstone Road | Measham | Flex (55) | 5891 | 4 | yes | ROAD CLOSURE,cones,check psv with CM | 2025-07-01 fri 25th: PERMIT GRANTED LCC SUPPLY IRON WORKS
CW - PLAN | N- Charn | Benscliffe Road | Newtown Linford - AK | Curve (60) | 665 | 4 | yes | ROAD CLOSURE | 2025-07-01 sat 26th: modified
CW - PLAN | N- Charn | Sharpley Hill | Newtown Linford | above | above | above | above | above | 2025-07-01 sat 26th: modified
CW - PLAN | N- Charn | Warren Hill | Newtown Linford | above | above | above | above | above | 2025-07-01 sat 26th: modified
CW - SD | N- Charn | Keyham Lane | Beeby | CG (55) | 930 | 3 | yes | ROAD CLOSURE, 2 way lights | 2025-07-01 tue 29th: PERMIT GRANTED
CW - PLAN | N- NWL | High Street | Measham | Curve (60 & 65) | 4390 | 5 | yes | Road Closure, cones, days & nights - Phasing needed | 2025-07-01 fri 25th: DAYS; 2025-07-01 mon 28th: DAYS; 2025-07-01 wed 30th: NIGHTS; 2025-08-01 sat 2nd: PERMIT GRANTED - LCC SUPPLY IRONWORKS
CW - PLAN | N- NWL | Bosworth Road | Measham | above | above | above | above | above | 2025-07-01 fri 25th: DAYS; 2025-07-01 mon 28th: DAYS; 2025-07-01 wed 30th: NIGHTS; 2025-08-01 sat 2nd: PERMIT GRANTED
CW - PLAN | N- NWL | Leicester Road | Measham | above | above | above | above | above | 2025-07-01 fri 25th: DAYS; 2025-07-01 mon 28th: DAYS; 2025-07-01 wed 30th: NIGHTS; 2025-08-01 sat 2nd: PERMIT GRANTED
|  |  | 2025-08-01 | Gang 1
CW - PLAN | N- Charn | Mill Road | Thurcaston | Coring | N/A | N/A | N/A | Multiway Stop/Go 07.00 AM START | 2025-08-01 sun 3rd: PERMIT SUBMITTED
CW - PLAN | N- Charn | Leiceter Road | Thurcaston | Coring | above | above | above | above | 2025-08-01 sun 3rd: PERMIT SUBMITTED
CW - PLAN | N- Charn | High Street | Quorn | Coring | above | above | above | above | 2025-08-01 sun 3rd: PERMIT SUBMITTED
CW - PLAN | N- NWL | High Street | Coalville | Coring | N/A | N/A | N/A | Mobile Lane Closure 07.00 AM START | 2025-08-01 mon 4th: PERMIT SUBMITTED
CW - PLAN | N- NWL | Belvoir Road | Coalville | Coring | above | above | above | above | 2025-08-01 mon 4th: PERMIT SUBMITTED
CW - PLAN | N- NWL | Ashby Road | Coalville | Coring | above | above | above | above | 2025-08-01 mon 4th: PERMIT SUBMITTED
CW - PLAN | N- NWL | Memorial Square | Coalville | Coring | above | above | above | above | 2025-08-01 mon 4th: PERMIT SUBMITTED
CW - PLAN | N- NWL | Market Street | Coalville | Coring | above | above | above | above | 2025-08-01 mon 4th: PERMIT SUBMITTED
CW - Reactive | S-H&B | Ashby Road | Hinckley | Curve | 3443 | 6 | yes | ROAD CLOSURE, Highways England approved (ID22561 NEMS 439309) | 2025-08-01 thu 7th: NIGHTS; 2025-08-01 mon 11th: PERMIT GRANTED
CW - Reactive | S-H&B | Normandy Way | Hinckley | above | above | above | above | above | 2025-08-01 thu 7th: NIGHTS; 2025-08-01 mon 11th: PERMIT GRANTED
CW - PLAN | S-H&B | Old Forge Road | Fenny Drayton | Superflex | 4973 | 5 | yes | ROAD CLOSURE,cones, lights, Highways England Approved (ID123213 - NEMS Ref 441814) | 2025-08-01 sat 16th: PERMIT GRANTED
CW - PLAN | S-H&B | Church Lane | Fenny Drayton | above | above | above | above | above | 2025-08-01 sat 16th: PERMIT GRANTED
CW - PLAN | S-H&B | Drayton Lane | Fenny Drayton | above | above | above | above | above | 2025-08-01 sat 16th: PERMIT GRANTED
CW - PLAN | S-H&B | Quaker Close | Fenny Drayton | above | above | above | above | above | 2025-08-01 sat 16th: PERMIT GRANTED
CW - Reactive | S-Harbor | Main Road | Claybrook Parva | Super Flex | 1297 | 3 | yes | ROAD CLOSURE, Highways England | 2025-08-01 mon 18th: PERMIT GRANTED
CW - Reactive | S-Harbor | Woodway Road | Claybrook Parva | above | above | above | above | above | 2025-08-01 mon 18th: PERMIT GRANTED
CW - PLAN | S-H&B | Belle Vue | Earl Shilton | Curve | 3449 | 4 | Yes | ROAD CLOSURE,cones, Stop/Go | 2025-08-01 wed 20th: PERMIT GRANTED
CW - PLAN | S-H&B | Moore Road | Earl Shilton | above | above | above | above | above | 2025-08-01 wed 20th: PERMIT GRANTED
CW - PLAN | S-H&B | Norton Road | Earl Shilton | above | above | above | above | above | 2025-08-01 wed 20th: PERMIT GRANTED
CW - SD | S-H&B | Stoke Road | Hinckley - TP (SG) | Prolay Flex | 4153 | 4 | No | ROAD CLOSURE, cones,sch hols | 2025-08-01 sat 23rd: PERMIT GRANTED
CW - SD | S-H&B | Tudor Road | Hinckley | above | above | above | above | above | 2025-08-01 sat 23rd: PERMIT GRANTED
CW - SD | S-H&B | Towers Drive | Hinckley | above | above | above | above | above (private) | 2025-08-01 sat 23rd: PERMIT GRANTED
CW - SD | S-H&B | Stanley Road | Hinckley | above | above | above | above | above | 2025-08-01 sat 23rd: PERMIT GRANTED
CW - SD | S-H&B | Hollycroft | Hinckley | above | above | above | above | above | 2025-08-01 sat 23rd: PERMIT GRANTED
CW - Reactive | S-H&B | Hinckley Road | Burbage | curve | 7588 | 5 | Yes | ROAD CLOSURE,nights cones, Highways England | 2025-08-01 wed 27th: NIGHTS; 2025-08-01 sun 31st: PERMIT GRANTED
CW - Reactive | S-H&B | Woodland Avenue | Burbage | above | above | above | above | above | 2025-08-01 wed 27th: NIGHTS; 2025-08-01 sun 31st: PERMIT GRANTED
CW - Reactive | S-H&B | Church Street | Burbage | above | above | above | above | above | 2025-08-01 wed 27th: NIGHTS; 2025-08-01 sun 31st: PERMIT GRANTED
|  |  | 2025-08-01 | Gang 2
CW - PLAN | N- NWL | Belvoir Road | Coalvile | Curve (60 & 65) | 2757 | TBC | yes | ROAD CLOSURE, nights/days, cones | 2025-08-01 mon 4th: DAYS; 2025-08-01 tue 5th: NIGHTS; 2025-08-01 fri 8th: PERMIT GRANTED LCC SUPPLY IRON WORKS
CW - PLAN | N- NWL | Avenue Road | Coalvile | above | above | above | above | above | 2025-08-01 mon 4th: DAYS; 2025-08-01 tue 5th: NIGHTS; 2025-08-01 fri 8th: PERMIT GRANTED
CW - PLAN | N- NWL | Berrisford Street | Coalvile | above | above | above | above | above | 2025-08-01 mon 4th: DAYS; 2025-08-01 tue 5th: NIGHTS; 2025-08-01 fri 8th: PERMIT GRANTED
CW - PLAN | N- NWL | James Street | Coalvile | above | above | above | above | above | 2025-08-01 mon 4th: DAYS; 2025-08-01 tue 5th: NIGHTS; 2025-08-01 fri 8th: PERMIT GRANTED
CW - PLAN | N- NWL | Melbourne Street | Coalvile | above | above | above | above | above | 2025-08-01 mon 4th: DAYS; 2025-08-01 tue 5th: NIGHTS; 2025-08-01 fri 8th: PERMIT GRANTED
CW - PLAN | N- NWL | Vaughan Street | Coalvile | above | above | above | above | suspention of one way & cones | 2025-08-01 mon 4th: DAYS; 2025-08-01 tue 5th: NIGHTS; 2025-08-01 fri 8th: PERMIT GRANTED
CW - PLAN | N- NWL | Owen Street | Coalville | Curve (60) | 924 | TBC | yes | ROAD CLOSURE, nights, cones | 2025-08-01 tue 5th: NIGHT; 2025-08-01 thu 7th: PERMIT GRANTED
CW - PLAN | N- Charn | Loughborough Rd | Quorn | Curve (65) | 807 | TBC | No | ROAD CLOSURE, nights | 2025-08-01 thu 7th: night; 2025-08-01 fri 8th: PAA PENDING
CW - SD | S- Blaby | Ratby Lane | LFE | Curve | 1097 | 3 | no | ROAD CLOSURE, nights, National Highways, Leicester city | 2025-08-01 fri 8th: NIGHT; 2025-08-01 sat 9th: PERMIT GRANTED
CW - SD | S- Blaby | Ratby Lane | Kirby Muxloe | above | above | above | above | above | 2025-08-01 fri 8th: NIGHT; 2025-08-01 sat 9th: PERMIT GRANTED
CW - PLAN | N- NWL | Broom Leys | Coalville | Curve (60/65) | 7483 | TBC | Yes | ROAD CLOSURE (cemetary) | 2025-08-01 sat 16th: PERMIT GRANTED LCC SUPPLY IRON WORKS
CW - PLAN | N- NWL | Meadow Lane | Coalville | above | above | above | above | above | 2025-08-01 sat 16th: PERMIT GRANTED
CW - PLAN | N- NWL | Blackwood | Coalville | above | above | above | above | above | 2025-08-01 sat 16th: PERMIT GRANTED
CW - PLAN | N- NWL | Hall Lane | Coalville | above | above | above | above | above | 2025-08-01 sat 16th: PERMIT GRANTED
CW - PLAN | N- NWL | Green hill | Coalville | above | above | above | above | above | 2025-08-01 sat 16th: PERMIT GRANTED
CW - SD | N- NWL | Burton Road | Ashby De La Zouch | Curve (65) | 2898 | TBC | No | Road Closure, lights, Derby CC , phasings needed | 2025-08-01 wed 20th: PERMIT PENDING
CW - SD | N- NWL | Ashby Road | Ashby De La Zouch | above | above | above | above | above | 2025-08-01 wed 20th: PERMIT PENDING
CW - PLAN | N- NWL | Jennys Lane | Ravenstone | Curve (55) | 754 | TBC | Yes | Road Closure, lights, | 2025-08-01 thu 21st: PAA PENDING
CW - PLAN | N- Charn | Woodhouse Road | Quorn | Curve (65) | 1499 | TBC | yes | Road Closure, off peak | 2025-08-01 sat 23rd: PAA PENDING
CW - PLAN | N- Charn | Loughborough Raod | Quorn | above | above | above | above | above | 2025-08-01 sat 23rd: PAA PENDING
CW - PLAN | N- Charn | Farley Way | Quorn | above | above | above | above | above | 2025-08-01 sat 23rd: PAA PENDING
CW - Reactive | S-Harbor | Hothorpe Road | Theddingworth | CG | 2082 | 3 | yes | ROAD CLOSURE, 2 way lights, bordering CC | 2025-08-01 thu 28th: PERMIT GRANTED
CW - SD | S-Harbor | Main Street | Laughton | CG | 4375 | 3 | tbc | ROAD CLOSURE | 2025-08-01 sat 30th: PERMIT GRANTED
CW - SD | S-Harbor | Gumley Road | Laughton | above | above | above | above | above | 2025-08-01 sat 30th: PERMIT GRANTED
CW - SD | S-Harbor | Gumley Road | Gumley | above | above | above | above | above | 2025-08-01 sat 30th: PERMIT PENDING
|  |  | 2025-09-01 | Gang 1
CW - SD | N- Melton | Hall Road | Buckminster | CG (55) | 1275 | TBC | No | ROAD CLOSURE, start 9am &Lincs | 2025-09-01 tue 2nd: PAA PENDING
CW - SD | N- Melton | Eastwell Road | Scalford | flex (55) | 1499 | TBC | no | ROAD CLOSURE, cones | 2025-09-01 wed 3rd: PAA PENDING
CW - SD | N- Melton | King Street | Scalford | above | above | above | above | above | 2025-09-01 wed 3rd: PAA PENDING
CW - SD | N- Melton | Pasture Lane | Gaddesby | CG (55) | 3385 | TBC | No | ROAD CLOSURE | bar: 2025-09-01 wed 3rd to 2025-09-01 fri 5th
CW - SD | N- Melton | Pasture Lane North | Gaddesby | above | above | above | above | above | bar: 2025-09-01 wed 3rd to 2025-09-01 fri 5th
CW - SD | N- Melton | Gaddesby Lane | Kirkby Bellars | above | above | above | above | above | bar: 2025-09-01 wed 3rd to 2025-09-01 fri 5th
CW - PLAN | N- Charn | Nanpantan Road Xrds | Loughborough | Curve (65) | 950 | TBC | Yes | ROAD CLOSURE | 2025-09-01 mon 8th: PERMIT GRANTED
CW - PLAN | N- Charn | Snells Nook Lane | Loughborough | above | above | above | above | above | 2025-09-01 mon 8th: PERMIT GRANTED
CW - PLAN | N- Charn | Woodhouse Lane | Loughborough | above | above | above | above | above | 2025-09-01 mon 8th: PERMIT GRANTED
CW - SD | N- Melton | Gaddesby Lane | Frisby on the Weake | CG (55) | 2122 | TBC | No | ROAD CLOSURE | 2025-09-01 wed 10th: PERMIT PENDING
CW - SD | N- Melton | Great Dalby Rd | Ashby Folville | CG (60) | 3051 | TBC | No | ROAD CLOSURE | 2025-09-01 sat 13th: PERMIT PENDING
CW - SD | N- Melton | Folville Street | Gaddesby | CG (60) | 3151 | TBC | No | ROAD CLOSURE | 2025-09-01 thu 18th: PERMIT PENDING
CW - SD | N- Melton | Ashby Road | Twyford | above | above | above | above | above | 2025-09-01 thu 18th: PERMIT PENDING
CW - PLAN | N- Melton | Tilton Road | Twyford | curve | 3401 | TBC | yes | ROAD CLOSURE, Nights, National Highways ?& Rutland | 2025-09-01 thu 18th: NIGHTS; 2025-09-01 sat 20th: PERMIT GRANTED
CW - PLAN | N- Melton | Main Road | Twyford | above | above | above | above | above | 2025-09-01 thu 18th: NIGHTS; 2025-09-01 sat 20th: PERMIT GRANTED
CW - PLAN | N- Melton | Main Street | Twyford | above | above | above | above | above | 2025-09-01 thu 18th: NIGHTS; 2025-09-01 sat 20th: PAA PENDING
CW - SD | N- Charn | A46 Slip | Wanlip | Curve (60) | 3506 | TBC | Yes | ROAD CLOSURE,nights, National Highways | 2025-09-01 tue 23rd: NIGHTS; 2025-09-01 thu 25th: PERMIT GRANTED
CW - SD | N- Charn | Fillingate | Wanlip | above | above | above | above | above | 2025-09-01 tue 23rd: NIGHTS; 2025-09-01 thu 25th: PERMIT GRANTED
CW - SD | N- Charn | Leicester Road dual | Anstey | Curve (65) | 879 | TBC | Yes | ROAD CLOSURE, nights, National Highways, Bordering CC RS | 2025-09-01 thu 25th: NIGHTS; 2025-09-01 sat 27th: PERMIT GRANTED
CW - SD | N- NWL | Ashby Road | Castle Donnington | Curve (60) | 562 | TBC | No | ROAD CLOSURE,nights, National Highways,contact airport | 2025-09-01 fri 26th: NIGHTS; 2025-09-01 sat 27th: PAA PENDING
CW - SD | N- Melton | Main Street | Normanton | Curve (60) | 8268 | TBC | No | ROAD CLOSURE, National Highways & Bordering CC | 2025-10-01 fri 3rd: PAA PENDING
CW - SD | N- Melton | Normanton Lane | Bottesford | above | above | above | above | above | 2025-10-01 fri 3rd: PAA PENDING
CW - SD | N- Melton | Normanton Lane | Normanton | above | above | above | above | above | 2025-10-01 fri 3rd: PAA PENDING
|  |  | 2025-09-01 | Gang 2
CW - SD | S- Blaby | Enderby Road | Whetstone - TP | Curve 65 | 5106 | TBC | No | ROAD CLOSURE, nights, lane closure, VMS | 2025-09-01 wed 3rd: NIGHTS; 2025-09-01 sun 7th: PAA PENDING
CW - SD | S-Harbor | Melton Road | East Langton - TP | Superflex | 8699 | TBC | No | ROAD CLOSURE, nights, | 2025-09-01 tue 9th: NIGHTS; 2025-09-01 fri 12th: PAA PENDING
CW - SD | S-Harbor | Melton Road | West Langton | above | above | above | above | above | 2025-09-01 tue 9th: NIGHTS; 2025-09-01 fri 12th: PAA PENDING
CW - Reactive | S-H&B | Wood Road | Nailstone - TP | Curve | 6551 | TBC | Yes | ROAD CLOSURE, nights | 2025-09-01 fri 12th: nights; 2025-09-01 tue 16th: nights; 2025-09-01 thu 18th: PAA PENDING
CW - Reactive | S-H&B | Bagworth Road | Nailstone | above | above | above | above | above | 2025-09-01 fri 12th: nigts; 2025-09-01 tue 16th: nights; 2025-09-01 thu 18th: PAA PENDING
CW - Reactive | S-H&B | Grange Lane | Nailstone | above | above | above | above | above | 2025-09-01 fri 12th: nigts; 2025-09-01 tue 16th: nights; 2025-09-01 thu 18th: PAA PENDING
CW - SD | N- NWL | Moor Lane | Tonge | Curve (60) | 1627 | TBC | No | ROAD CLOSURE,nights,Highways England ( wild flowers) | 2025-09-01 thu 18th: nights; 2025-09-01 sat 20th: PAA PENDING
CW - SD | N- NWL | A453 from Moor Lane | Tonge | above | above | above | above | above | 2025-09-01 thu 18th: nights; 2025-09-01 sat 20th: PAA PENDING
CW - Reactive | S- Blaby | Desford Road | Kiby Muxloe | curve | 675 | TBC | No | ROAD CLOSURE, nights | 2025-09-01 mon 22nd: nights; 2025-09-01 tue 23rd: PAA PENDING
CW - PLAN | N- NWL | High Street | Coalville | Curve 60? | 5730 | TBC | Yes | ROAD CLOSURE, nights, network rail | 2025-09-01 wed 24th: nights; 2025-09-01 sat 27th: PAA PENDING
CW - PLAN | N- NWL | Belvoir Road | Coalville | above | above | above | above | above | 2025-09-01 wed 24th: nights; 2025-09-01 sat 27th: PAA PENDING
CW - PLAN | N- NWL | Ashby Road | Coalville | above | above | above | above | above | 2025-09-01 wed 24th: nights; 2025-09-01 sat 27th: PAA PENDING
CW - PLAN | N- NWL | Memorial Square | Coalville | above | above | above | above | above | 2025-09-01 wed 24th: nights; 2025-09-01 sat 27th: PAA PENDING
CW - PLAN | N- NWL | Market Street | Coalville | above | above | above | above | above | 2025-09-01 wed 24th: nights; 2025-09-01 sat 27th: PAA PENDING
CW - PLAN | S-Harbor | Bunker Hill | Lubenham - TP | CGSC | 6975 | TBC | Yes | ROAD CLOSURE, normal | 2025-10-01 thu 2nd: PAA PENDING
CW - PLAN | S-Harbor | Gumley Road | Theddingworth | above | above | above | above | above | 2025-10-01 thu 2nd: PAA PENDING
CW - PLAN | S-Harbor | Station Street | Kibworth Beauchamp - TP | Prolay Flex | 499 | TBC | No | ROAD CLOSURE, cones, off peak | 2025-10-01 fri 3rd: PAA PENDING
CW - PLAN | S-Harbor | Church Road | Kibworth Beauchamp | above | above | above | above | above | 2025-10-01 fri 3rd: PAA PENDING
CW - SD | N- Charn | Breakback Road | Woodhouse Eaves AK- (MH) | CG (55) | tbc | 4 | No | ROAD CLOSURE (meterage tbc) | bar: 2025-10-01 fri 3rd
|  |  | 2025-10-01 | Gang 1
CW - SD | N- Melton | Harby Lane | Plungar | CG 55 | 1207 | TBC | No | ROAD CLOSURE, OFF PEAK, CONES | bar: 2025-10-01 fri 3rd
above | N- Melton | Barkerstone Lane | Plungar | above | above | above | above | above | bar: 2025-10-01 fri 3rd
above | N- Melton | Plugar Lane | Barkestone | above | above | above | above | above | bar: 2025-10-01 fri 3rd
CW - SD | N- Melton | Bevior Road | Redmile | CS /FLEXI/CURVE 55 & 64 | 4512 | TBC | Yes | ROAD CLOSURE, Bordering CC | bar: 2025-10-01 mon 6th to 2025-10-01 thu 9th
CW - PLAN | N- Melton | Saxby Road | Saxby | Curve 65 | 3662 | TBC | No | ROAD CLOSURE, nights, Lincs? | 2025-10-01 fri 10th: NIGHT; 2025-10-01 mon 13th: NIGHTS
CW - PLAN | N- Melton | Garthorpe Road | Saxby | above | above | above | above | above | 2025-10-01 fri 10th: NIGHT; 2025-10-01 mon 13th: NIGHTS
CW - PLAN | N- Melton | Coston Road | Garthorpe | Curve 65 | 2666 | TBC | No | ROAD CLOSURE, nights, Lincs? | 2025-10-01 wed 15th: NIGHTS
CW - PLAN | N- Melton | Garthorpe Rd to Coston Rd | Garthorpe | above | above | above | above | above | 2025-10-01 wed 15th: NIGHTS
CW - Reactive | S-H&B | Lower Bond Street | Hinckley | Curve | 1815 | TBC | Yes | ROAD CLOSURE Nights | 2025-10-01 wed 22nd: NIGHTS; 2025-10-01 sat 25th: PERMIT GRANTED
CW - Reactive | S-H&B | King Street | Hinckley | above | above | above | above | above | 2025-10-01 wed 22nd: NIGHTS; 2025-10-01 sat 25th: PERMIT GRANTED
CW - Reactive | S-H&B | Stockwell Head | Hinckley | above | above | above | above | above | 2025-10-01 wed 22nd: NIGHTS; 2025-10-01 sat 25th: PERMIT GRANTED
CW - Reactive | S-H&B | Upper Bond Street | Hinckley | above | above | above | above | above | 2025-10-01 wed 22nd: NIGHTS; 2025-10-01 sat 25th: PERMIT GRANTED
CW - Reactive | S-H&B | Trinity Lane | Hinckley | above | above | above | above | above | 2025-10-01 wed 22nd: NIGHTS; 2025-10-01 sat 25th: PERMIT GRANTED
CW - Reactive | S-H&B | The Borough | Hinckley | above | above | above | above | above | 2025-10-01 wed 22nd: NIGHTS; 2025-10-01 sat 25th: PERMIT GRANTED
CW - PLAN | S-Harbor | Cranoe Road | Glooston | CG | 221 | TBC | Yes | Road Closure, lights or stop/Go | bar: 2025-10-01 mon 27th
CW - PLAN | N- Charn | Loughborough Road | Hathern | Curve 65 | 6082 | TBC | yes | ROAD CLOSURE, nights | 2025-10-01 wed 29th: NIGHTS
|  |  | 2025-10-01 | Gang 2
CW - SD | N- Charn | Quorn Mountsorrel Bypass | Barrow Upon Soar | Curve 60 & 65 (on Slip) | 21432 | TBC | No | ROAD CLOSURE, nights,lane closure,National Highways | 2025-10-01 wed 8th: NIGHTS; 2025-10-01 wed 15th: NIGHTS; 2025-10-01 sat 18th: PAA PENDING
CW - SD | N- Charn | Slip Rd A6 to Mountsorrel | Barrow Upon Soar | above | above | above | above | above | 2025-10-01 wed 8th: NIGHTS; 2025-10-01 wed 15th: NIGHTS; 2025-10-01 sat 18th: PAA PENDING
CW - SD | N- Charn | Slip Rd southbound A6 | Rothley | above | above | above | above | above | 2025-10-01 wed 8th: NIGHTS; 2025-10-01 wed 15th: NIGHTS; 2025-10-01 sat 18th: PAA PENDING
CW - SD | N- Charn | Slip Rd northbound A6 | Rothley | above | above | above | above | above | 2025-10-01 wed 8th: NIGHTS; 2025-10-01 wed 15th: NIGHTS
CW - SD | N- Charn | Slip Rd Loughborough Rd A6 | Rothley | above | above | above | above | above | 2025-10-01 wed 8th: NIGHTS; 2025-10-01 wed 15th: NIGHTS; 2025-10-01 sat 18th: PAA PENDING
CW - SD | N- Charn | Slip Rd Loughborough Rd A6 | Rothley | above | above | above | above | above | 2025-10-01 wed 8th: NIGHTS; 2025-10-01 wed 15th: NIGHTS; 2025-10-01 sat 18th: PAA PENDING
CW - SD | N- Charn | Quorn Mountsorrel Bypass | Rothley | above | above | above | above | above | 2025-10-01 wed 8th: NIGHTS; 2025-10-01 wed 15th: NIGHTS; 2025-10-01 sat 18th: PAA PENDING
CW - SD | N- Charn | Quorn Mountsorrel Bypass | Mountsorrel | above | above | above | above | above | 2025-10-01 wed 8th: NIGHTS; 2025-10-01 wed 15th: NIGHTS
CW - SD | N- Charn | Quorn Mountsorrel Bypass | Mountsorrel | above | above | above | above | above | 2025-10-01 wed 8th: NIGHTS; 2025-10-01 wed 15th: NIGHTS
CW - SD | N- Charn | Quorn Mountsorrel Bypass | Wanlip | above | above | above | above | above | 2025-10-01 wed 8th: NIGHTS; 2025-10-01 wed 15th: NIGHTS; 2025-10-01 sat 18th: PAA PENDING
CW - SD | N- Charn | Loughborough Road | Wanlip | above | above | above | above | above | 2025-10-01 wed 8th: NIGHTS; 2025-10-01 wed 15th: NIGHTS; 2025-10-01 sat 18th: PAA PENDING
CW - SD | N- Charn | Slip Rd Mountsorrel Lane | Barrow Upon Soar | above | above | above | above | above | 2025-10-01 wed 8th: NIGHTS; 2025-10-01 wed 15th: NIGHTS; 2025-10-01 sat 18th: PAA PENDING
CW - SD | S-Harbor | Ashby Road | Ullesthorpe | CG | 2383 | TBC | Yes | ROAD CLOSURE, cones, sch hols | bar: 2025-10-01 wed 1st to 2025-10-01 fri 3rd; 2025-10-01 mon 20th to 2025-10-01 thu 23rd
CW - SD | S-Harbor | Ullesthorpe Road | Ashby Parva | above | above | above | above | above | bar: 2025-10-01 mon 20th to 2025-10-01 thu 23rd
1 X DAY/NIGHT FREE | bar: 2025-10-01 fri 24th
CW - Reactive | S-H&B | Roston Drive | Hinckley | Curve | 3028 | TBC | No | ROAD CLOSURE,lane closure,cones | 2025-10-01 wed 29th: TBC days/nights
|  |  | 2025-11-01 | Gang 1 (North)
CW - PLAN | N- NWL | North Street | Whitwick | Curve (55) | 1450 | TBC | yes | ROAD CLOSURE, off peak tbc day kerbing needed) | 2025-11-01 thu 6th: tbc
CW - PLAN | N- NWL | Market Place | Whitwick | above | above | above | above | above | bar: 2025-11-01 mon 3rd to 2025-11-01 thu 6th
CW - PLAN | N- NWL | Churhc Lane | Whitwick | above | above | above | above | above | bar: 2025-11-01 mon 3rd to 2025-11-01 thu 6th
CW - SD | N- Melton | Burton Road | Melton | Curve 65 | 4402 | TBC | yes | ROAD CLOSURE, wkend nights, Linc & Rutland, National Highways, national rail | 2025-11-01 sat 1st: tell network rail; 2025-11-01 fri 7th: NIGHTS; 2025-11-01 mon 10th: PERMIT PENDING
CW - SD | N- Melton | Burton Street | Melton | above | above | above | above | above | 2025-11-01 fri 7th: NIGHTS; 2025-11-01 mon 10th: PERMIT PENDING
CW - SD | N- Melton | Leicester Road | Melton | Curve 65 | 1485 | TBC | no | ROAD CLOSURE, nights, notts, National highways, national rail | 2025-11-01 sat 1st: tell network rail; 2025-11-01 mon 10th: NIGHTS
CW - PLAN | N- Charn | Derby Road | Loughborough | Curve (65) | 6669 | TBC | yes | ROAD CLOSURE, nights | 2025-11-01 wed 12th: NIGHTS
CW - PLAN | N- Melton | Main Street | Stathern | CG 60 | 6461 | TBC | yes | ROAD CLOSURE,cones, off peak, lights 17/06 | 2025-11-01 tue 18th: OFF PEAK
CW - PLAN | N- Melton | Mill Hill | Stathern | above | above | above | above | above | 2025-11-01 tue 18th: OFF PEAK
CW - PLAN | N- Melton | Penn Lane | Stathern | above | above | above | above | above | 2025-11-01 tue 18th: OFF PEAK
RF to meet KR 17 june for more stathern jobs
CW - SD | N- Charn | Iveshead Road | Shepshed | flex 55 | 531 | TBC | no | ROAD CLOSURE, off peak | bar: 2025-12-01 mon 1st
|  |  | 2025-11-01 | Gang 2 (South)
5 x days/nights free | bar: 2025-11-01 mon 3rd to 2025-11-01 fri 7th
CW - Reactive | S-H&B | Atherstone Road | Twycross | Curve (60) | 18870 | TBC | no | ROAD CLOSURE,nights , National highways | 2025-11-01 thu 13th: NIGHTS
CW - Reactive | S-H&B | Atherstone Road | Appleby Magna | above | above | above | above | above | 2025-11-01 thu 13th: NIGHTS
CW - Reactive | S-H&B | Burton Road | Norton Juxta | above | above | above | above | above | 2025-11-01 thu 13th: NIGHTS
1 x Day | bar: 2025-11-01 mon 17th
CW - SD | S-Harbor | Smeeton Road | Gumley | CG | 1086 | TBC | tbc | ROAD CLOSURE, cones | 2025-11-01 sat 22nd: PERMIT GRANTED
CW - SD | S-Harbor | Main Street | Gumley | above | above | above | above | above | 2025-11-01 sat 22nd: PERMIT GRANTED
CW - SD | S-Harbor | Foxton Road | Gumley | above | above | above | above | above | 2025-11-01 sat 22nd: PERMIT GRANTED
CW - Reactive | S-H&B | Brookside | Burbage | Curve | 5364 | TBC | TBC | ROAD CLOSURE,off peak,cones, lane closure, National Highways | 2025-12-01 sat 6th: PERMIT PENDING
CW - Reactive | S-H&B | Far Lash | Burbage | above | above | above | above | above | 2025-12-01 sat 6th: PERMIT PENDING
|  |  | 2025-12-01 | Gang 1
TBC
|  |  | 2025-12-01 | Gang 2
TBC
|  |  | 2026-01-01 | Gang 1
|  |  | 2026-01-01 | Gang 2
|  |  | 2026-02-01 | Gang 1
CW - PLAN | N- Charn | Leicester Road | Shepshed | Cuve 60 | 8049 | TBC | yes | Road Closure, sch hols | 2026-02-01 sat 21st: PAA PENDING
CW - PLAN | N- Charn | Cambridge Street | Shepshed | above | above | above | above | above | 2026-02-01 sat 21st: PAA PENDING
CW - PLAN | N- Charn | Newland Avenue | Shepshed | above | above | above | above | above | 2026-02-01 sat 21st: PAA PENDING
CW - PLAN | N- Charn | Forest Street | Shepshed | above | above | above | above | above | 2026-02-01 sat 21st: PAA PENDING
CW - PLAN | N- Charn | Park Avenue | Shepshed | above | above | above | above | above | 2026-02-01 sat 21st: PAA PENDING
|  |  | 2026-02-01 | Gang 2 (South)
CW - Reactive | S-Harbor | Rugby Road | South Kilworth | Flex | 12706 | TBC | TBC | ROAD CLOSURE, cones Northamptonshire CC | bar: 2026-02-01 mon 16th to 2026-02-01 fri 20th; 2026-02-01 mon 23rd to 2026-02-01 fri 27th; 2026-03-01 mon 2nd to 2026-03-01 fri 6th
CW - Reactive | S-Harbor | South Kilworth Road | North Kilworth | above | above | above | above | above | bar: 2026-02-01 mon 16th to 2026-02-01 fri 20th; 2026-02-01 mon 23rd to 2026-02-01 fri 27th; 2026-03-01 mon 2nd to 2026-03-01 fri 6th
CW - Reactive | S-Harbor | North Road | South Kilworth | above | above | above | above | above | bar: 2026-02-01 mon 16th to 2026-02-01 fri 20th; 2026-02-01 mon 23rd to 2026-02-01 fri 27th; 2026-03-01 mon 2nd to 2026-03-01 fri 6th
|  |  | 2026-03-01 | Gang 1 (North)
CW - PLAN | N- Melton | Dalby Road | Old Dalby | Prolay/Flex | 5406 | TBC | No | Road Closure, nights? | 2026-03-01 tue 10th: nights?
CW - PLAN | N- Melton | Station Road | Old Dalby | above | above | above | above | above | 2026-03-01 tue 10th: nights?
CW - PLAN | N- Melton | Waltham Road | Eastwell | Flex/ Curve 60 | 7425 | TBC | yes | ROAD CLOSURE, 3 way lights,works commence @9am | bar: 2026-03-01 mon 16th to 2026-03-01 fri 20th
CW - PLAN | N- Melton | Eastwell Road | Goadby | above | above | above | above | above | bar: 2026-03-01 mon 16th to 2026-03-01 fri 20th
CW - PLAN | N- Melton | Eastwell Road | Waltham | above | above | above | above | above | bar: 2026-03-01 mon 16th to 2026-03-01 fri 20th
CW - PLAN | N- Charn | Colby Drive | Thurmaston | Flex | 860 | TBC | yes | Road Closure, Leicester CC RS | bar: 2026-03-01 sun 22nd
CW - PLAN | N- Charn | Blout Road | Thurmaston | above | above | above | above | above | bar: 2026-03-01 sun 22nd
CW - PLAN | N- Charn | Griffin Close | Thurmaston | above | above | above | above | above | bar: 2026-03-01 sun 22nd
CW - PLAN | N- Charn | Hamilton Lane | Barkby Thorpe | flex 55 & Curve 60 | 2237 | TBC | yes | ROAD CLOSURE, tlights | bar: 2026-03-01 mon 23rd to 2026-03-01 wed 25th
CW - PLAN | N- Charn | King Street | Thurmaston | above | above | above | above | above | bar: 2026-03-01 mon 23rd to 2026-03-01 wed 25th
CW - PLAN | N- Charn | King Street | Barkby Thorpe | above | above | above | above | above | bar: 2026-03-01 mon 23rd to 2026-03-01 wed 25th
CW - PLAN | N- Charn | Mill Road | Thurcaston | Prolay Curve | 1115 | TBC | No | Road Closure Off peak | 2026-03-01 thu 26th: OFF PEAK
CW - PLAN | N- Charn | Leicester Road | Thurcaston | above | above | above | above | above | 2026-03-01 thu 26th: OFF PEAK
CW - PLAN | N- Charn | High Street | Quorn | Curve 60 | 562 | TBC | yes | ROAD CLOSURE Sunday - drainage must go in first | bar: 2026-03-01 sun 29th
|  |  | 2026-03-01 | Gang 2 (South)
Note on C161: Julie X Wilkinson: usrn 16400481
Note on D41: Julie X Wilkinson: W/C 3rd March - 12 week lead time
Note on D63: Julie X Wilkinson: W/C 7th April - 12 week lead time
Note on D87: Julie X Wilkinson: W/C 7th April - 12 week lead time
Note on D108: Julie X Wilkinson: W/C 5th May - 12 week lead time
Note on D136: Julie X Wilkinson: W/C 5th May - 12 week lead time
Note on D162: Julie X Wilkinson: W/C 9th June - 12 week lead time
Note on D186: Julie X Wilkinson: W/C 9th June - 12 week lead time
Note on D206: Julie X Wilkinson: W/C 7th July - 12 week lead time
Note on D223: Julie X Wilkinson: W/C 7th July - 12 week lead time
Note on D240: Rebecca Forknall: W/C 4th Aug - 12 week lead time
Note on D255: Rebecca Forknall: W/C 4th Aug - 12 week lead time
Note on D268: Julie X Wilkinson: W/c 8th Sept - 12 week lead time
Note on D270: Julie X Wilkinson: W/c 8th Sept - 12 week lead time
Note on D272: Julie X Wilkinson: W/c 6th Oct - 12 week lead time
Note on D274: Julie X Wilkinson: W/c 6th Oct - 12 week lead time
Note on D276: Julie X Wilkinson: W/c 3rd Nov - 1 2 week lead time
Note on D287: Julie X Wilkinson: W/c 8th Dec - 12 week lead time
Note on D303: Julie X Wilkinson: W/c 8th Dec - 12 week lead time
Note on E5: Julie X Wilkinson: Foam mix used on site
Note on E11: Julie X Wilkinson: potentially use foam mix on site
Note on F23: Julie X Wilkinson: meterage increased from 11909 m2 to 14316.26 m2
Note on F31: Julie X Wilkinson: meteraged increased from 876 m2 to 1011 m2
Note on F33: Julie X Wilkinson: meterage decreased 2689 m2 to 2458 m2
Note on F159: Julie X Wilkinson: meterage increased from 1231 m2 to 4375 m2
Note on F176: Julie X Wilkinson: meterage increased from 2424 m2 to 3401 m2
Note on F284: Julie X Wilkinson Meterage incrased from 9131 m2 to 12706
Note on F299: Julie X Wilkinson: meterage increased from 699 m2 to 1114.51 m2
Note on K5: Julie X Wilkinson: Bridge street got opened at 15:30 today
Note on M5: Julie X Wilkinson: gang not off site until 4pm due to shortage of materials
Note on AY23: Julie X Wilkinson: extra night needed for paco
Note on AY25: Julie X Wilkinson: extra night needed for paco
Note on BK37: Julie X Wilkinson: gang not working as patching has all been completed
Note on BP40: Julie X Wilkinson: road to remain closed tonight due to wet weather and foam mix needing to dry
Note on BR40: Julie X Wilkinson: Works will now take place in 4 days instead of 5 (Saturday 31st cancelled from permit)
Note on BX45: Julie X Wilkinson: Holcim cancelled works 05/06/2025 due to predicited poor weather conditions
Note on BZ47: Julie X Wilkinson: Holcim cancelled works 07/06/2025 due to predicited poor weather conditions
Note on CC52: Julie X Wilkinson: Delay in opening road back up at night
Note on CE52: Julie X Wilkinson: road opened late site diary shows 15.45
Note on CG47: Julie X Wilkinson: Holcim cancelled these works for the complete weekend
Note on CG48: Julie X Wilkinson: Holcim cancelled these works for the complete weekend
Note on CH47: Julie X Wilkinson: Holcim cancelled these works for the complete weekend
Note on CH48: Julie X Wilkinson: Holcim cancelled these works for the complete weekend
Note on DF70: Julie X Wilkinson: job now just two days
Note on DV105: Julie X Wilkinson: permit needed for iron works to be completed no marshalls needed - RG just put out road closure
Note on DY105: Julie X Wilkinson: permit needed for iron works to be completed no marshalls needed - RG just put out road closure
Note on EH143: Julie X Wilkinson: permit forThursday night for iron works no marshalls needed
Note on EI137: Julie X Wilkinson: 3rd night needed for ironworks
Note on EK117: Julie X Wilkinson: WJ needed for studs - still to be closed and marshalls needed
Note on IF257: Julie X Wilkinson: 7th night for lining only

## Sheet2 (hidden)
Ashby Road / Hinckley Road, Cadeby and Osbaston (cross roads) | Hickling Road | Nether Broughton
Coventry Road, Hinckley (cross roads) | Ashby Road | Woodville
B676 from Buckminster Rd to Coston Rd, Buckminster | Stapleford Xroads | Somerby
Skeffington and Glebe Road, Tilton (narrow lane) | Market Bosworth Xroads | Cadeby
A511 Bardon Road, Bardon | Coventry Road | Hinckley
Ashby Road, Woodville | Thorpe Satchville
Ashby Road, Thingstone (2 x three way junctions) | Skeffington
Mill Hill, Laughton (narrow lane) | Osgathorpe boarder
A5460 Junction 21 Approach, Braunstone | Ashfordby
Hickling Road, Nether Broughton (New Funding) | Stathern
Oakham Road, Somerby (1) | Burton & Dalby
Main Road / Melton Road, Asfordby (2) | Illston Lane | Frisby
Blacksmith End, Stathern (3) | Mill Hill | Laughton
Borrough Road, Little Dalby (3) | North Street | Melton
Ilston Lane, Frisby (3) | Burneston Way | Wigston
Goadby Road, Goadby (TO QUESTION VALIDITY OF SCHEME) | Craythorne Way | Wigston
A5199 Bull Head Street, Leicester Road, Wigston | Dean Road West | Hinckley
North Street, Melton Mowbray | Harrogate Way | Wigston
| Rookery Close | Fenny Drayton
| Waterfall Way | Barwell
| Hinckley Road | Stoke Golding
Blaby | Moore Road | Barwell
Charnwood | Springfield Road | Hinckley
Harborough | St Bernards Road | Whitwick
Hinckley & Bosworth | The Oval | Oadby/Wigston border
Melton | Broadway | Loughborough
NWL | Holt Drive | Loughborough
Oadby & Wigston | Willow Road | Loughborough
Various
| Cosby Road | Br. Astley
| Brookside | Hinckley
| Park Hill Lane | Seagrave
| London Road | Great Glen
| Soar Mills | Sutton in the Elms
Flood Span at Blaby
| Wanlip Road | Syston
| Cosby Road | Broughton Astley
| Dishley Hill | Hathern