## Guidance Sheet
Grant Assurance Data Return template - guidance for LAs
Which projects should I enter information about?
This template is designed to support LAs to provide details of the projects being funded by their High Needs Provision Capital Allocations (HNPCA). As we have now announced five years of HNPCA funding, LAs should include all projects that have used HNPCA funding since 2021-22 up to 2025-26.
LAs should return their updated templates to the department by 1 October 2025 by emailing the completed template to: capital.allocations@education.gov.uk.
LAs should enter data on any known projects that will benefit from investment as a result of their HNPCA. We recognise that at this stage projects may be at different stages in their delivery cycle, and may still be in the process of being fully developed (feasibility, planning, procurement etc). Recording a project on this form does not signal or create a final commitment to this project. LAs are simply requested to provide as complete a picture of intended works as possible. We recognise that not all HNPCA funding may be committed by 1 October 2025, and therefore the template includes a record of funding that is not currently committed to a project. We would however encourage all LAs to complete the data return template to the best of their ability as this provides valuable data to the department as to the needs and the priorities of the sector in respect of High Needs capital funding, which will help inform future policy development.
If certain information might be considered locally or commercially sensitive (i.e. detailed costings for projects still in procurement or naming specific institutions where this might pre-empt local consultation), LAs should consider whether they can instead provide indicative figures or generic information (e.g. a plan to create a new SEN unit in an unidentified local secondary, pending conclusion of local consultation etc.). If LAs have any queries or concerns about the information requested, they can contact the department at capital.allocations@education.gov.uk for further information or guidance.
How to Enter Information
You can select your LA name from the drop down list in Cell D7. This will auto-populate the LA Number and HNPCA funding in the boxes below. If for any reason there is any discrepancy between this figure and the figure available on the allocations spreadsheet on GOV.UK, the published allocations spreadsheet is final.
Enter the date of completion in Cell L7.
The total amount of funding from HNPCA that your LA has committed and uncommitted will auto-complete in cells L12 to L13 as you complete columns M,N,O,P and Q
Please complete all yellow boxes, the template will not populate with last year's return.
Information on individual projects
In the section of the form indicated as Project Information please provide the requested details for each column for any projects being funded as a result of any HNPCA funding.
When you click on a yellow cell to enter data, instructions of how to enter the data will appear in a white box.
Some of these fields are protected to only allow specific answers. Please select the most relevant answer from the selection available. Please do not override and provide a different answer as this may not be counted as it is more difficult to process.
Where final costings are not yet known, you may choose to provide indicative figures in the funding columns. When entering cost information please provide details of any proposed costs being met from:
a) your LA's 2021-22 HNPCA grant;
b) your LA's 2022-23 HNPCA grant;
c) your LA's 2023-24 HNPCA grant;
d) your LA's 2024-25 HNPCA grant;
e) your LA's 2025-26 HNPCA grant;
f) housing developer contributions (e.g. s106, CIL); and
g) any additional proposed funding from other sources being used to support the project (e.g. from Basic Need funding, council reserves, etc.).
If the project will not be using funding from one of the above sources, please put a '0' in the relevant column.
When entering the number of places being delivered by the project, please break these down into:
a) the initial number of new High Needs places expected to be delivered by the project when it is first completed (i.e. places that didn't previously exist or were not suitable for High Needs provision);
b) the total number of new places expected to be delivered by this project once it is at full capacity; and
c) the number of places expected to be reprovided by this project. By 'reprovided places' we mean High Needs places that may have already existed, but were not suited to meet local needs (i.e. places that have been adapted, remodelled or otherwise improved to change their use, bring them up to modern standards or to meet a wider range of need).
If you require additional rows added to the table, select the bottom row of the table, and right click > insert row.
Data validation is drawn from tables on a hidden tables tab. Please do not change the tables or your data will not be consistent and we won't be able to analyse it.
Please also use the 'Description of Project' section to set out further details of any listed projects. For example, if you have selected 'adapting existing provision to meet different needs' as the main purpose of your project, please set out what those adaptations are and how you expect them to improve the available provision. Please also use this space to let us know where Safety Valve capital has been used to fund a project. This kind of information helps us to better understand how local authorities are prioritising their funding and will help to inform future policy development.
Acronyms used in this return template
AP - Alternative Provision
AY - Academic Year
HN - High Needs
HNPCA - High Needs Provision Capital Allocations
LA - Local Authority
N/A - Not Applicable
PRU - Pupil Referral Unit
RP - Resourced Provision
SEN - Special Educational Needs
SPI - Special Post-16 Institution
TBC - To Be Confirmed
UTC - University Technical College

## Data Return
High Needs Provision Capital Allocations - Assurance Data Return
LAs should return this completed template to the department by 1 October 2025 by emailing the completed template to: capital.allocations@education.gov.uk. For more information on how to complete this form, please see the included Guidance Sheet.
| LOCAL AUTHORITY | Leicestershire | [6 empty] | Date Template Completed | 2025-09-30
| LA Number | 855
| 2021-22 HNPCA Grant | 3641554.5
| 2022-23 HNPCA Grant | 12735106.2 | [6 empty] | HNPCA total funding
| 2023-24 HNPCA Grant | 11759690.01 | [6 empty] | Total funding committed | 23239596.71
| 2024-25 HNPCA Grant | 3248168.87 | [6 empty] | Total uncommitted funding | 17964552.65
| 2025-26 HNPCA Grant | 9819629.78
Project Information
[6 empty] | Places |  |  | Types of Need |  | Indicative/Provisional Funding | [7 empty] | Local Consultation |  | Project delivery
Name of School or Institution | URN (If known) | Institution Type | If institution type is 'other', please provide a brief description | What is the main purpose of the project? (please provide additional project information in column Z) | Age Range | Initial number of new HN places operational upon completion | Total number of new HN places the project will deliver once at capacity | Number of reprovided HN places | What is the primary type of need this project will address? | In addition to the primary type of need, will the project address any other types of need? | How much 2021-22 HNPCA funding will the project use? | How much 2022-23 HNPCA funding will the project use? | How much 2023-24 HNPCA funding will the project use? | How much 2024-25 HNPCA funding will the project use? | How much 2025-26 HNPCA funding will the project use? | In addition to HNPCA, how much additional funding from housing developer contributions (s106 and CIL) will the project use? | If the project will use any other additional funding, how much funding will this be? | What is the source of this additional funding? | Have you consulted locally regarding this project? | Please give more details about what you have done as part of the consultation process | Has this project been completed? | If the project plans have slipped, why is this? | Which academic year do you anticipate the project being completed and the places being in use? | Description of Project Please briefly set out any further details of the project - this helps us to better understand how funding is being prioritised.
Foxfields Academy | 148029 | Academy/free school - Special | N/A | Entirely new free school | Primary and secondary | 20 | 50 | 0 | Social, Emotional and Mental Health | No - The project will only address its primary type of need | 1979988.5 | 269752.5 | 0 | 0 | 0 | 0 | TBC | TBC | Consultation completed | Followed Free School presumption process arrangements for establishing a new school | Yes, the project has been completed | N/A | AY 2020/21 | Completion of First Phase (50 places) of new SEMH school
Foxfields Academy | 148029 | Academy/free school - Special | N/A | Expansion of existing provision (existing site) | Primary and secondary | 30 | 30 | 0 | Social, Emotional and Mental Health | No - The project will only address its primary type of need | 0 | 3954808 | 0 | 0 | 0 | 0 | TBC | TBC | Consultation completed | Academy submitted a significant change application | Yes, the project has been completed | N/A | AY 2023/24 | The project consists of a standalone block providing 2x additional classrooms. Due to delay in DfE delivering Bowman Academy also needed to refurb coachhouse to take interim pupils for 1 year
Ashmount School | 120352 | Maintained Special school | N/A | Expansion of existing provision (existing site) | Primary, secondary and post-16 | 24 | 24 | 0 | Severe Learning Difficulty | No - The project will only address its primary type of need | 0 | 1233282 | 0 | 0 | 0 | 0 | TBC | TBC | Consultation completed | Head Teacher notified parents via news letter and perspective parents site visits | Yes, the project has been completed | N/A | AY 2023/24 | School temporarily used a conference room for 12 places whilst construction of new 2 classroom block took place
Forest Way School | 137905 | Academy/free school - Special | N/A | Expansion of existing provision (existing site) | Primary, secondary and post-16 | 3 | 10 | 0 | Severe Learning Difficulty | Yes - Profound & Multiple Learning Difficulty | 0 | 761335 | 0 | 0 | 0 | 103963 | TBC | TBC | Consultation completed | Head Teacher notified parents via news letter and perspective parents site visits | Yes, the project has been completed | N/A | AY 2023/24 | Construction of new 2 classroom block
Birch Wood (Melton Area Special School) | 134640 | Maintained Special school | N/A | Expansion of existing provision (existing site) | Primary, secondary and post-16 | 12 | 12 | 0 | Severe Learning Difficulty | Yes - Profound & Multiple Learning Difficulty | 0 | 606653 | 0 | 0 | 0 | 30370 | TBC | TBC | Consultation completed | Head Teacher notified parents via news letter and perspective parents site visits | Yes, the project has been completed | N/A | AY 2022/23 | Conversion of staffroom and soft play area into new EYFS base with freeflow into internal courtyard works completed.
Birch Wood (Melton Area Special School) | 134640 | Maintained Special school | N/A | Expansion of existing provision (existing site) | Primary, secondary and post-16 | 6 | 6 | 0 | Profound & Multiple Learning Difficulty | Yes - The project will address a range of other needs | 0 | 90000 | 0 | 0 | 0 | 0 | TBC | TBC | N/A | N/A | Yes, the project has been completed | N/A | AY 2022/23 | Install mezzanine floor to create space for Art Studio - The previous staffroom converted to an additional classroom and the former Art room became the staff room.
Dorothy Goodman School | 138156 | Academy/free school - Special | N/A | Expansion of existing provision (satellite site) | Primary, secondary and post-16 | 24 | 24 | 0 | Severe Learning Difficulty | Yes - Profound & Multiple Learning Difficulty | 0 | 194430 | 0 | 0 | 0 | 0 | TBC | TBC | Consultation completed | Head Teacher notified parents via news letter and perspective parents site visits | Yes, the project has been completed | N/A | AY 2022/23 | DG operating a satelitte site at Lubbesthorpe primary. Project remodelling work to provide external play, sensory space, access to other teaching areas works completed.
Dorothy Goodman School | 138156 | Academy/free school - Special | N/A | Improvement of an existing provision | Primary, secondary and post-16 | 10 | 10 | 0 | Severe Learning Difficulty | Yes - Profound & Multiple Learning Difficulty | 0 | 600000 | 0 | 0 | 0 | 172374 | TBC | TBC | N/A | N/A | Yes, the project has been completed | N/A | AY 2023/24 | Dorothy Goodman Reception Remodel to provide additional teaching space for additional pupils scheme to be agreed expected delivery September 2023.
Dorothy Goodman School | 138156 | Academy/free school - Special | N/A | Improvement of an existing provision | Primary, secondary and post-16 | 24 | 0 | 24 | Severe Learning Difficulty | Yes - Profound & Multiple Learning Difficulty | 283509 | 27755 | 0 | 0 | 0 | 0 | TBC | TBC | N/A | N/A | Yes, the project has been completed | N/A | AY 2022/23 | Redmoor Academy served notice on DG to vacate 2 of their classrooms occupied by DG students. LCC relocated a modular building onto the campus to enable DG students to remain in this locality.
Maplewell Hall School | 120348 | Maintained Special school | N/A | Expansion of existing provision (existing site) | Primary, secondary and post-16 | 12 | 12 | 0 | Moderate Learning Difficulty | No - The project will only address its primary type of need | 0 | 65000 | 0 | 0 | 0 | 0 | TBC | TBC | N/A | N/A | Yes, the project has been completed |  | AY 2023/24 | Passported funding to school to deliver a single teaching base project completed.
Robert Smyth Academy | 137161 | Academy/free school - Mainstream | N/A | Entirely new SEN unit within a school | Secondary | 5 | 15 | 0 | Autistic Spectrum Disorder | No - The project will only address its primary type of need | 600000 | 0 | 0 | 0 | 0 | 0 | TBC | TBC | Consultation completed | School consulted with local community as part of significant change process and submission approved Jan 2022 |  |  |  | Construct new teaching bases for pupils with C&I . Funding passported to Trust to deliver project.
All Saints Church of England Primary School | 145973 | Academy/free school - Mainstream | N/A | Expansion of existing provision (existing site) | Primary | 10 | 20 | 0 | Autistic Spectrum Disorder | No - The project will only address its primary type of need | 23263 | 0 | 0 | 0 | 0 | 0 | TBC | TBC | Consultation completed | School consulted with local community as part of significant change process and submission approved June 2022 | Yes, the project has been completed |  | AY 2022/23 | Refurbishment of internal space to expand current C&I provision project completed.
The Cedars Academy | 140787 | Academy/free school - Mainstream | N/A | Entirely new SEN unit within a school | Primary, secondary and post-16 | 5 | 15 | 0 | Social, Emotional and Mental Health | No - The project will only address its primary type of need | 554794 | 0 | 0 | 0 | 0 | 0 | TBC | TBC | Consultation completed | School consulted with local community as part of significant change process and submission approved September 2020 | Yes, the project has been completed |  | AY 2022/23 | New standalone building constructed on former Youth block site project completed April 2022. Funding passported to Academy Trust to deliver project.
Westfield Junior School | 119928 | Maintained school | N/A | Improvement of an existing provision | Primary | 25 | 0 | 25 | Speech, Language and Communication | No - The project will only address its primary type of need | 0 | 92083 | 0 | 0 | 0 | 0 | TBC | TBC | N/A | N/A | Yes, the project has been completed |  | AY 2022/23 | Install stud wall to exisiting classroom to create a corridor as currently the end class have to walk through the middle classroom to access WCs which is distracting and disruptive. The toilet block needs to be reconfigured to include wash down space - exisitng WC accessible toilet not fit for purpose and being replaced.
Wreake Valley | 137983 | Academy/free school - Mainstream | N/A | Expansion of existing provision (existing site) | Primary, secondary and post-16 | 15 | 45 | 0 | Speech, Language and Communication | No - The project will only address its primary type of need | 0 | 243452 | 0 | 0 | 0 | 0 | TBC | TBC | Consultation completed | RSC approved proposal after public consultation with local community as part of SCA | Yes, the project has been completed |  | AY 2022/23 | Refurbishment of exsiting building to provide 6 classrooms, staff area and support spaces. Funding passported to the Academy Trust to deliver project.
Lutterworth John Wycliffe School | 144111 | Academy/free school - Mainstream | N/A | Entirely new SEN unit within a school | Primary | 5 | 12 | 0 | Autistic Spectrum Disorder | Yes - The project will address a range of other needs | 0 | 78083 | 0 | 0 | 0 | 0 | TBC | TBC | N/A | N/A | Yes, the project has been completed |  | AY 2022/23
Bowman Academy | 150787 | Academy/free school - Special | N/A | Entirely new free school | Primary and secondary | 27 | 64 | 0 | Social, Emotional and Mental Health | No - The project will only address its primary type of need | 200000 | 831558 | 0 | 0 | 0 | 0 | TBC | TBC | N/A | LA successful in bidding for a new SEMH School | Yes, the project has been completed | Other | AY 2024/25 | DfE constructed School 12 month delay due to agreeing costing. LA funded abnormals costs as detailed in MOU
Farley Way Quorn |  | Academy/free school - Special | N/A | Entirely new free school | Primary and secondary | 0 | 90 | 0 | Speech, Language and Communication | No - The project will only address its primary type of need | 0 | 1250000 | 1000000 | 0 | 0 | 0 | TBC | TBC | N/A | LA successful in bidding for a new C&I School | No, the project has not yet started |  | AY 2027/28 | £2.25m allocated to meet abnormals - DfE driven scheme awaiting confirmation of commencement expected opening Sept 2026 but currently unknown.
Dorothy Goodman School | 138156 | Academy/free school - Special | N/A | Other (please provide details in project description) | Primary, secondary and post-16 | 11 | 36 | 24 | Severe Learning Difficulty | Yes - Profound & Multiple Learning Difficulty | 0 | 1200000 | 0 | 0 | 0 | 0 | TBC | TBC | Consultation completed | Head Teacher notified parents via news letter and perspective parents site visits | Yes, the project has been completed |  | AY 2024/25 | Relocation of EY SEND satellite from temporary location at New Lubbesthorpe to permanent site at Ravenhurst creating additional spaces SCA approved
Birch Wood (Melton Area Special School) | 134640 | Maintained Special school | N/A | Expansion of existing provision (existing site) | Primary, secondary and post-16 | 8 | 8 | 0 | Severe Learning Difficulty | Yes - Profound & Multiple Learning Difficulty | 0 | 15141 | 0 | 0 | 0 | 0 | TBC | TBC | N/A | Head Teacher notified parents via news letter and perspective parents site visits | Yes, the project has been completed |  | AY 2024/25 | Internal Adaptations to create additional space for early years (Ashton House building)
Birch Wood (Melton Area Special School) | 134640 | Maintained Special school | N/A | Expansion of existing provision (existing site) | Primary, secondary and post-16 | 0 | 20 | 0 | Severe Learning Difficulty | Yes - Profound & Multiple Learning Difficulty | 0 | 1000000 | 0 | 0 | 0 | 0 | TBC | TBC | Consultation completed | Head Teacher notified parents via news letter and perspective parents site visits | No, but the project is in progress and on track |  | AY 2025/26 | Creation of 2 additional classrooms - consults with SENA ongoing pupils due to attend from Janaury 2026.
St Botolphs Primary School | 120159 | Maintained school | N/A | Other (please provide details in project description) | Primary | 10 | 10 | 0 | Autistic Spectrum Disorder | Yes - The project will address a range of other needs | 0 | 100000 | 0 | 0 | 0 | 0 | TBC | TBC | Consultation completed | Head Teacher notified parents via news letter and perspective parents site visits | Yes, the project has been completed |  | AY 2024/25 | Refurb former DT area to create classroom and sensory room completed new canopy for freeflow completed May 2025
Forest Way Cabin Provision | 137905 | Academy/free school - Special | N/A | New facility within an existing provision | Primary, secondary and post-16 | 0 | 0 |  | Autistic Spectrum Disorder | Yes - The project will address a range of other needs | 0 | 14000 | 0 | 0 | 0 | 0 | TBC | TBC | N/A | N/A | Yes, the project has been completed |  | AY 2024/25 | Creation of outdoor learning space for short-term targeted intervention using and outdoor learning approach
John Wycliffe Primary | 144111 | Academy/free school - Mainstream | N/A | Adapting existing provision to meet different needs | Primary | 0 | 0 | 0 | Autistic Spectrum Disorder | Yes - The project will address a range of other needs | 0 | 26405 | 0 | 0 | 0 | 0 | TBC | TBC | N/A | N/A | Yes, the project has been completed |  | AY 2024/25 | Additional works to secure external area as part of original project.
Westfield Infants School | 119929 | Maintained school | N/A | Improvement of an existing provision | Primary | 0 | 0 | 12 | Autistic Spectrum Disorder | Yes - The project will address a range of other needs | 0 | 81368.7 | 68631.3 | 0 | 0 | 0 | TBC | TBC | Consultation completed | Head Teacher notified parents via news letter and perspective parents site visits | Yes, the project has been completed |  | AY 2025/26 | Refurbishment of internal room to provide teaching space and creation of a sensory room.
Foxfields Academy - Satellite at Hinckley Parks | 148029 | Academy/free school - Special | N/A | Improvement of an existing provision | Primary and secondary | 0 | 0 | 0 | Autistic Spectrum Disorder | Yes - The project will address a range of other needs | 0 | 0 | 48742 | 0 | 0 | 0 | TBC | TBC | Consultation completed | DfE approved transfer from OWLS to CIT - parents ntoified via newsletter and perspective parents site visits | Yes, the project has been completed |  | AY 2024/25 | Remodelling of space to created enchanced teaching environment
Oakfield South at Blaby Stokes | 136754 | AP - PRU (LA maintained) | N/A | Improvement of an existing provision | Primary | 0 | 0 | 0 | Moderate Learning Difficulty | Yes - Moderate Learning Difficulty | 0 | 0 | 4494000 | 0 | 0 | 0 | TBC | TBC | Consultation completed | Head Teacher notified parents via news letter and perspective parents site visits | No, the project has not yet started |  | AY 2025/26 | Reorganisation of school to relocate current primary school into one building and refurb former infant building for Oakfield South to move into
Sapcote All Saints | 144113 | Academy/free school - Mainstream | N/A | Entirely new SEN unit or Resourced Provision within a school | Primary | 0 | 10 | 0 | Autistic Spectrum Disorder | Yes - The project will address a range of other needs | 0 | 0 | 148945 | 0 | 0 | 0 | TBC | TBC | Consultation completed | Head Teacher notified parents via news letter and perspective parents site visits | Yes, the project has been completed |  | AY 2024/25 | Remodelling of space to created enchanced teaching environment
Sharnford Primary | 144110 | Academy/free school - Mainstream | N/A | Accessibility | Primary | 0 | 0 | 0 | Physical Disability | Yes - Physical Disability | 0 | 0 | 128095 | 0 | 0 | 0 | TBC | TBC | N/A | N/A | Yes, the project has been completed |  | AY 2024/25 | create ramped access for pupil in wheelchair
St Peters & St Pauls Syston | 139349 | Academy/free school - Mainstream | N/A | Entirely new SEN unit or Resourced Provision within a school | Primary | 0 | 10 | 0 | Autistic Spectrum Disorder | Yes - The project will address a range of other needs | 0 | 0 | 236977 | 0 | 0 | 0 | TBC | TBC | Consultation completed | Head Teacher notified parents via news letter and perspective parents site visits | No, but the project is in progress and on track |  | AY 2025/26 | Remodelling of space to created enchanced teaching environment for SEND pupils
St Hardulphs | 120119 | Maintained school | N/A | Entirely new SEN unit or Resourced Provision within a school | Primary | 0 | 10 | 0 | Autistic Spectrum Disorder | Yes - The project will address a range of other needs | 0 | 0 | 100000 | 0 | 0 | 0 | TBC | TBC | Consultation completed | Head Teacher notified parents via news letter and perspective parents site visits | No, but the project is in progress and on track |  | AY 2025/26 | Onsite remodelling work to create ERB for 10 pupils
St Botolphs Primary School | 120159 | Maintained school | N/A | Entirely new SEN unit or Resourced Provision within a school | Primary | 0 | 10 | 0 | Autistic Spectrum Disorder | Yes - The project will address a range of other needs | 0 | 0 | 100000 | 0 | 0 | 0 | TBC | TBC | Consultation completed | Head Teacher notified parents via news letter and perspective parents site visits | Yes, the project has been completed |  | AY 2024/25 | Refurbishment of former DT room to create SEND room and sensory space
Wigston All Saints | 145973 | Academy/free school - Mainstream | N/A | Improvement of an existing provision | Primary | 0 | 0 | 20 | Autistic Spectrum Disorder | Yes - The project will address a range of other needs | 0 | 0 | 100860 | 0 | 0 | 0 | TBC | TBC | N/A | N/A | Yes, the project has been completed |  | AY 2025/26 | Remodelling of space to created enchanced teaching environment
Hall Orchard Primary | 140230 | Academy/free school - Mainstream | N/A | Other (please provide details in project description) | Primary | 0 | 0 | 0 | Other (please provide details in project description) | Yes - Other (please provide details in project description) | 0 | 0 | 14999 | 0 | 0 | 0 | TBC | TBC | N/A | N/A | Yes, the project has been completed |  | AY 2025/26 | Creation of hygiene room for medical needs pupil
Brownlow Primary | 140702 | Academy/free school - Mainstream | N/A | Entirely new SEN unit or Resourced Provision within a school | Primary | 0 | 10 | 0 | Autistic Spectrum Disorder | Yes - The project will address a range of other needs | 0 | 0 | 100000 | 0 | 0 | 0 | TBC | TBC | Consultation completed | Head Teacher notified parents via news letter and perspective parents site visits | No, but the project is in progress and on track |  | AY 2025/26 | Onsite remodelling work to create ERB for 10 pupils
Woodcote Primary | 120096 | Maintained school | N/A | Entirely new SEN unit or Resourced Provision within a school | Primary | 0 | 10 | 0 | Autistic Spectrum Disorder | Yes - The project will address a range of other needs | 0 | 0 | 10000 | 0 | 0 | 0 | TBC | TBC | Consultation completed | Head Teacher notified parents via news letter and perspective parents site visits | No, but the project is in progress and on track |  | AY 2025/26 | Onsite remodelling work to create ERB for 10 pupils
Newbold Verdon Primary | 119942 | Maintained school | N/A | Improvement of an existing provision | Primary | 0 | 0 | 0 | Autistic Spectrum Disorder | Yes - The project will address a range of other needs | 0 | 0 | 98331 | 0 | 0 | 0 | TBC | TBC | N/A | N/A | No, the project is in progress but has slipped against original plans |  | AY 2025/26 | Remodelling of space to created enchanced teaching environment for SEND pupils
Captains Close Primary | 139845 | Academy/free school - Mainstream | N/A | Improvement of an existing provision | Primary | 0 | 0 | 0 | Autistic Spectrum Disorder | Yes - The project will address a range of other needs | 0 | 0 | 20000 | 0 | 0 | 0 | TBC | TBC | N/A | N/A | Yes, the project has been completed |  | AY 2025/26 | Creation of a sensory room to support teaching and learning of existing ERB
The Latimer Primary School | 119903 | Maintained school | N/A | Improvement of an existing provision | Primary | 0 | 0 | 0 | Other (please provide details in project description) | Yes - Other (please provide details in project description) | 0 | 0 | 5770 | 0 | 0 | 0 | TBC | TBC | N/A | N/A | Yes, the project has been completed | N/A | AY 2024/25 | Secure main entrance & create holding area -door/hatch
The Latimer Primary School | 119903 | Maintained school | N/A | Improvement of an existing provision | Primary | 0 | 0 | 0 | Other (please provide details in project description) | Yes - Other (please provide details in project description) | 0 | 0 | 1727 | 0 | 0 | 0 | TBC | TBC | N/A | N/A | Yes, the project has been completed | N/A | AY 2024/25 | Hatch to complete main entrance/holding area
Burbage Junior School | 119964 | Maintained school | N/A | Improvement of an existing provision | Primary | 0 | 0 | 0 | Other (please provide details in project description) | Yes - Other (please provide details in project description) | 0 | 0 | 12204 | 0 | 0 | 0 | TBC | TBC | N/A | N/A | Yes, the project has been completed | N/A | AY 2024/25 | Invacuation drill - 4 doors unable to be locked as key lock only. Other doors magnetic, thumb lock or firebar Flight risk pupil - reception door/gate playground & swimming pool
Sketchley Hill Primary School Burbage | 119986 | Maintained school | N/A | Improvement of an existing provision | Primary | 0 | 0 | 0 | Other (please provide details in project description) | Yes - Other (please provide details in project description) | 0 | 0 | 8810 | 0 | 0 | 0 | TBC | TBC | N/A | N/A | Yes, the project has been completed | N/A | AY 2024/25 | Doors requiring maglocks due to flight risk pupils
Burton-on-the-Wolds Primary School | 119912 | Maintained school | N/A | New facility within an existing provision | Primary | 0 | 10 | 10 | Other (please provide details in project description) | Yes - Other (please provide details in project description) | 0 | 0 | 28401.67 | 0 | 0 | 0 | TBC | TBC | N/A | N/A | Yes, the project has been completed | N/A | AY 2024/25 | Garden Studio- SEND space
Cossington Church of England Primary School | 120124 | Maintained school | N/A | New facility within an existing provision | Primary | 0 | 0 | 0 | Other (please provide details in project description) | Yes - Other (please provide details in project description) | 0 | 0 | 16516 | 0 | 0 | 0 | TBC | TBC | N/A | N/A | Yes, the project has been completed | N/A | AY 2024/25 | Additional SEND space. Garden studio
Griffydam Primary School | 119918 | Maintained school | N/A | Adapting existing provision to meet different needs | Primary | 0 | 0 | 0 | Other (please provide details in project description) | Yes - Other (please provide details in project description) | 0 | 0 | 29038 | 0 | 0 | 0 | TBC | TBC | N/A | N/A | Yes, the project has been completed | N/A | AY 2024/25 | Create breakout area for pupil starting school. Make outdoor log cabin suitable for year round use
Ibstock Junior School | 119931 | Maintained school | N/A | Accessibility | Primary | 1 | 1 | 0 | Physical Disability | Yes - Other (please provide details in project description) | 0 | 0 | 3500 | 0 | 0 | 0 | TBC | TBC | N/A | N/A | Yes, the project has been completed | N/A | AY 2024/25 | Toileting facilities for pupil starting in September
St Denys Church of England Infant School, Ibstock | 120138 | Maintained school | N/A | Adapting existing provision to meet different needs | Primary | 4 | 4 | 0 | Other (please provide details in project description) | Yes - Other (please provide details in project description) | 0 | 0 | 10990 | 0 | 0 | 0 | TBC | TBC | N/A | N/A | Yes, the project has been completed | N/A | AY 2024/25 | Partitioning and withdrawal
St Denys Church of England Infant School, Ibstock | 120138 | Maintained school | N/A | Accessibility | Primary | 0 | 0 | 0 | Other (please provide details in project description) | Yes - Other (please provide details in project description) | 0 | 0 | 14521.14 | 0 | 0 | 0 | TBC | TBC | N/A | N/A | Yes, the project has been completed | N/A | AY 2024/25 | Shower facility in special unit.
Kirby Muxloe Primary School | 140315 | Academy/free school - Mainstream | N/A | Adapting existing provision to meet different needs | Primary | 10 | 10 | 0 | Multi- Sensory Impairment | Yes - The project will address a range of other needs | 0 | 0 | 1226.64 | 0 | 0 | 0 | TBC | TBC | N/A | N/A | Yes, the project has been completed | N/A | AY 2024/25 | Works to Year 1 classroom for SEN children - soundproofing, ramp, fencing
Moira Primary School | 119906 | Maintained school | N/A | New facility within an existing provision | Primary | 10 | 10 | 0 | Other (please provide details in project description) | Yes - The project will address a range of other needs | 0 | 0 | 20744.66 | 0 | 0 | 0 | TBC | TBC | N/A | N/A | Yes, the project has been completed | N/A | AY 2024/25 | Garden studio for SEND space
Moira Primary School | 119906 | Maintained school | N/A | Improvement of an existing provision | Primary | 1 | 1 | 0 | Other (please provide details in project description) | Yes - The project will address a range of other needs | 0 | 0 | 4175.6 | 0 | 0 | 0 | TBC | TBC | N/A | N/A | Yes, the project has been completed | N/A | AY 2024/25 | Child absconded site. Breached perimeter - picket fence and hedge.
New Swannington Primary School | 119917 | Maintained school | N/A | Improvement of an existing provision | Primary | 0 | 0 | 0 | Other (please provide details in project description) | Yes - Other (please provide details in project description) | 0 | 0 | 2556 | 0 | 0 | 0 | TBC | TBC | N/A | N/A | Yes, the project has been completed | N/A | AY 2024/25 | Safeguarding concerns - fencing
New Swannington Primary School | 119917 | Maintained school | N/A | Other (please provide details in project description) | Primary | 0 | 0 | 0 | Other (please provide details in project description) | Yes - Other (please provide details in project description) | 0 | 0 | 5166 | 0 | 0 | 0 | TBC | TBC | N/A | N/A | Yes, the project has been completed | N/A | AY 2024/25 | 2 doors to classrooms currently open. Issues with flight risk pupils
New Swannington Primary School | 119917 | Maintained school | N/A | New facility within an existing provision | Primary | 10 | 10 | 0 | Other (please provide details in project description) | Yes - The project will address a range of other needs | 0 | 0 | 230 | 0 | 0 | 0 | TBC | TBC | N/A | N/A | Yes, the project has been completed | N/A | AY 2024/25 | SEN Space
Newbold Verdon Primary School | 119942 | Maintained school | N/A | Other (please provide details in project description) | Primary | 0 | 0 | 0 | Other (please provide details in project description) | Yes - Other (please provide details in project description) | 0 | 0 | 10683 | 0 | 0 | 0 | TBC | TBC | N/A | N/A | Yes, the project has been completed | N/A | AY 2024/25 | Lightings and ceilings in SEND area being damaged by pupil throwing objects
Newbold Verdon Primary School | 119942 | Maintained school | N/A | Improvement of an existing provision | Primary | 0 | 0 | 0 | Other (please provide details in project description) | Yes - Other (please provide details in project description) | 0 | 0 | 2220 | 0 | 0 | 0 | TBC | TBC | N/A | N/A | Yes, the project has been completed | N/A | AY 2024/25 | Maglock to classroom door in unit- flight risk pupil
Quorn Rawlins Academy | 137640 | Academy/free school - Mainstream | N/A | Accessibility | Secondary | 1 | 1 | 0 | Physical Disability | Yes - Physical Disability | 0 | 0 | 14646 | 0 | 0 | 0 | TBC | TBC | N/A | N/A | Yes, the project has been completed | N/A | AY 2024/25 | Platform lift
Thythorn Field Community Primary School | 119993 | Maintained school | N/A | Improvement of an existing provision | Primary | 0 | 0 | 0 | Physical Disability | Yes - Physical Disability | 0 | 0 | 230 | 0 | 0 | 0 | TBC | TBC | N/A | N/A | Yes, the project has been completed | N/A | AY 2024/25 | Toilet adaptations - hand rails, cubicles too narrow
The LA is currently exploring other options to address its growing demand for specialist places, particularly in its Area Special Schools. Additionally the Delivering Better Value Programme and SEND Review will impact the way in which the LA approaches this issue. The remainder of the HNPCA grant will be utilised alongside the LA's own resources to address these requirements
If you require additional rows added to the table, select the bottom row of the table, and right click > insert row.

## Tables (hidden)
|  | 2021-22 ALLOCATION | 2022-23 ALLOCATION | 2023-24 ALLOCATION | 2024-25 ALLOCATION | 2025-26 ALLOCATION
SELECT INSTITUTION TYPE
- | SELECT LOCAL AUTHORITY | [5 empty] | Independent school | Ofsted inspection judgment | Age Range
301 | Barking and Dagenham | 2159812.71 | 9181089.37 | 5067365.61 | 1093807.65 | 4230915.27 | 16-19 Academy/free school | Outstanding | Under 5s
302 | Barnet | 2928936.6 | 10104935 | 6685996.64 | 1675023.9 | 3950769.4 | Academy/free school - Special | Good | Primary
370 | Barnsley | 1460729.06 | 5714239.13 | 4492168.73 | 1261774.04 | 3780214.76 | Academy/free school - Mainstream | Requires Improvement | Secondary
800 | Bath and North East Somerset | 726954.52 | 4551454.16 | 6903801.98 | 611083.37 | 2627532.63 | AP - Academy or free school | Inadequate | Primary and secondary
822 | Bedford Borough | 517417.54 | 3160879.3 | 2985935.56 | 736462.72 | 2251811.93 | AP - PRU (LA maintained) | This institution is not inspected by Ofsted | Post-16
303 | Bexley | 956587.48 | 4062810.94 | 15138051.54 | 1765862.8 | 3703855.03 | LA nursery school | This institution is open, but has not yet been inspected by Ofsted | Secondary and post-16
330 | Birmingham | 6500323.78 | 21688399.74 | 17731902.03 | 4940122.7 | 14871912.23 | Maintained school | This institution is not yet open | Primary, secondary and post-16
889 | Blackburn with Darwen | 500000 | 2342618.75 | 2550921.36 | 719973.39 | 2642346.85 | Maintained Special school | This institution is still to be determined | Other category in 0-25 age-range (please specify in project description)
890 | Blackpool | 500000 | 1464529.14 | 8174736.8 | 634305.99 | 1566306.14 | Non-Maintained Special School
350 | Bolton | 1327440.51 | 15364796.24 | 4474654.43 | 1298937.12 | 4801753.64 | Other nursery or early years provision
839 | Bournemouth, Christchurch and Poole | 2365961.51 | 9213326.35 | 5894586.3 | 1341728.33 | 4026952.21 | Other school |  | Secondary Type of Need
867 | Bracknell Forest | 500000 | 2725564.43 | 2473486.47 | 4623311.73 | 2211992.27 | Other sixth-form or FE college |  | No - The project will only address its primary type of need
380 | Bradford | 2144168.48 | 9232723.15 | 8869160.4 | 2433636.15 | 7292757.55 | SPI (Special Post-16 Institution) | Primary Type of Need | Yes - The project will address a range of other needs
304 | Brent | 1923257.38 | 5880805.56 | 6786090.03 | 2130266.31 | 6355244.9 | Studio school | Autistic Spectrum Disorder | Yes - Autistic Spectrum Disorder
846 | Brighton and Hove | 1029704.8 | 4706298.11 | 3516201.74 | 849323.16 | 1967112.51 | University technical college | Hearing Impairment | Yes - Hearing Impairment
801 | Bristol, City of | 1840832.33 | 11270922.68 | 6727453.54 | 14470505.23 | 3816159.24 |  | Moderate Learning Difficulty | Yes - Moderate Learning Difficulty
305 | Bromley | 2450780.28 | 6651669.96 | 6165963.93 | 1764938.28 | 5276856.53 |  | Multi- Sensory Impairment | Yes - Multi- Sensory Impairment
825 | Buckinghamshire | 3555125.39 | 11121278.56 | 9860063.34 | 2797448.43 | 8453563.41 |  | Other (please provide details in project description) | Yes - Other (please provide details in project description)
351 | Bury | 4370946.66 | 2931468.09 | 3550642.98 | 1077227.05 | 3231066.37 |  | Physical Disability | Yes - Physical Disability
381 | Calderdale | 551745.88 | 3422213.36 | 2214505.54 | 607364.65 | 2299436.11 |  | Profound & Multiple Learning Difficulty | Yes - Profound & Multiple Learning Difficulty
873 | Cambridgeshire | 2709339.06 | 22581378.82 | 9104835.14 | 2352233.2 | 7109868.63 | Main Purpose of Project | Severe Learning Difficulty | Yes - Severe Learning Difficulty
202 | Camden | 2659040.41 | 8639919.17 | 3243472.99 | 456024.45 | 1323140.3 | Entirely new free school | Social, Emotional and Mental Health | Yes - Social, Emotional and Mental Health
823 | Central Bedfordshire | 1940603.89 | 8760302.88 | 6687071.18 | 1701826.9 | 4421465.35 | Entirely new LA presumption route school | Specific Learning Difficulty | Yes - Specific Learning Difficulty
895 | Cheshire East | 1263815.33 | 7214677.56 | 5744443.81 | 18251968.28 | 5955824.16 | Entirely new SEN unit or Resourced Provision within a school | Speech, Language and Communication | Yes - Speech, Language and Communication
896 | Cheshire West and Chester | 1079140.93 | 5698026.42 | 4700460.85 | 1236794.08 | 4504401.39 | Expansion of existing provision (existing site) | Visual Impairment | Yes - Visual Impairment
201 | City of London | 0 | 0 | N/A | N/A | #N/A | Expansion of existing provision (satellite site)
908 | Cornwall | 2442128.57 | 11147439.51 | 9727957.96 | 2804639.5 | 8317743.57 | Improvement of an existing provision
331 | Coventry | 2426212.34 | 10518024.69 | 6776584.34 | 1686577.16 | 5160168.34 | New facility within an existing provision
306 | Croydon | 1583319.34 | 5578111.89 | 6043026.32 | 1839744.92 | 5548420.56 | Adapting existing provision to meet different needs
942 | Cumberland | N/A | N/A | 4387643.04 | 949593.93 | 2868203.43 | Accessibility | Anticipated completion | Has the project been completed?
909 | Cumbria | 753286.89 | 2672619.17 | N/A | N/A | #N/A | Other (please provide details in project description) |  | Yes, the project has been completed
841 | Darlington | 500000 | 1736535.73 | 1498065.03 | 463367.27 | 1144792.43 |  | AY 2021/22 | No, but the project is in progress and on track
831 | Derby | 1565260.46 | 7274447.9 | 5863036.38 | 1640408.57 | 4973930.88 |  | AY 2022/23 | No, the project is in progress but has slipped against original plans
830 | Derbyshire | 2489980 | 10179536.29 | 13242601.34 | 4204819.41 | 12609313.48 |  | AY 2023/24 | No, the project has not yet started
878 | Devon | 2145040.68 | 12790568.34 | 12965577.06 | 3772852.11 | 11243583.62 |  | AY 2024/25 | The project is no longer going ahead
371 | Doncaster | 1064926.66 | 5502839.49 | 5543010.11 | 1614401.75 | 4155520.23 |  | AY 2025/26
838 | Dorset | 500000 | 4901989.18 | 5743828.05 | 12297935.22 | 5023392.13 |  | AY 2026/27 | If project has been cancelled
332 | Dudley | 1416043.37 | 6707208.5 | 5877397 | 1718054.1 | 3633512.39 | Local consultation | AY 2027/28 | N/A
840 | Durham | 2354865.22 | 8510183.33 | 7805806.52 | 2063484.65 | 5061175.62 | Consultation completed | AY 2028/29 | Funding needed to be prioritised elsewhere
307 | Ealing | 2298819.98 | 6825163.98 | 6754992.16 | 1942886.19 | 5812461.36 | Consultation in progress | AY 2029/30 | Costs of the project were higher than anticipated
811 | East Riding of Yorkshire | 746801.38 | 4918860.25 | 5156632.27 | 1506106.43 | 4479279.8 | Consultation planned, but not yet started | Beyond 2030 | Site was not viable
845 | East Sussex | 1273987.46 | 6726770.93 | 6932116.44 | 1935934.37 | 7031213.75 | TBC | NA | The need for places has changed
308 | Enfield | 1317955.79 | 4485182.52 | 7686580.44 | 2466314.46 | 6181904.95 | N/A |  | Other
881 | Essex | 5238295.05 | 19345531.04 | 20732949.06 | 5685293.86 | 20946099.49
390 | Gateshead | 1343333.38 | 3492238.28 | 2063527.53 | 489679.71 | 1483647.39 |  |  | If the project plans have slipped, why is this?
916 | Gloucestershire | 1988464.83 | 10990306.73 | 8937337.59 | 2280409.91 | 6889243.42 |  |  | N/A
203 | Greenwich | 2784606.77 | 10020102.81 | 6442424.29 | 1322188.6 | 3948641.14 |  |  | Funding needed to be prioritised elsewhere
204 | Hackney | 2724671.29 | 10083307.6 | 5105975.4 | 984214.91 | 3507977.66 |  |  | Costs of the project were higher than anticipated
876 | Halton | 500000 | 2666386.97 | 2198924.32 | 626655.48 | 1197073.37 |  |  | Site was not viable
205 | Hammersmith and Fulham | 2329829.59 | 4801556.14 | 2242432.59 | 390645.27 | 1153669.7 |  |  | Difficulties in procuring work/delays in construction
850 | Hampshire | 6789279.35 | 25243509.04 | 24835932.48 | 7621972.65 | 22866660.69 |  |  | Other
309 | Haringey | 1023937.98 | 9339911.81 | 3364919.1 | 1080832.51 | 2481631.36
310 | Harrow | 821789.71 | 4138547.45 | 5219519.43 | 1407784.88 | 4223677.14
805 | Hartlepool | 500000 | 1384647.48 | 975805.18 | 270604.69 | 822278.13
311 | Havering | 2206149.31 | 7670580.12 | 5675974.72 | 1289438 | 3945057.01
884 | Herefordshire | 648121.72 | 2611683.04 | 2819829.82 | 823167.22 | 2465830.17
919 | Hertfordshire | 4761202.95 | 20007920.5 | 18331544.53 | 4710765.17 | 11116913.94
312 | Hillingdon | 2872215.63 | 15090653.15 | 6120161.02 | 1505204.77 | 4520938.86
313 | Hounslow | 2419088.63 | 9508908.73 | 7156678.31 | 1961385.1 | 5016772.95
921 | Isle of Wight | 500000 | 1050083.77 | 1087841.01 | 356205.65 | 1056771.96
420 | Isles of Scilly | 500000 | 788074.51 | 211925.49 | 500000 | #N/A
206 | Islington | 1834418.8 | 5638378.53 | 3015407.85 | 559637.22 | 1666742.14
207 | Kensington and Chelsea | 2383501.3 | 7461394.79 | 3059324.53 | 270788.92 | 605401.37
886 | Kent | 6638936.62 | 32108713.21 | 29001569.25 | 7980358.94 | 24051816.24
810 | Kingston Upon Hull, City of | 1488666.89 | 7192376.88 | 5389726.66 | 1488209.7 | 3800949.85
314 | Kingston upon Thames | 5114646.33 | 5540177.8 | 3176269.06 | 715027.93 | 2146503.91
382 | Kirklees | 1609971.75 | 15861570.56 | 6977510.55 | 2040132.19 | 6118922.33
340 | Knowsley | 509167.24 | 3890300.75 | 2859035.28 | 760081.74 | 2338916.18
208 | Lambeth | 2541861.32 | 4855965.19 | 3380219.86 | 845627.71 | 2468211.92
888 | Lancashire | 4724149.55 | 20178483.14 | 19581598.78 | 5559078.56 | 19677317.74
383 | Leeds | 4574287.88 | 22576594.86 | 11734902.24 | 2321304.59 | 7026751.28
856 | Leicester | 2013815.67 | 8420348.51 | 5436624.97 | 1290550.8 | 3904359.41
855 | Leicestershire | 3641554.5 | 12735106.2 | 11759690.01 | 3248168.87 | 9819629.78
209 | Lewisham | 2550162.94 | 8052934.31 | 5499203.4 | 1337033.13 | 5710313.22
925 | Lincolnshire | 2986063.27 | 12901062.56 | 12370059.38 | 3434621.64 | 10287855.09
341 | Liverpool | 3460315.08 | 14301620.34 | 7045886.16 | 1373537.2 | 5362801.42
821 | Luton | 1243963.04 | 4313023.04 | 3206488.37 | 845667.16 | 3309602
352 | Manchester | 2323799.63 | 12710172.23 | 9429499.48 | 2323156.39 | 6999299.61
887 | Medway | 1939762.41 | 13540524.23 | 5482269.01 | 1574935.68 | 4837956.77
315 | Merton | 2192304.74 | 13585092.28 | 4344501.44 | 1233921.71 | 3636149.62
806 | Middlesbrough | 1159882.3 | 3848136.66 | 2319833.7 | 471911.54 | 1426412.94
826 | Milton Keynes | 2971552.17 | 10132199.9 | 5546021.24 | 1088334.89 | 3324805.85
391 | Newcastle upon Tyne | 1461608.45 | 7010093.85 | 4113624.62 | 753678.03 | 2295071.73
316 | Newham | 2611716.38 | 7296290.68 | 8494621.03 | 2728149.17 | 8106207.72
926 | Norfolk | 4393596.96 | 14928082.7 | 11853823.34 | 3034143.12 | 13041499.57
812 | North East Lincolnshire | 883215.54 | 2796066.49 | 1741727.99 | 458089.8 | 2513892.71
813 | North Lincolnshire | 729278.21 | 3002092.99 | 2992572.67 | 854468 | 2537798
940 | North Northamptonshire | 1296620.5058 | 7137774.67 | 6803123.52 | 1844172.91 | 3592109.76
802 | North Somerset | 1152776.08 | 3260036.66 | 6919418.33 | 1159472.33 | 3485806.02
392 | North Tyneside | 663431.61 | 2971475.43 | 6926139.22 | 557991.51 | 1688683.13
815 | North Yorkshire | 716840.2 | 6543369.57 | 7491930.42 | 2264233.5 | 6754896.3
929 | Northumberland | 851301.82 | 2665635.95 | 3978192.25 | 1195442.7 | 2932991.21
892 | Nottingham | 2550244.97 | 11973140.92 | 5985535.04 | 1035259.4 | 4888550.83
891 | Nottinghamshire | 5316391.06 | 19988078.32 | 16548153.29 | 4629822.83 | 13967109.52
353 | Oldham | 830008.86 | 3924992.4 | 3396522.64 | 862005.91 | 2602498.11
931 | Oxfordshire | 3520938.22 | 11987215.81 | 10121255.12 | 2620535.16 | 7936968.96
874 | Peterborough | 1777784.42 | 7049175.33 | 3777067.11 | 791525.27 | 3068709.34
879 | Plymouth | 1447787.32 | 6956768.68 | 4505429.14 | 977733.39 | 2922903.07
851 | Portsmouth | 1181280.62 | 4559375.47 | 2800951.5 | 632119.6 | 1920552
870 | Reading | 954776.21 | 3857086.57 | 3229083.47 | 857535.13 | 2587908.48
317 | Redbridge | 1847655.81 | 8564467.2 | 5629640 | 1228177.41 | 3688563.63
807 | Redcar and Cleveland | 807275.48 | 1608840.55 | 1620911.02 | 369088.86 | 1407560.22
318 | Richmond upon Thames | 6134035.28 | 6926302.6 | 4817630.2 | 1067542.44 | 3168043.77
354 | Rochdale | 1156818.5 | 5268703.92 | 4943824.78 | 1467113.33 | 4441171.57
372 | Rotherham | 1059889.81 | 9228873.48 | 3752187.08 | 1002745.16 | 3681518.55
857 | Rutland | 500000 | 810549.76 | 653392.07 | 172805.84 | 516783.17
355 | Salford | 2467910.75 | 10206097.65 | 5055669.69 | 772198.76 | 2358095.63
333 | Sandwell | 1488855.05 | 6868024.9 | 5753081.72 | 1485421.55 | 4493674.1
343 | Sefton | 675523.94 | 3737877.68 | 4602768.42 | 1370441.57 | 3513521.32
373 | Sheffield | 1944425.94 | 10830418.13 | 6805547.35 | 1538633.19 | 4646094.14
893 | Shropshire | 500000 | 3875585.98 | 4126723.33 | 1141085.94 | 4004729.84
871 | Slough | 2065765.64 | 5297676.02 | 3850624.22 | 1055806.46 | 2614739.88
334 | Solihull | 1055762.06 | 4910941.3 | 3826993.47 | 1000250.26 | 2480572.44
933 | Somerset | 983283.28 | 7683078.75 | 9393696.19 | 2797769.09 | 8363673.63
803 | South Gloucestershire | 1908231.29 | 8377976.54 | 6249892.6 | 1583333.42 | 4837054.12
393 | South Tyneside | 632130.41 | 2559951.67 | 1951861.38 | 517220.91 | 1557983.61
852 | Southampton | 2106601.46 | 7602038.55 | 4424276.2 | 980954.63 | 2996726.45
882 | Southend-on-Sea | 1061569.94 | 4770879.63 | 2411737.52 | 557610.05 | 1695459.81
210 | Southwark | 1306335.56 | 9515182.17 | 5957728.84 | 1697691.64 | 5028291.71
342 | St Helens | 649444.03 | 3242266.7 | 2144123.21 | 525512.49 | 2016550.66
860 | Staffordshire | 2441299.98 | 10278776.55 | 11760528.56 | 3558948.25 | 10707560.99
356 | Stockport | 1274115.32 | 5243398.76 | 4656283.24 | 1350642.5 | 2613610.19
808 | Stockton-on-Tees | 876119.04 | 3458089.77 | 2936671.69 | 736430.18 | 2208960.34
861 | Stoke-on-Trent | 10199220.46 | 5410992.99 | 5208986.52 | 1491835.7 | 4546547.53
935 | Suffolk | 2111925.19 | 9381620.67 | 10758718.22 | 3156716.74 | 9441347.83
394 | Sunderland | 520782.55 | 4280724.63 | 3893510.81 | 1154532.96 | 3489472.06
936 | Surrey | 6920304.22 | 29572648.76 | 19915638.18 | 5391703.52 | 16139321.1
319 | Sutton | 1924542.49 | 6430671.29 | 3370191.61 | 824740.11 | 2491675.84
866 | Swindon | 1598452.1 | 5996536.64 | 3917519.58 | 989736.57 | 2353184.36
357 | Tameside | 1223336.11 | 5732980.3 | 4865994.02 | 1371829.21 | 4145747.91
894 | Telford and Wrekin | 1303857.87 | 4401129.98 | 3798337.84 | 1062775.27 | 3220872.91
883 | Thurrock | 678526 | 4487808.58 | 2994414.65 | 654821.29 | 1988793.3
880 | Torbay | 530149.55 | 2076643.91 | 2011175.75 | 576354.5 | 1405115.72
211 | Tower Hamlets | 2638807.37 | 10507823.99 | 5217690.92 | 1053093.72 | 3999063.92
358 | Trafford | 1676744.46 | 6849264.81 | 4542907.24 | 1213129.43 | 3656658.24
384 | Wakefield | 1473875.94 | 6076097.78 | 6106417.85 | 1834798.64 | 4714510.83
335 | Walsall | 1419381.97 | 7227924.29 | 6091965.42 | 1724970.86 | 5239639.75
320 | Waltham Forest | 1434725.15 | 5514062.59 | 3848027.46 | 1001073.59 | 3016011.5
212 | Wandsworth | 4837414.07 | 15827055.42 | 6015457.03 | 753530.44 | 2242893.97
877 | Warrington | 710210.47 | 2727753.24 | 3144056.6 | 1001367.15 | 3016561.68
937 | Warwickshire | 2747759.95 | 9583082.43 | 7533184.49 | 2027958.72 | 6184147.45
869 | West Berkshire | 500000 | 2651580.15 | 2298724.34 | 496819.17 | 1477676.18
941 | West Northamptonshire | 1522119.7242 | 10900195.92 | 8080272.71 | 2132850.49 | 6436616.19
938 | West Sussex | 4095781.27 | 16479349.06 | 14403828.5 | 3998703.82 | 12015480.34
943 | Westminster | 1040039.03 | 4523712.16 | 2964348.24 | 649082.76 | 1902310.84
213 | Westmorland and Furness | N/A | N/A | 4041095.41 | 987532.01 | 2941763.68
359 | Wigan | 1625569.97 | 5585450.33 | 5162254.91 | 1526636.99 | 4635185.4
865 | Wiltshire | 2055333.02 | 6753045.92 | 8630681.55 | 2591775.7 | 7725888.34
868 | Windsor and Maidenhead | 500000 | 2406905.31 | 1870043.63 | 429329.26 | 1287577.07
344 | Wirral | 1046545.72 | 4390504.05 | 4092751.09 | 1209682 | 2822529.8
872 | Wokingham | 1266317.22 | 5634050.45 | 9578819.9 | 797168.4 | 1896307.48
336 | Wolverhampton | 2254086.99 | 5808551.94 | 3876746.81 | 886241.34 | 2708912.29
885 | Worcestershire | 1539043.81 | 8408559.81 | 8187337.66 | 2394959.65 | 7167130.45
816 | York | 627439.06 | 7056626.19 | 2270412.45 | 451093.47 | 1724481.44