## Sheet1
Highways Works Programme - last update end of September 2018
District | Location | Scheme | Details | Planned Completion Date | Complete
Melton | Ab Kettleby | Heat Damage - Retexturing | Wartnaby Road / "From Six Hills Road to Wartnaby Road" | To be scheduled
Charnwood | Anstey | Surface Dressing | CHARLES DRIVE from Link Road to Andrew Road incl cul-de-sacs | 2018-07-30 | Completed
Charnwood | Anstey | Surface Dressing | CHURCH LANE from Bradgate Road to Bradgate Road | 2018-07-30 | Completed
Charnwood | Anstey | Surface Dressing | DALBY ROAD from Edward Street to Hollow Road | 2018-07-30 | Completed
Charnwood | Anstey | Surface Dressing | KING WILLIAMS WAY from Cropston Road to Charles Drive | 2018-07-30 | Completed
Charnwood | Anstey | Surface Dressing | KITCHENER ROAD from Charnwood Road to Andrew Road | 2018-07-30 | Completed
Charnwood | Anstey | Surface Dressing | LATIMER STREET from jnc Leicester Road to end incl all bitmac speed humps | 2018-07-30 | Completed
Charnwood | Anstey | Surface Dressing | LINK ROAD CUL-DE-SAC (opposite Charles Drive) from Link Road to end | 2018-04-26 | Completed
Melton | Asfordby Hill | MicroAsphalt | Welby Road Service Road from jnc Welby Road to ends at school | To be scheduled | Completed
North West Leicestershire | Ashby de la Zouch | Crossing Renewal | Ashby de la Zouch, Market Street | To be scheduled | N/A
North West Leicestershire | Ashby de la Zouch | Patching | DENTS ROAD | 2018-08-31 | Completed
North West Leicestershire | Ashby de la Zouch | Patching | LEICESTER ROAD | 2018-07-31 | Completed
North West Leicestershire | Ashby de la Zouch | Patching | RANGE ROAD | 2018-07-31 | Completed
Melton | Ashby Folville / Gaddesby | Heat Damage - Retexturing | Gaddesby Lane / Ashby Road | To be scheduled
Harborough | Ashby Magna / Willoughby Waterleys | Heat Damage - Retexturing | Willoughby Road / Ashby Lane / Old Forge Road | To be scheduled
Harborough | Ashby Parva | Heat Damage - Retexturing | Mere Road | To be scheduled
Harborough | Ashby Parva | Patching | Ullesthorpe Road | 2018-05-31 | Completed
Harborough | Ashby Parva / Dunton Bassett | Heat Damage - Retexturing | Dunton Lane / Ashby Parva Road / Little Lunnon | To be scheduled
North West Leicestershire | Ashby Wolds | Heat Damage - Surfacing / Retread | Willesley Wood Side | To be scheduled
Blaby | Aston Flamville / Sharnford | Heat Damage - Retexturing | Sharnford Road / Aston Lane | To be scheduled
Hinckley & Bosworth | Bagworth and Thornton | Surface Dressing | FROM MARKFIELD LANE TO RESERVOIR ROAD | 2018-08-09 | Completed
Hinckley & Bosworth | Bagworth and Thornton | Surface Dressing | RESERVOIR ROAD from "From Markfield Lane To Reservoir Road" across dam to SD joint at Thornton end of dam | 2018-08-09 | Completed
Melton | Barkestone-le-Vale | Heat Damage - Surfacing / Retread | Wood Lane | To be scheduled
Melton | Barkstone | Patching | FISHPOND LANE | 2018-09-30 | Completed
Hinckley & Bosworth | Barlestone | Patching | FERRERS CROFT - SD | 2018-04-30 | Completed
Hinckley & Bosworth | Barlestone | Surface Dressing | NEWBOLD ROAD | 2018-05-14 | Completed
Hinckley & Bosworth | Barlestone | Patching | Newbold Road - SD | 2018-04-30 | Completed
Hinckley & Bosworth | Barlestone | Patching | SMITHY CLOSE - SD | 2018-04-30 | Completed
Hinckley & Bosworth | Barlestone | Patching | SPINNEY DRIVE - SD | 2018-04-30 | Completed
Charnwood | Barrow on Soar | Carriage Way Scheme | Melton Road | 2018-07-03 | Completed
Melton | Barsby | Heat Damage - Retexturing | Ashby Road | To be scheduled
Melton | Barsby | Heat Damage - Retexturing | Gaddesby Lane - Main Street | To be scheduled
Hinckley & Bosworth | Barton In The Beans | Patching | CARLTON ROAD | 2018-09-30 | Completed
Hinckley & Bosworth | Barton In The Beans | Surface Dressing | ODSTONE ROAD from Barton Road, Odstone at culvert to SD joint approx 200m beyond culvert |  | Completed
Hinckley & Bosworth | BARWELL | Patching | CLICKERS WAY | 2018-05-31 | Completed
Hinckley & Bosworth | BARWELL | Patching | RUSSETT CLOSE | 2018-08-31 | Completed
Hinckley & Bosworth | BARWELL | Patching | STAPLETON LANE | 2018-08-31 | Completed
Hinckley & Bosworth | BARWELL | Patching | THE COMMON | 2018-08-31 | Completed
Hinckley & Bosworth | BARWELL | Patching | THE DRIVE | 2018-09-30 | Completed
North West Leicestershire | Belton | Surface Dressing | REMPSTONE ROAD from SD joint near jnc Smithy Lane to Ashby Road under M1 bridge | 2018-04-24 | Completed
Hinckley & Bosworth | Bilestone | Bridge Replacement | Bilstone, Gibbet Lane | To be scheduled | Completed
Harborough | Billesdon | Flood Alleviation Scheme | Billesdon, Brook Lane | To be scheduled | N/A
Harborough | Billesdon | Flood Alleviation Scheme | Billesdon, Great Easton | To be scheduled | N/A
Harborough | Billesdon | Patching | Tilton Rd URGENT SD | 2018-05-31 | Completed
Harborough | Billesdon | Surface Dressing | TILTON ROAD from Leicester Road, Tilton to Tilton Road, Skeffington | 2018-06-06 | Completed
Blaby | Blaby | Patching | Hospital Lane | 2018-07-31 | Completed
Blaby | Blaby | Patching | Mill Lane | 2018-05-31 | Completed
Blaby | Blaby | Carriage Way Scheme | Winchester Avenue | 2018-07-13 | Completed
Blaby | Blaby | Resurfacing | Winchester Avenue | To be scheduled | N/A
North West Leicestershire | Blackfordby | Heat Damage - Retexturing | Butt Lane | To be scheduled
Harborough | Blaston | Vehicle Restraint Systems | Blaston Road | 2018-11-14 | N/A
Melton | Bottesford | Patching | BARKESTONE LANE | 2018-09-30 | Completed
Melton | Bottesford | Surface Dressing | BELVOIR ROAD from jnc A52 to last patch after canal |  | Completed
Melton | Bottesford | Patching | BOWBRIDGE LANE | 2018-09-30 | Completed
Melton | Bottesford | Patching | DEVON LANE | 2018-09-30 | Completed
Melton | Bottesford | Patching | QUEEN STREET | 2018-09-30 | Completed
Blaby | Braunstone | Surface Dressing | KINGSWAY (west side) from jnc Ashurst Road to mini-rndbt at jnc Narborough Road South Service Road | 2018-06-20 | Completed
North West Leicestershire | Breedon | Surface Dressing | BREEDON BRAND from Top Brand, Worthington to near rndbt at jnc A42 incl layby | 2018-05-18 | Completed
Melton | Brentingby | Surface Dressing | SAXBY ROAD from Saxby Road, Melton at Brentingby Lodge to SD joint past Woodfold Lane X-rds | 2018-06-05 | Completed
Harborough | Broughton Astley | Surface Dressing | DUNTON ROAD from SD joint near 30mph Broughton Astley to Broughton Lane, Dunton Bassett | 2018-06-11 | Completed
Harborough | Broughton Astley | Carriage Way Scheme | Main St / Orchard Way | 2019-04-26 | 24%
Harborough | Bruntingthorpe | Patching | BATH LANE | 2018-07-31 | Completed
Harborough | Bruntingthorpe | Patching | CHURCH LANE | 2018-07-31 | Completed
Harborough | Bruntingthorpe | Surface Dressing | CHURCHILL DRIVE from Mere Road to Mere Road | 2018-08-15 | Completed
Harborough | Bruntingthorpe | Surface Dressing | LITTLE END from Main Street to end | 2018-08-15 | Completed
Harborough | Bruntingthorpe | Surface Dressing | PARTRIDGE CLOSE from Churchill Drive to end | 2018-08-15 | Completed
Melton | Buckminster | Surface Dressing | COSTON ROAD from surfacing joint at bend at Byway E38A to 30mph Buckminster | 2018-05-22 | Completed
Hinckley & Bosworth | Burbage | Flood Alleviation Scheme | Burbage, Sketchley Road | To be scheduled | N/A
Melton | Burton and Dalby | Surface Dressing | CHURCH LANE from Gartree Hill Road to end of metalled road | 2018-08-13 | Completed
Melton | Burton and Dalby | Surface Dressing | FROM GARTREE HILL ROAD TO ASHGROVE to end at house called Ashgrove | 2018-08-13 | Completed
Melton | Burton and Dalby | Surface Dressing | GARTREE HILL ROAD from jnc Pickwell Rd through village to SD joint near 30mph - KERBS REQUIRED AT BENDS | 2018-05-02 | Completed
Charnwood | Burton on the Wolds | Patching | Melton Road | 2018-08-24 | 61% Complete
Harborough | Burton Overy / Kings Norton | Heat Damage - Retexturing | Oaks Road / Great Glen Road | To be scheduled
Hinckley & Bosworth | Carlton | Surface Dressing | BARTON ROAD from Bosworth Road to 30mph | 2018-05-17 | Completed
Hinckley & Bosworth | Carlton | Surface Dressing | BOSWORTH ROAD from Barton Road to 30mph | 2018-05-17 | Completed
Hinckley & Bosworth | Carlton | Heat Damage - Retexturing | Main Street | To be scheduled
Hinckley & Bosworth | Carlton / Illston | Patching | Three Gates | 2018-04-30 | Completed
Harborough | Carlton Curlieu | Surface Dressing | KIBWORTH ROAD from Three Gates Road at jnc Grange Road to Carlton Road, Kibworth Harcourt | 2018-06-08 | Completed
Harborough | Carlton Curlieu | Surface Dressing | THREE GATES ROAD from Kibworth Road, Illston at jnc Gartree Road to Kibworth Road, Carlton at jnc Grange Road | 2018-06-07 | Completed
Melton | Chadwell / Wycomb | Heat Damage - Retexturing | Goadby Road / Waltham Lane | To be scheduled
North West Leicestershire | Charley | Carriage Way Scheme | Charley Road | 2018-07-26 | 75%
North West Leicestershire | Charley | Heat Damage - Retexturing | Copt Oak Road | To be scheduled
North West Leicestershire | Charley | Surface Dressing | OAKS ROAD from Oaks Road, Whitwick to jnc Abbey Road at X-rds | 2018-04-23 | Completed
Melton | Clawson, Hose and Harby | Surface Dressing | CANAL LANE from The Green to 30mph | 2018-08-07 | Completed
Melton | Clawson, Hose and Harby | Surface Dressing | CHAPEL LANE from The Green to Coal Lane | 2018-08-07 | Completed
Melton | Clawson, Hose and Harby | Surface Dressing | CLAXTON RISE from West End to end | 2018-08-07 | Completed
Melton | Clawson, Hose and Harby | Surface Dressing | COAL LANE from Harby Lane to Chapel Lane | 2018-08-07 | Completed
Melton | Clawson, Hose and Harby | Surface Dressing | DAIRY LANE from Harby Lane to The Green | 2018-08-07 | Completed
Melton | Clawson, Hose and Harby | Surface Dressing | HOME PASTURES from Chapel Lane to end | 2018-08-07 | Completed
Melton | Clawson, Hose and Harby | Surface Dressing | KINGS ROAD from jnc Sand Pit Lane to road ends | 2018-07-12 | Completed
Melton | Clawson, Hose and Harby | Surface Dressing | MILL LANE from The Sands to road end | 2018-08-06 | Completed
Melton | Clawson, Hose and Harby | Surface Dressing | SAND PIT LANE from jnc Back Lane to road end at Sand Pit Farm | 2018-08-07 | Completed
Melton | Clawson, Hose and Harby | Surface Dressing | STATHERN LANE from jnc Pinfold Place in Harby to SD joint near old railway bridge near jnc Canal Lane | 2018-05-21 | Completed
Melton | Clawson, Hose and Harby | Surface Dressing | THE GREEN from Church Close to Canal Lane | 2018-08-07 | Completed
North West Leicestershire | Coalville | Patching | bardon Rd | 2018-04-30 | Completed
North West Leicestershire | Coalville | Patching | Beveridge Lane - CAT2H | 2018-05-31 | Completed
North West Leicestershire | Coalville | Surface Dressing | FULTON DRIVE | 2018-06-22 | Completed
North West Leicestershire | Coalville | Surface Dressing | GRACEDIEU ROAD from Gracedieu Road, Whitwick to jnc Talbot Street | 2018-06-26 | Completed
North West Leicestershire | Coalville | Patching | Green Hill Road - SD | 2018-04-30 | Completed
North West Leicestershire | Coalville | Surface Dressing | KINGFISHER CLOSE | 2018-06-01 | Completed
North West Leicestershire | Coalville | Heat Damage - Retexturing | Stephensons Way | To be scheduled
North West Leicestershire | Coleorton | Heat Damage - Retexturing | The Moorlands | To be scheduled
North West Leicestershire | Congerstone / Carlton | Heat Damage - Retexturing | Bosworth Road / Congerstone Road | To be scheduled
Blaby | Cosby | Surface Dressing | CAMBRIDGE ROAD from Park Road to 30mph | 2018-06-15 | Completed
Blaby | Cosby | Surface Dressing | COVENTRY ROAD from surfacing joint near traffic lights at jnc Croft Road, Cosby to Coventry Road, Narborough | To be scheduled | Completed
Blaby | Cosby | Surface Dressing | PARK ROAD from jnc Croft Road to Cambridge Road incl bitmac speed humps | 2018-06-15 | Completed
Charnwood | Cossington | Patching | Back Lane - CAT2H | 2018-04-30 | Completed
Melton | Coston | Surface Dressing | B676 FROM COSTON ROAD TO BUCKMINSTER ROAD from start of dragons teeth near 30mph, Coston to Buckminster Road, Coston at Corner Cottage | 2018-05-22 | Completed
Melton | Coston | Heat Damage - Resurfacing | Buckminster Road | To be scheduled
Melton | Coston | Surface Dressing | BUCKMINSTER ROAD from Corner Cottage in Coston to SD joint near The Grange & 30mph | 2018-05-22 | Completed
Charnwood | Cotes | Surface Dressing | LOUGHBOROUGH ROAD from Loughborough Road, Hoton to HFS near jnc Barrow Road | 2018-05-29 | Completed
Blaby | Croft / Potters Marston | Heat Damage - Retexturing | Stanton Lane | To be scheduled
Blaby | Croft / Thurlaston | Heat Damage - Retexturing | Thurlaston Lane / Croft Lane | To be scheduled
Melton | Croxton Kerrial | Surface Dressing | GRANTHAM ROAD from SD joint near delimits at Croxton Kerrial to Lincs boundary | 2018-05-24 | Completed
Melton | Croxton Kerrial | Patching | KNIPTON ROAD | 2018-09-30 | Completed
Hinckley & Bosworth | Dadlington | Heat Damage - Resurfacing | Main Street | To be scheduled
Hinckley & Bosworth | Dadlington | Carriage Way Scheme | Shenton Lane | 2019-05-03 | 24%
Hinckley & Bosworth | Desford | Heat Damage - Retexturing | High Street | To be scheduled
Hinckley & Bosworth | Desford | Heat Damage - Retexturing | Peckleton Lane | To be scheduled
North West Leicestershire | Donisthorpe | Patching | Ashby Road | 2018-04-30 | Completed
Harborough | Dunton Bassett | Surface Dressing | BROUGHTON LANE from Dunton Road, Broughton Astley to SD joint near 30mph Dunton Bassett | 2018-06-11 | Completed
Harborough | Dunton Bassett | Junction Renewal | Dunton Basset, A4626/Coopers Lane | To be scheduled | N/A
Harborough | Dunton Bassett | MicroAsphalt | Elwells Avenue from Main Street to end | To be scheduled | Completed
Harborough | Dunton Bassett | Patching | MAIN STREET | 2018-09-30 | Completed
Hinckley & Bosworth | Earl Shilton | Heat Damage - Retexturing | Coronation Road | To be scheduled
Harborough | East Norton | Surface Dressing | CHURCH LANE from Uppingham Road to end | 2018-08-14 | Completed
Harborough | East Norton | Surface Dressing | HALLATON ROAD from Uppingham Road to end at gate at A47 | 2018-08-14 | Completed
Melton | Easthorpe | Carriage Way Scheme | Castle View Road | 2018-09-28 | 58% Complete
Melton | Eastwell / Scalford | Heat Damage - Retexturing | Scalford Road / Eastwell Road | To be scheduled
Melton | Eaton | Surface Dressing | HALL LANE from main Street to end of metalled road at gate | 2018-08-10 | Completed
Melton | EDMONDTHORPE | Patching | CORDHILL LANE | 2018-09-30 | Completed
Blaby | Elmesthorpe | Patching | STATION ROAD | 2018-05-31 | Completed
Blaby | Elmesthorpe | Surface Dressing | STATION ROAD from jnc Bostock Close near railway bridge to HFS near A47 Clickers Way | 2018-08-22 | Completed
Blaby | Enderby | Carriage Way Scheme | A5460 J21 Approach | 2018-09-21 | Completed
Blaby | Enderby | Junction Renewal | Braunstone, Osiers Bridge (top) | To be scheduled | N/A
Blaby | Enderby | Surface Dressing | CHAPEL STREET from Gumley Square to Seine Lane incl spur opposite chapel | 2018-06-19 | Completed
Blaby | Enderby | Surface Dressing | CONERY LANE from Chapel Street to Mill Hill | 2018-06-19 | Completed
Blaby | Enderby | Patching | Fosse Park | 2018-09-21 | 59% Complete
Blaby | Enderby | Surface Dressing | FOSSE PARK AVENUE from Narborough Road South roundabout to Asda roundabout | To be scheduled | Completed
Blaby | Enderby | Surface Dressing | GUMLEY SQUARE from High Street to The Nook | 2018-06-19 | Completed
Blaby | Enderby | Surface Dressing | HIGH STREET from Blaby Road to Gumley Square | 2018-06-19 | Completed
Blaby | Enderby | Surface Dressing | LEICESTER ROAD from Foxhunter Roundabout to King Edward Avenue, Narborough (southbound dual) | To be scheduled | Completed
Blaby | Enderby | Vehicle Restraint Systems | Narborough Rd South | 2018-11-14 | N/A
Blaby | Enderby | Surface Dressing | SEINE LANE from Chapel Street to near Hawgrip Nurseries | 2018-06-19 | Completed
Blaby | Enderby | Surface Dressing | THE NOOK from Gumley Square to ends | 2018-06-19 | Completed
Hinckley & Bosworth | Far Coton | Heat Damage - Surfacing / Retread | Coton Bridge Lane | To be scheduled
Hinckley & Bosworth | Far Coton | Patching | PRIORY LANE | 2018-07-31 | Completed
Harborough | Fleckney | Heat Damage - Retexturing | Arnesby Road | To be scheduled
Harborough | Fleckney | Patching | Kilby Rd | 2018-05-31 | Completed
Harborough | Foxton | Patching | Main St | 2018-05-31 | Completed
Melton | Freeby | Surface Dressing | CHURCH LANE from B676 to end of metalled road just past 30mph | 2018-08-10 | Completed
Melton | Freeby | Surface Dressing | MINOR ROAD FROM B676 SAXBY ROAD TO WYMONDHAM ROAD near the Elms Farm | 2018-08-10 | Completed
Melton | Freeby | Surface Dressing | STAPLEFORD ROAD at Lower Leesthorpe from A606 Oakham Rd to jnc Whissendine Road | 2018-06-04 | Completed
Melton | Frisby on the Wreake | Surface Dressing | ASH WAY from Oak Way to end | 2018-08-02 | Completed
Melton | Frisby on the Wreake | Surface Dressing | HALL ORCHARD LANE from main Street to end at school | 2018-08-02 | Completed
Melton | Frisby on the Wreake | Surface Dressing | LEICESTER ROAD from surfacing joint near jnc Frisby turn on Chalkpool Hill to Leicester Road, Rotherby | 2018-06-01 | Completed
Melton | Frisby on the Wreake | Surface Dressing | OAK WAY from Hall Orchard Lane to end | 2018-07-10 | Completed
Harborough | Frolesworth | Surface Dressing | FROM BROUGHTON ROAD TO LODGE FARM (Sharnford Tractors) from jnc Broughton Road to end at farm (PRIVATE WORK) | 2018-06-12 | Completed
Harborough | Gaulby / Illston on the Hill / Burton Overy | Heat Damage - Surfacing / Retread | Burton Overy Road | To be scheduled
Harborough | Gaulby Illston on the Hill | Heat Damage - Retexturing | Gaulby Lane / New Road / Gaulby Road | To be scheduled
Harborough | Gilmorton | Heat Damage - Retexturing | Kimcote Road | To be scheduled
Harborough | Gilmorton | Heat Damage - Retexturing | Lutterworth Road | To be scheduled
Blaby | Glen Parva | Safety Scheme | Glen Parva, A426 Leicester Road junction with Little Glen Road | To be scheduled | N/A
Blaby | Glen Parva | Bridge Repairs | Glen Parva, Blaby Bridge (A426) | To be scheduled | N/A
Blaby | Glen Parva | Surface Dressing | LITTLE GLEN ROAD from surfacing joint near railway bridge to jnc Leicester Road | To be scheduled | Completed
Blaby | Glenfield | Surface Dressing | ELM TREE AVENUE from Kirby Road to Park Drive incl bitmac speed humps | 2018-06-15 | Completed
Blaby | Glenfield | Surface Dressing | FAIRE ROAD from A50 Leicester Road to Glenfield Frith Drive | 2018-06-22 | Completed
Blaby | Glenfield | Surface Dressing | FAIRE ROAD SERVICE ROAD o/s shops from Faire Road to Faire Road | 2018-06-22 | Completed
Blaby | Glenfield | Surface Dressing | GLENFIELD FRITH DRIVE from Tysoe Hill to A50 Leicester Road | 2018-06-22 | Completed
Blaby | Glenfield | Surface Dressing | JUNO CLOSE from Normandy Close to end including bitmac speed humps | 2018-06-20 | Completed
Blaby | Glenfield | Surface Dressing | MEADOWCROFT CLOSE from Somerset Drive to ends | 2018-06-21 | Completed
Blaby | Glenfield | Surface Dressing | NORMANDY CLOSE from Wheatfield Close to end including bitmac speed humps | 2018-06-21 | Completed
Blaby | Glenfield | Surface Dressing | PARK DRIVE from Elm Tree Avenue to Stamford Street incl bitmac speed humps | 2018-06-15 | Completed
Blaby | Glenfield | Surface Dressing | SOMERSET DRIVE from Elm Tree Avenue to Park Drive incl bitmac speed humps | 2018-06-21 | Completed
Blaby | Glenfield | Surface Dressing | SWORD CLOSE from Normandy Close to end including bitmac speed humps | 2018-06-20 | Completed
Blaby | Glenfield | Surface Dressing | UTAH CLOSE from Wheatfield Close to end including bitmac speed humps | 2018-06-20 | Completed
Blaby | Glenfield | Surface Dressing | WHEATFIELD CLOSE from Somerset Drive to road ends including bitmac speed humps | 2018-06-21 | Completed
Harborough | Glooston | Heat Damage - Retexturing | Harborough Road | To be scheduled
Harborough | Great Glen | Heat Damage - Retexturing | Stretton Road | To be scheduled
Harborough | Great Glen | Heat Damage - Resurfacing | Stretton Road | To be scheduled
North West Leicestershire | Griffydam | Patching | Rempstone Road - SD | 2018-04-30 | Completed
North West Leicestershire | Griffydam | Heat Damage - Resurfacing | The Tentas | To be scheduled
Hinckley & Bosworth | Groby | Junction Renewal | Groby, A50/Lena Drive | To be scheduled | N/A
Harborough | Hallaton | Surface Dressing | GOADBY ROAD - dress recent surfacing from joint at ford to joint past access to Cock Abingdon Farm | 2018-08-14 | Completed
Harborough | Hallaton | Patching | HORNINGHOLD ROAD | 2018-09-30 | Completed
Harborough | Hallaton | Patching | HORNINGHOLD ROAD | 2018-09-30 | Completed
Harborough | Hallaton | Heat Damage - Resurfacing | Medbourne Road | To be scheduled
Harborough | Hallaton / Allexton | Heat Damage - Surfacing / Retread | Allexton Road / Hallaton Road | To be scheduled
Melton | Harby / Eastwell | Heat Damage - Retexturing | Waltham Lane / Waltham Road | To be scheduled
Melton | Harston | Surface Dressing | CROXTON LANE from jnc Denton Road, Harston to jnc Knipton Road, Croxton Kerrial | 2018-08-28 | Completed
Melton | Harston | Patching | DENTON LANE | 2018-09-30 | Completed
Melton | Harston | Patching | KNIPTON LANE | 2018-09-30 | Completed
Charnwood | HATHERN | Patching | DERBY ROAD (through village) | 2018-09-30 | Completed
Hinckley & Bosworth | Hinckley | Surface Dressing | ASHFORD ROAD from jnc Coventry Road to end at school | 2018-08-21 | Completed
Hinckley & Bosworth | Hinckley | Surface Dressing | BEAUMONT AVENUE from jnc Strathmore Road to jnc Coventry Road | 2018-08-21 | Completed
Hinckley & Bosworth | Hinckley | Patching | CLICKERS WAY | 2018-08-31 | Completed
Hinckley & Bosworth | Hinckley | Patching | CLICKERS WAY | 2018-08-31 | Completed
Hinckley & Bosworth | Hinckley | Surface Dressing | EASTWOODS ROAD from jnc Leicester Road to end | 2018-08-21 | Completed
Hinckley & Bosworth | Hinckley | Crossing Renewal | Hinckley, Castle Street | To be scheduled | N/A
Hinckley & Bosworth | Hinckley | Surface Dressing | LANGDALE ROAD from Sunnydale Road to jnc Brodick Road | 2018-08-21 | Completed
Hinckley & Bosworth | Hinckley | Surface Dressing | MIDDLEFIELD LANE from SD joint near jnc Factory Road to road ends | 2018-08-21 | Completed
Hinckley & Bosworth | Hinckley | Patching | NORMANDY WAY | 2018-05-31 | Completed
Hinckley & Bosworth | Hinckley | Patching | NORMANDY WAY | 2018-07-31 | Completed
Hinckley & Bosworth | Hinckley | Patching | NORMANDY WAY | 2018-08-31 | Completed
Hinckley & Bosworth | Hinckley | Patching | NORMANDY WAY/roston dr | 2018-08-31 | Completed
Hinckley & Bosworth | Hinckley | Surface Dressing | NORTHFIELD ROAD from Coventry Road to Westfield Road | 2018-08-21 | Completed
Hinckley & Bosworth | Hinckley | Surface Dressing | SUNNYDALE ROAD from jnc Coventry Road to Langdale Road | 2018-08-21 | Completed
Hinckley & Bosworth | Hinckley | Surface Dressing | TEIGN BANK ROAD from jnc Factory Road to jnc Tudor Road | 2018-08-22 | Completed
Hinckley & Bosworth | Hinckley | Surface Dressing | WESTFIELD ROAD from Northfield Road to Merevale Avenue | 2018-08-21 | Completed
Melton | Holwell | Heat Damage - Retexturing | Clawson Road | To be scheduled
Melton | Holwell | Heat Damage - Retexturing | Landyke Lane | To be scheduled
Harborough | HORNINGHOLD | Patching | HALLATON ROAD | 2018-09-30 | Completed
Harborough | HORNINGHOLD | Patching | KNOB HILL ROAD | 2018-08-31 | Completed
Charnwood | Hoton | Surface Dressing | LOUGHBOROUGH ROAD from SD joint at 30mph Hoton to Loughborough Road, Cotes | 2018-05-29 | Completed
Harborough | Hungarton | Heat Damage - Retexturing | Barley Leas | To be scheduled
Harborough | Husbands Bosworth | MicroAsphalt | Highcroft from Berridges Lane to ends | To be scheduled | Completed
Harborough | Husbands Bosworth | Patching | LEICESTER ROAD | 2018-07-31 | Completed
Harborough | Husbands Bosworth | MicroAsphalt | Wells Close from Bell Lane to end | To be scheduled | Completed
Harborough | Illston on the Hill | Surface Dressing | ASHLANDS ROAD from Main Street to Gaulby Road | 2018-07-27 | Completed
Harborough | Illston on the Hill | Surface Dressing | KIBWORTH ROAD from jnc B6047 at Three Gates to Three Gates Road, Carlton at jnc Gartree Road | 2018-06-07 | Completed
Harborough | Illston on the Hill | Surface Dressing | MAIN STREET from Ashlands Road to end | 2018-07-27 | Completed
North West Leicestershire | Isley Cum Langley | Carriage Way Scheme | A453 | 2018-12-21 | 49%
Harborough | Kibworth | Traffic Signal Investigation | Kibworth, Warwick Road | To be scheduled | N/A
Harborough | Kibworth Beauchamp | Surface Dressing | BIRDIE CLOSE from Fairway to ends | 2018-07-26 | Completed
Harborough | Kibworth Beauchamp | Surface Dressing | FAIRWAY from Springfield Crescent to Birdie Close and to Links Road | 2018-07-26 | Completed
Harborough | Kibworth Beauchamp | Surface Dressing | GRANARY CLOSE from Weir Road to end | 2018-07-25 | Completed
Harborough | Kibworth Beauchamp | Surface Dressing | GREENWAY from Springfield Crescent to end | 2018-07-25 | Completed
Harborough | Kibworth Beauchamp | Patching | HILLCREST AVENUE | 2018-07-31 | Completed
Harborough | Kibworth Beauchamp | Surface Dressing | LINKS ROAD from Springfield Crescent to New Road | 2018-07-26 | Completed
Harborough | Kibworth Beauchamp | Surface Dressing | SPRINGFIELD CLOSE from Springfield Crescent to ends | 2018-07-25 | Completed
Harborough | Kibworth Beauchamp | Surface Dressing | SPRINGFIELD CRESCENT from Weir Road to Weir Road | 2018-07-25 | Completed
Harborough | Kibworth Beauchamp | Surface Dressing | THE DRIVE from Greenway to end | 2018-07-25 | Completed
Harborough | Kibworth Beauchamp | Surface Dressing | THE PADDOCK from Greenway to Springfield Crescent | 2018-07-26 | Completed
Harborough | Kibworth Beauchamp | Surface Dressing | WENTWORTH CLOSE from Springfield Crescent to ends | 2018-07-26 | Completed
Harborough | Kibworth Harcourt | Surface Dressing | BRAYMISH CLOSE from Marriott Drive to ends | 2018-07-26 | Completed
Harborough | Kibworth Harcourt | Surface Dressing | CARLTON ROAD from Kibworth Road, Carlton Curlieu to jnc Albert Street in Kibworth Harcourt | 2018-06-08 | Completed
Harborough | Kibworth Harcourt | Surface Dressing | HARBOROUGH ROAD from SD joint near West Langton Road to SD joint near Business Park | 2018-06-11 | Completed
Harborough | Kibworth Harcourt | Surface Dressing | MARRIOTT DRIVE from New Road to ends | 2018-07-27 | Completed
Harborough | Kibworth Harcourt | Carriage Way Scheme | Marsh Drive | 2019-05-03 | 24%
Harborough | Kibworth Harcourt | Surface Dressing | MILESTONE CLOSE from Marriott Drive to ends | To be scheduled | Completed
Harborough | Kibworth Harcourt | Surface Dressing | WEST LANGTON ROAD from jnc A6 Harborough Road to West langton Road, Tur Langton | 2018-06-12 | Completed
Harborough | Kimcote | Surface Dressing | GURNEY LANE from jnc Walton Road to Kilworth Road | 2018-06-14 | Completed
Harborough | Kimcote | Surface Dressing | KILWORTH ROAD from Gurney Lane to Kilworth Road, North Kilworth | 2018-06-14 | Completed
Melton | Kirby Bellars | Surface Dressing | MAIN STREET from Leicester Road to end | 2018-08-02 | Completed
Melton | Kirby Bellars | Surface Dressing | WASHDYKE LANE from Main Street to end | 2018-08-02 | Completed
Hinckley & Bosworth | Kirkby Mallory / Brascote | Heat Damage - Retexturing | Newbold Road / Brascote Lane | To be scheduled
Harborough | Knaptoft | Patching | FROM A5199 WELFORD ROAD TO MOWSLEY LANE | 2018-07-31 | Completed
Harborough | Knaptoft | Heat Damage - Resurfacing | Welford Road | To be scheduled
Harborough | Knaptoft | Heat Damage - Resurfacing | Welford Road | To be scheduled
Melton | KNIPTON | Patching | CROXTON ROAD | 2018-09-30 | Completed
Melton | Knossington | Heat Damage - Retexturing | Owston Road | To be scheduled
Melton | Knossington and Cold Overton | Surface Dressing | THE GLEBE from Westmoor Lane to Oakham/Knossington Road | 2018-06-04 | Completed
Melton | Knossington and Cold Overton | Surface Dressing | WHISSENDINE LANE from 30mph Cold Overton to Rutland boundary at bridge past Northfield Farm | 2018-06-04 | Completed
Harborough | Launde | Heat Damage - Surfacing / Retread | Wood Lane | To be scheduled
Blaby | Leicester Forest East, | Resurfacing | Leicester Forest East, Hinckley Road A47 | To be scheduled | N/A
Harborough | LITTLE BOWDEN | Patching | BRAYBROOKE ROAD | 2018-09-30 | Completed
Melton | Little Dalby | Heat Damage - Retexturing | "From Gartree Hill to Melton Road" | To be scheduled
Harborough | Little Stretton | Surface Dressing | FROM MAIN STREET TO MANOR FARM TOP FARM THE BYRE AND CORNFIELDS | 2018-07-27 | Completed
Harborough | Little Stretton | Patching | MERE ROAD | 2018-09-30 | Completed
Harborough | Loddington | Heat Damage - Surfacing / Retread | From Loddington Road to Main Street | To be scheduled
Harborough | Loddington | Patching | Wood Lane | 2018-10-05 | 58% Complete
Melton | Long Clawson | Patching | CANAL LANE | 2018-09-30 | Completed
Melton | Long Clawson | Flood Alleviation Scheme | Long Clawson, Stand Pit Lane | To be scheduled | N/A
Melton | Long Clawson | Carriage Way Scheme | Melton Road | 2018-11-02 | 74%
Melton | Long Clawson | Heat Damage - Retexturing | Melton Road | To be scheduled
Melton | Long Clawson | Heat Damage - Resurfacing | Melton Road | To be scheduled
North West Leicestershire | Long Whatton and Diseworth | Surface Dressing | ASHBY ROAD from Rempstone Road under M1 bridge to HRA joint near farm traffic warning sign | 2018-04-24 | Completed
Charnwood | Lough | Patching | Burfield Ave | 2018-05-31 | Completed
Charnwood | Lough | Patching | Meadow Lane | 2018-05-31 | Completed
Charnwood | Loughborough | Surface Dressing | ASHBY ROAD from surfacing joint at Cumberland Road to jnc Epinal Way | 2018-05-20 | Completed
Charnwood | Loughborough | Surface Dressing | ASHLEIGH DRIVE from Forest Road to end | 2018-06-28 | Completed
Charnwood | Loughborough | Carriage Way Scheme | Belton Rd West Ext | 2018-07-27 | Completed
Charnwood | Loughborough | Patching | Belton Road 8pm | 2018-08-31 | Completed
Charnwood | Loughborough | Patching | BELVOIR DRIVE | 2018-08-31 | Completed
Charnwood | Loughborough | Surface Dressing | BYRON STREET EXTENSION from jnc Derby Road to end | 2018-04-26 | Completed
Charnwood | Loughborough | Patching | CHARTERIS CLOSE | 2018-08-31 | Completed
Charnwood | Loughborough | Patching | CHARTERIS CLOSE | 2018-08-31 | Completed
Charnwood | Loughborough | Surface Dressing | CLARENCE STREET from Nottingham Road to Meadow Lane | 2018-05-20 | Completed
Charnwood | Loughborough | Surface Dressing | COBDEN STREET from Freehold Street to end | 2018-06-28 | Completed
Charnwood | Loughborough | Surface Dressing | COLGROVE ROAD from Wallace Road to Beacon Road | 2018-06-28 | Completed
Charnwood | Loughborough | Patching | Cordell Road - CAT2H | 2018-04-30 | Completed
Charnwood | Loughborough | Patching | DERBY ROAD (B&M retail) | 2018-08-31 | Completed
Charnwood | Loughborough | Patching | Derby Road (Bishop Meadow) - CAT2H | 2018-05-31 | Completed
Charnwood | Loughborough | Patching | DERBY ROAD (regent st) | 2018-08-31 | Completed
Charnwood | Loughborough | Surface Dressing | DUKE STREET from Clarence Street to ends | 2018-06-29 | Completed
Charnwood | Loughborough | Patching | Empress Road - CAT2H | 2018-04-30 | Completed
Charnwood | Loughborough | Patching | Epinal Way - CAT2H | 2018-05-31 | Completed
Charnwood | Loughborough | Surface Dressing | FACTORY STREET from Moira Street to Leicester Road | 2018-07-02 | Completed
Charnwood | Loughborough | Patching | forest rd | 2018-06-30 | Completed
Charnwood | Loughborough | Surface Dressing | FREEHOLD STREET from Queens Road to end | 2018-07-02 | Completed
Charnwood | Loughborough | Patching | Gallico Close | 2018-08-31 | Completed
Charnwood | Loughborough | Patching | Granby Street - CAT2H | 2018-04-30 | Completed
Charnwood | Loughborough | Patching | Great Central Road - CAT2H | 2018-04-30 | Completed
Charnwood | Loughborough | Surface Dressing | GREGORY STREET from Moira Street to Leicester Road | 2018-07-02 | Completed
Charnwood | Loughborough | MicroAsphalt | Harlech Close from Milton Street to end | To be scheduled | Completed
Charnwood | Loughborough | Patching | Jubille Drive - CAT2H | 2018-04-30 | Completed
Charnwood | Loughborough | Patching | LEOPOLD STREET | 2018-08-31 | Completed
Charnwood | Loughborough | Surface Dressing | LIMETREE GROVE from Trinity Street to blocks | 2018-06-29 | Completed
Charnwood | Loughborough | Junction Renewal | Loughborough, A6 (Bishops Meadow) | To be scheduled | N/A
Charnwood | Loughborough | Safety Scheme | Loughborough, A6 Loughborough Road junction with Beeches Road | To be scheduled | N/A
Charnwood | Loughborough | Junction Renewal | Loughborough, Belton Road / Jubilee Drive | To be scheduled | N/A
Charnwood | Loughborough | Safety Scheme | Loughborough, Leicester Road junction with Shelthorpe Road | To be scheduled | N/A
Charnwood | Loughborough | Bridge Repairs | Loughborough, Shakespeare Street | To be scheduled | N/A
Charnwood | Loughborough | Flood Alleviation Scheme | Loughborough, Windsor Road | To be scheduled | N/A
Charnwood | Loughborough | Surface Dressing | MEADOW LANE from Belton Road to Clarence Street | To be scheduled | Completed
Charnwood | Loughborough | Surface Dressing | MOIRA STREET from King Street to Barrow Street including bitmac speed hump | 2018-06-29 | Completed
Charnwood | Loughborough | Surface Dressing | MOUNTFIELDS DRIVE from Forest Road to end | 2018-06-28 | Completed
Charnwood | Loughborough | Surface Dressing | NOTTINGHAM ROAD from Morley Street to The Coneries | 2018-05-20 | Completed
Charnwood | Loughborough | MicroAsphalt | Oakham Close from HRA joint near jnc Rockingham Road to end | To be scheduled | Completed
Charnwood | Loughborough | Patching | PAGET STREET | 2018-08-31 | Completed
Charnwood | Loughborough | Surface Dressing | PEEL DRIVE from Freehold Street to end | 2018-07-02 | Completed
Charnwood | Loughborough | Surface Dressing | RADMOOR ROAD from Ashby Road to end | 2018-07-02 | Completed
Charnwood | Loughborough | Surface Dressing | RUSSELL STREET from Moor Lane to end of highway | 2018-06-29 | Completed
Charnwood | Loughborough | Surface Dressing | RUTLAND STREET from Moor Lane to Wellington Street | 2018-07-02 | Completed
Charnwood | Loughborough | Patching | Schofield Road | 2018-08-31 | Completed
Charnwood | Loughborough | Surface Dressing | SCHOOL STREET from Cobden Street to end | 2018-07-02 | Completed
Charnwood | Loughborough | Surface Dressing | SELBOURNE STREET from Russell Street to Wharncliffe Road | 2018-06-29 | Completed
Charnwood | Loughborough | Patching | Shelthorpe Road - CAT2H | 2018-04-30 | Completed
Charnwood | Loughborough | MicroAsphalt | Stewart Drive (cul-de-sac at end between house nos 16 - 34) from SD joint to end | To be scheduled | Completed
Charnwood | Loughborough | Surface Dressing | THE CONERIES from Nottingham Road to near jnc Sparrow Hill | 2018-05-20 | Completed
Charnwood | Loughborough | Patching | Thorpe Hill | 2018-08-31 | Completed
Charnwood | Loughborough | Surface Dressing | TRINITY STREET from Moira Street across Wellington Street to Moor Lane | 2018-07-03 | Completed
Charnwood | Loughborough | Surface Dressing | WALLACE ROAD from Forest Road to Beacon Road | 2018-06-28 | Completed
Charnwood | Loughborough | MicroAsphalt | Waterside Close from jnc Meadow Lane to ends | To be scheduled | Completed
Charnwood | Loughborough | Surface Dressing | WELLINGTON STREET from Rutland Street across Trinity Street to end | 2018-06-29 | Completed
Harborough | LOWESBY | Patching | PARK ROAD | 2018-09-30 | Completed
Harborough | Lubenham | Footbridge Replacement | Lubenham, Scoborugh Road | To be scheduled | N/A
Harborough | Lutterworth | MicroAsphalt | Cherrytree Avenue from Greenacres Drive to end | To be scheduled | Completed
Harborough | Lutterworth | Heat Damage - Retexturing | Maxwell Way | To be scheduled
Harborough | Lutterworth | Surface Dressing | NEW STREET from Bitteswell Road to end near Spencer Road | 2018-08-16 | Completed
Harborough | Lutterworth | Patching | SPENCER ROAD - SD | 2018-04-30 | Completed
Harborough | Lutterworth | Surface Dressing | SPENCER ROAD from New Street to Crescent Road | 2018-08-16 | Completed
Harborough | Lutterworth | MicroAsphalt | Walker-Manor Court from Market Street to ends | To be scheduled | Completed
Harborough | Market Harborough | Surface Dressing | ALBANY ROAD from Connaught Road to end | 2018-07-31 | Completed
Harborough | Market Harborough | MicroAsphalt | Arden Close from Arden Way to end | To be scheduled | Completed
Harborough | Market Harborough | MicroAsphalt | Arden Way from Great Bowden Road to Nunneley Way | To be scheduled | Completed
Harborough | Market Harborough | Surface Dressing | ASHLEY WAY from jnc Rockingham Road to jnc Kettering Road | 2018-07-30 | Completed
Harborough | Market Harborough | Surface Dressing | AUDLEY CLOSE from Sandringham Way to Ashley Way incl bitmac speed humps | 2018-07-31 | Completed
Harborough | Market Harborough | Surface Dressing | BALMORAL CLOSE from Petworth Drive to end | 2018-07-27 | Completed
Harborough | Market Harborough | Surface Dressing | BAMBURGH CLOSE from Chatsworth Drive to end | 2018-07-30 | Completed
Harborough | Market Harborough | Patching | BATH STREET | 2018-09-30 | Completed
Harborough | Market Harborough | Surface Dressing | BURGHLEY CLOSE from Chatsworth Drive to end | 2018-07-30 | Completed
Harborough | Market Harborough | Surface Dressing | BURNMILL ROAD from SD joint near 30mph to jnc Main Street, Gt Bowden | 2018-08-15 | Completed
Harborough | Market Harborough | Surface Dressing | CHATSWORTH DRIVE from Sandringham Way to SD joint o/s no.43 | 2018-07-30 | Completed
Harborough | Market Harborough | Heat Damage - Retexturing | Cromwell Crescent | To be scheduled
Harborough | Market Harborough | Surface Dressing | DEENE CLOSE from Chatsworth Drive to end | 2018-07-30 | Completed
Harborough | Market Harborough | Surface Dressing | FERNFIELD CLOSE from rndbt at Meadowdale Road to ends | 2018-07-27 | Completed
Harborough | Market Harborough | Surface Dressing | FLAXLAND CLOSE from Audley Close to end | 2018-07-30 | Completed
Harborough | Market Harborough | Surface Dressing | GILBERT CLOSE from Audley Close to blocks | 2018-07-30 | Completed
Harborough | Market Harborough | Surface Dressing | HAGLEY CLOSE from Chatsworth Drive to ends and blocks | 2018-07-31 | Completed
Harborough | Market Harborough | MicroAsphalt | Harrod Drive from speed table at jnc Great Bowden Road to end | To be scheduled | Completed
Harborough | Market Harborough | Surface Dressing | HILLSIDE ROAD from The Headlands to The Broadway | 2018-07-31 | Completed
Harborough | Market Harborough | Patching | HILLSIDE ROAD- SD | 2018-04-30 | Completed
Harborough | Market Harborough | MicroAsphalt | Huntingdon Gardens from Lenthall Square to Balfour Gardens | To be scheduled | Completed
Harborough | Market Harborough | Surface Dressing | LONGLEAT CLOSE from Sandringham Way to end | 2018-07-31 | Completed
Harborough | Market Harborough | Surface Dressing | PETWORTH DRIVE from Sandringham Way to end | 2018-07-27 | Completed
Harborough | Market Harborough | Surface Dressing | REDLICH CLOSE from Petworth Drive to end | 2018-08-01 | Completed
Harborough | Market Harborough | Surface Dressing | ROSEMOOR CLOSE from Chatsworth Drive to end | 2018-08-01 | Completed
Harborough | Market Harborough | MicroAsphalt | Rowan Avenue - both sections from Cromwell Crescent to Rupert Road | To be scheduled | Completed
Harborough | Market Harborough | Surface Dressing | SANDRINGHAM WAY from Kettering Road to ends | 2018-08-01 | Completed
Harborough | Market Harborough | Patching | springfield st | 2018-06-30 | Completed
Harborough | Market Harborough | Surface Dressing | STANWAY CLOSE from Chatsworth Drive to end | 2018-08-01 | Completed
Harborough | Market Harborough | Carriage Way Scheme | Welland Park Road | 2018-10-05 | Completed
Harborough | Market Harborough | Patching | Welland Park Road | 2018-06-30 | Completed
Harborough | Market Harborough | Surface Dressing | WOODGATE CLOSE from Audley Close to blocks | 2018-08-01 | Completed
Hinckley & Bosworth | Markfield | Surfacing Scheme | A511 Shaw Lane | 2018-11-23 | 83%
Hinckley & Bosworth | Markfield | Heat Damage - Retexturing | Forest Road | To be scheduled
Hinckley & Bosworth | Markfield | Surface Dressing | LAUNDE ROAD from rndbt at jnc A50 to Ratby Lane, Field Head | 2018-08-24 | Completed
Hinckley & Bosworth | Markfield | Heat Damage - Resurfacing | London Road | To be scheduled
Hinckley & Bosworth | Markfield | Bridge Repairs | Markfield, A50 | On Site | On Site
Hinckley & Bosworth | Markfield | Surface Dressing | RATBY LANE from Ratby Lane, Field Head to jnc London Road | 2018-08-24 | Completed
Hinckley & Bosworth | Markfield | Surface Dressing | SLIP ROAD FROM A50 NORTHBOUND C/W TO WHITWICK ROAD | To be scheduled | Completed
Hinckley & Bosworth | Markfield | Surface Dressing | SLIP ROAD FROM WHITWICK ROAD TO A50 NORTHBOUND C/W (incl both spurs) | To be scheduled | Completed
Hinckley & Bosworth | Markfield / Ulverscroft | Heat Damage - Retexturing | Priory Lane | To be scheduled
North West Leicestershire | Measham | Patching | Gallows Lane SD | 2018-05-31 | Completed
North West Leicestershire | Measham | Surface Dressing | GALLOWS LANE from Measham Road, Snarestone to just past jnc Bosworth Road X-rds | 2018-05-21 | Completed
North West Leicestershire | Measham | Patching | Leciester Road | 2018-04-30 | Completed
Harborough | Medbourne | Heat Damage - Retexturing | Drayton Road | To be scheduled
Harborough | Medbourne | Heat Damage - Resurfacing | Drayton Road | To be scheduled
Harborough | Medbourne | Patching | SLAWSTON ROAD | 2018-09-30 | Completed
Harborough | Medbourne | Patching | SLAWSTON ROAD covered by 390400 | 2018-09-30 | Completed
Harborough | Medbourne | Patching | SLAWSTON ROAD covered by 390400 | 2018-09-30 | Completed
Melton | Melton | Patching | Saxby Road - CAT2H | 2018-05-31 | Completed
Melton | Melton Mowbray | MicroAsphalt | Albert Street from Victoria Street to Craven Street | To be scheduled | Completed
Melton | Melton Mowbray | Surface Dressing | BENTLEY STREET from Sage Cross Street to bend at Greenslade | 2018-08-06 | Completed
Melton | Melton Mowbray | Surface Dressing | BRIGHTSIDE AVENUE from Sherwood Drive to Dorothy Avenue | 2018-08-03 | Completed
Melton | Melton Mowbray | Surface Dressing | CHAPEL STREET from surfacing joint near jnc Norman Way to surfacing joint near car park | 2018-08-06 | Completed
Melton | Melton Mowbray | Surface Dressing | EAST AVENUE from Sysonby Street to Douglas Jane Close | 2018-08-03 | Completed
Melton | Melton Mowbray | Surface Dressing | ELMHURST AVENUE from Welby Lane to end | 2018-08-03 | Completed
Melton | Melton Mowbray | Heat Damage - Retexturing | Leicester Road | To be scheduled
Melton | Melton Mowbray | Surface Dressing | MORLEY CLOSE from Sysonby Street to end | 2018-08-03 | Completed
Melton | Melton Mowbray | Surface Dressing | RICHARD CLOSE from Saxby Road to blocks | 2018-08-03 | Completed
Melton | Melton Mowbray | Surface Dressing | SAXBY ROAD from 30mph to Saxby Road, Brentingby at Brentingby Lodge | 2018-06-05 | Completed
Melton | Melton Mowbray | Surface Dressing | ST BARTHOLMEWS WAY from jnc Welby Lane to road end at entrance to business park | 2018-06-01 | Completed
Melton | Melton Mowbray | Carriage Way Scheme | St Bartholomew's Way | 2019-04-12 | 46%
Melton | Melton Mowbray | Surface Dressing | SYSONBY STREET from Staveley Road to Welby Lane | 2018-08-03 | Completed
Charnwood | Mountsorrel | Patching | LEICESTER ROAD | 2018-07-31 | Completed
Charnwood | Mountsorrel | Patching | Lough Road (Granite Way) | 2018-05-31 | Completed
Charnwood | Mountsorrel | Patching | loughborough rd | 2018-05-31 | Completed
Harborough | Mowsley | Heat Damage - Retexturing | Laughton Road | To be scheduled
Hinckley & Bosworth | Nailstone | Heat Damage - Resurfacing | Main Street / Bagworth Road | To be scheduled
Blaby | Narborough | Surface Dressing | COVENTRY ROAD from Coventry Road, Cosby to old railway bridge after 40mph | To be scheduled | Completed
Blaby | Narborough | Patching | FOREST ROAD | 2018-07-31 | Completed
Blaby | Narborough | Surface Dressing | KING EDWARD AVENUE from Leicester Road, Enderby to rndbt at jnc Desford Road (southbound dual only incl central link roads to and from Carlton Park) | To be scheduled | Completed
Melton | Nether Broughton | Surface Dressing | CLAWSON LANE from Church End at 30mph to SD joint o/s Bridge Farm | 2018-08-08 | Completed
Charnwood | Newtown Linford | Surface Dressing | JOE MOORES LANE from Roecliffe Crossroads to jnc Benscliffe Road | 2018-04-26 | Completed
Charnwood | Newtown Linford | Surface Dressing | MAIN STREET from jnc Markfield Lane to Sharply Hill | 2018-04-27 | Completed
Charnwood | Newtown Linford | Surface Dressing | MARKFIELD LANE from jnc Main Street to jnc A50 at Field Head | 2018-04-27 | Completed
Charnwood | Newtown Linford | Surface Dressing | SHARPLY HILL from Main Street to jnc Benscliffe Road | 2018-04-27 | Completed
Charnwood | Newtown Linford | Surface Dressing | SLIP ROAD FROM A50 TO WHITWICK ROAD | To be scheduled | Completed
Charnwood | Normanton | Patching | MAIN STREET | 2018-07-31 | Completed
Charnwood | Normanton | Patching | NORMANTON LANE | 2018-07-31 | Completed
Harborough | North Kilworth | Surface Dressing | KILWORTH ROAD from Kilworth Road, Kimcote to jnc A4304 Lutterworth Road | 2018-06-14 | Completed
Harborough | Noseley | Patching | ILLSTON ROAD | 2018-07-31 | Completed
Harborough | Noseley | Patching | THREE GATES ROAD | 2018-07-31 | Completed
Oadby and Wigston | Oadby | Carriage Way Scheme | Howdon Road | 2018-09-27 | Completed
Oadby and Wigston | Oadby | Carriage Way Scheme | Ridge Way | 2018-09-20 | Completed
Oadby and Wigston | Oadby and Wigston | Surface Dressing | BRIAR WALK from Rosemead Drive to SD joint at Briar Meads | 2018-08-17 | Completed
Oadby and Wigston | Oadby and Wigston | Surface Dressing | CHESHIRE DRIVE from Gloucester Crescent to Dorset Avenue | 2018-08-17 | Completed
Oadby and Wigston | Oadby and Wigston | Surface Dressing | CRETE AVENUE from Saffron Road to highway boundary just past Moores Close | 2018-08-17 | Completed
Oadby and Wigston | Oadby and Wigston | Surface Dressing | CUMBERLAND ROAD from Gloucester Crescent to Dorset Avenue | 2018-08-17 | Completed
Oadby and Wigston | Oadby and Wigston | Surface Dressing | ESSEX ROAD from Sussex Road to Norfolk Road | 2018-08-17 | Completed
Oadby and Wigston | Oadby and Wigston | Surface Dressing | GAULBY LANE from jnc Gartree Road to Gaulby Lane, Stoughton | 2018-06-13 | Completed
Oadby and Wigston | Oadby and Wigston | Surface Dressing | HINDOOSTAN AVENUE from Crete Avenue to highway boundary o/s The Cottage | 2018-08-17 | Completed
Oadby and Wigston | Oadby and Wigston | Surface Dressing | MOORES CLOSE from Crete Avenue to end | 2018-08-17 | Completed
Oadby and Wigston | Oadby and Wigston | Surface Dressing | NORFOLK ROAD from Northumberland Road to Cheshire Drive | 2018-08-17 | Completed
Oadby and Wigston | Oadby and Wigston | Surface Dressing | SUFFOLK CLOSE from Cheshire Drive to ends | 2018-08-17 | Completed
Oadby and Wigston | Oadby and Wigston | Surface Dressing | SUSSEX ROAD from Northumberland Road to Cheshire Drive | 2018-08-20 | Completed
Oadby and Wigston | Oadby and Wigston | Surface Dressing | NEWTON LANE from new surfacing joint near dvpt to SD joint at Harborough district bdy | 2018-08-16 | Completed
Oadby and Wigston | Oadby and Wigston | Surface Dressing | ROSEMEAD DRIVE | 2018-08-20 | Completed
Oadby and Wigston | Oadby and Wigston | Surface Dressing | UPLANDS ROAD from near jnc A6 to no.133 just past jnc Dove Rise | 2018-06-12 | Completed
Melton | Old Dalby | Surface Dressing | LONGCLIFFE HILL from Main Street to Nottingham Lane | 2018-08-09 | Completed
Melton | Old Dalby | Heat Damage - Retexturing | Nottinghaam lane | To be scheduled
Melton | Old Dalby | Surface Dressing | NOTTINGHAM LANE from Lawn Lane to SD joint approx 100m past jnc Longcliffe Hill | 2018-08-09 | Completed
Melton | Old Dalby | Surface Dressing | SIX HILLS LANE from A6006 Shoby X-rds to SD joint near jnc Lawn Lane | 2018-05-21 | Completed
Hinckley & Bosworth | Orton on the Hill | Bridge Replacement | Orton on the Hill, Sheepy Lane | To be scheduled | N/A
Hinckley & Bosworth | Orton on the Hill | Patching | THE GREEN - SD | 2018-04-30 | Completed
North West Leicestershire | Osgathorpe | Surface Dressing | ASHBY ROAD from SD joint near 40mph Osgathorpe to jnc Dodgeford Lane | 2018-04-24 | Completed
Harborough | Owston | Heat Damage - Surfacing / Retread | Washdyke Road | To be scheduled
North West Leicestershire | Packington | Heat Damage - Resurfacing | Coleorton Lane | To be scheduled
Charnwood | Prestwold | Vehicle Restraint Systems | Barrow Road | 2018-11-14 | N/A
Charnwood | Prestwold | Heat Damage - Retexturing | Loughborough Road / Barrow Road | To be scheduled
Harborough | Primethorpe | MicroAsphalt | Main Street (part) from speed table near jnc Orchard Road to end at turning head | To be scheduled | Completed
Charnwood | Queniborough | Patching | south croxton rd | 2018-05-31 | Completed
Charnwood | Quorndon | Surface Dressing | ALEXANDER ROAD from Farley Way to end | 2018-06-08 | Completed
Charnwood | Quorndon | Heat Damage - Retexturing | Chaveney Road | To be scheduled
Charnwood | Quorndon | Surface Dressing | DEXTER CLOSE from Alexander Road to end | 2018-06-08 | Completed
Charnwood | Quorndon | Heat Damage - Retexturing | Meeting Street | To be scheduled
Charnwood | Quorndon | Surface Dressing | PARKERS FIELDS from Alexander Road to end | 2018-06-08 | Completed
Charnwood | Quorndon | Bridge Repairs | Quorn, Barrow Road | To be scheduled | N/A
Charnwood | Quorndon | Surface Dressing | STIRLING CLOSE from Alexander Road to end | 2018-06-08 | Completed
Charnwood | Quorndon | Surface Dressing | TURNER CLOSE from Alexander Road to end | 2018-06-08 | Completed
Charnwood | Quorndon | Heat Damage - Retexturing | Woodhouse Road | To be scheduled
Hinckley & Bosworth | Raby | Heat Damage - Retexturing | Markfield Road | To be scheduled
Hinckley & Bosworth | Ratby | Surface Dressing | BERRYS LANE from Church Lane to Main Street | 2018-08-23 | Completed
Hinckley & Bosworth | Ratby | Surface Dressing | CHAPEL LANE from Church Lane to Station Road | 2018-08-23 | Completed
Hinckley & Bosworth | Ratby | Surface Dressing | CHURCH LANE from Main Street to Berrys Lane | 2018-08-23 | Completed
Hinckley & Bosworth | Ratby | Heat Damage - Retexturing | Desford Lane | To be scheduled
Hinckley & Bosworth | Ratby | Heat Damage - Resurfacing | Markfield Road | To be scheduled
North West Leicestershire | Ravenstone | Patching | RAVENSLEA - SD | 2018-04-30 | Completed
North West Leicestershire | Ravenstone with Snibstone | Surface Dressing | RAVENSLEA all sections from Leicester Road | 2018-06-25 | Completed
Melton | Redmile | Patching | BARKESTONE LANE | 2018-09-30 | Completed
Melton | Redmile | Patching | BELVOIR ROAD | 2018-09-30 | Completed
Melton | Redmile | Surface Dressing | LONG LANE - two patches between Redmile crossroads and bend at end of straight section | 2018-08-08 | Completed
Melton | Redmile | Patching | SUTTON ROAD | 2018-09-30 | Completed
Melton | Rotherby | Surface Dressing | LEICESTER ROAD from Leicester Road, Frisby on the Wreake to surfacing joint before jnc Rotherby Top Road | 2018-06-01 | Completed
Charnwood | Rothley | Flood Alleviation Scheme | Rothley, Welsic Lane | To be scheduled | N/A
Melton | Saltby / Sproxton | Heat Damage - Retexturing | Sproxton Road / Saltby Road | To be scheduled
Blaby | Sapcote | Patching | Layby off B4114 | 2018-06-30 | Completed
Harborough | SCRAPTOFT | Patching | KEYHAM LANE EAST | 2018-09-30 | Completed
Charnwood | Seagrave | Surface Dressing | BERRYCOTT LANE from jnc King Street to 30mph | 2018-07-31 | Completed
Charnwood | Seagrave | Surface Dressing | CHURCH STREET from Swan Street to King Street | 2018-07-31 | Completed
Charnwood | Seagrave | Surface Dressing | GREEN LANE CLOSE from Green Lane to end | 2018-07-31 | Completed
Charnwood | Seagrave | Surface Dressing | GREEN LANE from jnc Swan Street to end of highway | 2018-08-01 | Completed
Charnwood | Seagrave | Surface Dressing | KING STREET from Green Lane to Park Hill Lane | 2018-07-31 | Completed
Charnwood | Seagrave | Surface Dressing | MUCKLE GATE LANE from jnc Green Lane to end of metalled road | 2018-08-01 | Completed
Charnwood | Seagrave | Surface Dressing | POND STREET from Swan Street to end | 2018-08-01 | Completed
Charnwood | Seagrave | Surface Dressing | THE BANKS from King Street to end of metalled road | 2018-08-01 | Completed
Charnwood | Seagrave | Surface Dressing | THE ORCHARD from King Street to end | 2018-08-01 | Completed
Melton | SEWSTERN | Patching | SCHOOL LANE | 2018-08-31 | Completed
Melton | SEWSTERN | Patching | THE DRIFT | 2018-08-31 | Completed
Hinckley & Bosworth | Shackerstone | Surface Dressing | BARTON ROAD from Newton Lane, Odstone to Odstone Road, Barton in the Beans at culvert | 2018-05-17 | Completed
Hinckley & Bosworth | Shackerstone | Surface Dressing | ODSTONE ROAD from Newton Lane, Odstone at culvert to surfacing joint approx 200m beyond culvert | 2018-05-17 | Completed
Harborough | Shearsby | Patching | BRUNTINGTHORPE ROAD | 2018-07-31 | Completed
Harborough | Shearsby | Heat Damage - Retexturing | Fleckney Road | To be scheduled
Hinckley & Bosworth | Sheepy | Patching | ORTON LANE - SD | 2018-04-30 | Completed
Hinckley & Bosworth | Sheepy | Surface Dressing | ORTON LANE from Sheepy Lane, Orton to jnc B4116 Twycross Road at The Cross Hands | 2018-05-17 | Completed
Hinckley & Bosworth | Sheepy | Heat Damage - Surfacing / Retread | Tinsel Lane | To be scheduled
Hinckley & Bosworth | Sheepy | Heat Damage - Surfacing / Retread | Tinsel Lane | To be scheduled
Charnwood | Shepshed | Vehicle Restraint Systems | Ashby Road West | 2018-10-19 | 24% Complete
Charnwood | Shepshed | Heat Damage - Retexturing | Leicester Road | To be scheduled
Charnwood | Sileby | Patching | COSSINGTON ROAD | 2018-07-31 | Completed
Charnwood | Sileby | Patching | COSSINGTON ROAD | 2018-07-31 | Completed
Harborough | Skeffington | Carriage Way Scheme | A47 Uppingham Road | 2019-04-26 | 46%
Harborough | Skeffington | Surface Dressing | FROM A47 UPPINGHAM ROAD TO MAIN STREET from jnc Rolleston Road to gate at delimits | 2018-08-14 | Completed
Harborough | Skeffington | Surface Dressing | FROM MAIN STREET TO END from Main Street to road end | 2018-08-14 | Completed
Harborough | Skeffington | Surface Dressing | MAIN STREET from A47 to jnc Rolleston Road | 2018-08-14 | Completed
Harborough | Skeffington | Surface Dressing | ROLLESTON ROAD from Main Street to 30mph | 2018-08-14 | Completed
Harborough | Skeffington | Surface Dressing | TILTON ROAD from Tilton Road, Billesdon to jnc A47 | 2018-06-06 | Completed
North West Leicestershire | Snarestone | Patching | measham rd | 2018-05-31 | Completed
North West Leicestershire | Snarestone | Surface Dressing | MEASHAM ROAD from SD joint near jnc Appleby Lane to Gallows Lane, Measham | 2018-05-21 | Completed
North West Leicestershire | Snarestone | Heat Damage - Retexturing | Twycross Road | To be scheduled
Melton | Somerby | Carriage Way Scheme | Newbold Lane | 2018-09-21 | Completed
Melton | Sproxton | Heat Damage - Surfacing / Retread | "From Buckminster Road to B676" | To be scheduled
Hinckley & Bosworth | STANTON UNDER BARDON | Patching | MAIN STREET | 2018-09-30 | Completed
Hinckley & Bosworth | Stoke Golding | Patching | HIGHAM LANE | 2018-07-31 | Completed
Blaby | Stoney Stanton | Carriage Way Scheme | Hinckley Road | 2018-09-14 | Completed
Harborough | Stoughton | Surface Dressing | CHURCH LANE from jnc Gaulby Lane to first speed hump on Thurnby Lane incl dress speed humps | 2018-08-20 | Completed
Harborough | Stoughton | Surface Dressing | GAULBY LANE from jnc Church Lane to Gaulby Lane, Oadby | 2018-06-13 | Completed
Hinckley & Bosworth | Sutton Cheney | Heat Damage - Resurfacing | Main Street | To be scheduled
North West Leicestershire | Swannington | Heat Damage - Resurfacing | Church Hill | To be scheduled
North West Leicestershire | Swannington | Heat Damage - Retexturing | Church Hill / Talbot Lane | To be scheduled
Harborough | Swinford | Surface Dressing | CHAPEL STREET from Rugby Road to North Street | 2018-08-16 | Completed
Harborough | Swinford | Patching | LUTTERWORTH ROAD - SD | 2018-04-30 | Completed
Harborough | Swinford | Surface Dressing | LUTTERWORTH ROAD from 30mph to Swinford Corner | 2018-06-13 | Completed
Charnwood | Swithland | Heat Damage - Retexturing | Leicester Lane | To be scheduled
Charnwood | Swithland | Heat Damage - Retexturing | Main Street | To be scheduled
Charnwood | Swithland | Flood Alleviation Scheme | Swithland, Main Street | To be scheduled | N/A
Charnwood | Syston | Carriage Way Scheme | A607 | 2018-07-19 | Completed
Charnwood | Syston | Patching | BARKBY ROAD | 2018-08-31 | Completed
Charnwood | Syston | Patching | COLLEGE ROAD | 2018-08-31 | Completed
Charnwood | Syston | Patching | East Avenue | 2018-05-31 | Completed
Charnwood | Syston | Patching | FOSSE WAY | 2018-09-30 | Completed
Charnwood | Syston | Patching | Melton road | 2018-06-30 | Completed
Charnwood | Syston | Patching | melton road | 2018-06-30 | Completed
Charnwood | Syston | Patching | Millstone Lane | 2018-05-31 | Completed
Charnwood | Syston | Patching | St Peters Court | 2018-05-31 | Completed
Charnwood | Syston | Patching | WANLIP ROAD | 2018-08-31 | Completed
Charnwood | Syston | Patching | WANLIP ROAD | 2018-08-31 | Completed
Harborough | Theddingworth | Patching | GUMLEY ROAD | 2018-07-31 | Completed
Hinckley & Bosworth | Thornton | Heat Damage - Retexturing | Bagworth Lane | To be scheduled
Hinckley & Bosworth | Thornton | Patching | FROM MARKFIELD LANE TO RESERVOIR ROAD | 2018-07-31 | Completed
Hinckley & Bosworth | Thornton | Heat Damage - Retexturing | Main Street | To be scheduled
Hinckley & Bosworth | Thornton / Stanton Under Bardon / Markfield | Heat Damage - Retexturing | Markfield Lane / Broad Lane / Grassy Lane | To be scheduled
Harborough | Thorpe Langton | Surface Dressing | BACK LANE from Main Street to end of metalled road at pub car park | 2018-07-25 | Completed
Harborough | Thorpe Langton | Heat Damage - Retexturing | Bowden Road | To be scheduled
Harborough | Thorpe Langton | Surface Dressing | CHURCH LANE from Main Street to end | 2018-07-25 | Completed
Harborough | Thorpe Langton | Heat Damage - Retexturing | Welham Road / Main Street | To be scheduled
Charnwood | Thurmaston | Surface Dressing | BEVERLEY CLOSE from Churchill Road to end | 2018-07-04 | Completed
Charnwood | Thurmaston | Surface Dressing | CHARNWOOD AVENUE from Sandiacre Drive to Highway Road | 2018-07-04 | Completed
Charnwood | Thurmaston | Surface Dressing | CHECKLAND ROAD from Newark Road to Sandiacre Drive | 2018-07-04 | Completed
Charnwood | Thurmaston | Surface Dressing | CHURCH HILL ROAD from Colby Drive to Wayside Drive | 2018-06-08 | Completed
Charnwood | Thurmaston | Surface Dressing | SANDIACRE DRIVE from Beacon Avenue to Red Hill Lane | 2018-07-04 | Completed
Charnwood | Thurmaston | Surface Dressing | SILVERDALE DRIVE from Humberstone Lane to Churchill Road | 2018-07-05 | Completed
Harborough | Tilton | Heat Damage - Surfacing / Retread | Hyde Lodge Road | To be scheduled
Harborough | Tilton | Heat Damage - Surfacing / Retread | Launde Road | To be scheduled
Harborough | Tilton | Surface Dressing | LEICESTER ROAD from 30mph Tilton to Tilton Road, Billesdon | 2018-06-06 | Completed
Harborough | Tilton | Surface Dressing | MELTON ROAD - on Tilton Hill between Tilton village and Marefield turn - dress failed section | 2018-06-06 | Completed
Harborough | Tilton | Surface Dressing | MELTON ROAD from 30mph to Leicester Rd | 2018-06-06 | Completed
Harborough | Tur Langton | Surface Dressing | WEST LANGTON ROAD from West Langton Road, Kibworth to West Langton Road, West Langton | 2018-06-11 | Completed
Hinckley & Bosworth | Twycross | Patching | A44 Burton Road - CAT2H | 2018-05-31 | Completed
Hinckley & Bosworth | Twycross | Heat Damage - Retexturing | Burton Road | To be scheduled
Hinckley & Bosworth | Twycross | Surface Dressing | SHEEPY LANE from The Green to Orton Lane, Sheepy | 2018-05-17 | Completed
Hinckley & Bosworth | Twycross | Surface Dressing | THE GREEN from joint at jnc Warton Lane and jnc Orton Ln to Sheepy Lane | 2018-05-17 | Completed
Charnwood | Ulverscroft | Safety Scheme | Ulverscroft, Shepshed Road junction with Beacon Road | To be scheduled | N/A
Charnwood | Ulverscroft / Charley | Heat Damage - Retexturing | Beacon Road | To be scheduled
Melton | Waltham | Surface Dressing | GRANTHAM ROAD from Melton Road at jnc Mere Road to past jnc Station Road | 2018-06-01 | Completed
Melton | Waltham | Surface Dressing | HIGH STREET from jnc A607 Melton Road to SD joint near Church Street | 2018-08-10 | Completed
Melton | Waltham | Surface Dressing | LAG LANE from jnc A607 Waltham Road to jnc B676 Saxby Road | 2018-08-10 | Completed
Melton | Waltham | Surface Dressing | MINOR ROAD FROM FREEBY LANE TO END at back of Waltham Lodge & Mars offices | 2018-08-10 | Completed
Melton | Waltham on the wolds | Patching | FREEBY LANE | 2018-08-31 | Completed
Hinckley & Bosworth | Wellsborough | Heat Damage - Surfacing / Retread | Bosworth Road | To be scheduled
Harborough | West Langton | Surface Dressing | WEST LANGTON ROAD from West Langton Road, Tur Langton to jnc B6047 Melton Road | 2018-06-12 | Completed
Blaby | Whetstone | Carriage Way Scheme | A426 Lutterworth Road | 2018-08-02 | Completed
Blaby | Whetstone | Surface Dressing | DOG AND GUN LANE from rndbt at Wychwood Road past Coop to end at pub | 2018-06-18 | Completed
Blaby | Whetstone | Surface Dressing | GREBE WAY Harlequin Close to end | 2018-06-18 | Completed
Blaby | Whetstone | Surface Dressing | HOPPER WAY from jnc Dog and Gun Lane opp Coop to blocks | 2018-06-18 | Completed
Blaby | Whetstone | Surface Dressing | SUNNYSIDE CLOSE from Woodyard Lane to ends | 2018-06-18 | Completed
Blaby | Whetstone | Surface Dressing | WINTERBURN GARDENS from The Nook to end | 2018-06-18 | Completed
Blaby | Whetstone | Surface Dressing | WOODYARD LANE from B582 Enderby Road to end | 2018-06-18 | Completed
North West Leicestershire | Whitwick | Surface Dressing | CITY OF THREE WATERS from jnc Loughborough Road to Gracedieu Road | 2018-06-26 | Completed
North West Leicestershire | Whitwick | Surface Dressing | GRACEDIEU ROAD from City Of Three Waters to Gracedieu Road, Thringstone | 2018-06-26 | Completed
North West Leicestershire | Whitwick | Surface Dressing | HILARY CRESCENT from Peterfield Road to Peterfield Road | 2018-06-25 | Completed
North West Leicestershire | Whitwick | Surface Dressing | OAKS ROAD from near jnc Swannymote Road to Oaks Road, Charley | 2018-04-23 | Completed
North West Leicestershire | Whitwick | Surface Dressing | PARSONWOOD HILL from Cademan Street to Loughborough Road | 2018-06-25 | Completed
North West Leicestershire | Whitwick | Surface Dressing | PETERFIELD ROAD from Hall Lane to Tressal Road | 2018-06-25 | Completed
North West Leicestershire | Whitwick | Patching | ST BERNARDS ROAD - SD | 2018-04-30 | Completed
North West Leicestershire | whitwick | Patching | st bernards road (remedials) | 2018-05-31 | Completed
North West Leicestershire | Whitwick | Surface Dressing | ST BERNARDS ROAD from Leicester Road to end incl link to Leicester Rd opp no.102 | 2018-06-04 | Completed
North West Leicestershire | Whitwick | Surface Dressing | VICARAGE STREET | 2018-06-25 | Completed
North West Leicestershire | Whitwick | Flood Alleviation Scheme | Whitwick, Breedon | To be scheduled | N/A
North West Leicestershire | Whitwick | Bridge Repairs | Whitwick, City of Three Waters | To be scheduled | Deferred to next due to environmental factors.
North West Leicestershire | Whitwick | Flood Alleviation Scheme | Whitwick, Grace dieu Road | To be scheduled | N/A
Oadby and Wigston | Wigston | Patching | HORSEWELL LANE | 2018-08-31 | Completed
Oadby and Wigston | Wigston | Safety Scheme | Wigston, Leicester Road junction with Carlton Drive | To be scheduled | N/A
Oadby and Wigston | Wigston | Safety Scheme | Wigston, Saffron Road junction with Gloucester Crescent | To be scheduled | N/A
North West Leicestershire | Wilson | Heat Damage - Retexturing | Slade Lane | To be scheduled
Harborough | wistow | Patching | fleckney rd | 2018-05-31 | Completed
Harborough | Withcote | Patching | Launde Road - CAT2H | 2018-05-31 | Completed
Hinckley & Bosworth | Witherley | Surface Dressing | ATHERSTONE ROAD from jnc Mythe Lane to SD joint near Atherstone Stables | 2018-05-17 | Completed
Hinckley & Bosworth | Witherley | Surface Dressing | MYTHE LANE from SD joint at stream bridge to jnc Ratcliffe Road at Mythe Cottage | 2018-08-23 | Completed
Hinckley & Bosworth | Witherley | Surface Dressing | RATCLIFFE ROAD from jnc Mythe Lane to County boundary at Ratcliffe bridge | 2018-05-17 | Completed
Charnwood | Woodhouse | Surface Dressing | BRAND LANE from School Lane to bridleway at stream | 2018-04-25 | Completed
Charnwood | Woodhouse | Surface Dressing | DEANS LANE | 2018-04-25 | Completed
Charnwood | Woodhouse | Patching | main st | 2018-08-31 | Completed
Charnwood | Woodhouse | Surface Dressing | SCHOOL LANE from Forest Road to Brand Lane | 2018-04-25 | Completed
Charnwood | Woodhouse | Surface Dressing | SWITHLAND ROAD (part) from both junctions Brand Lane to Swithland Woods entrance | 2018-04-25 | Completed
Charnwood | Woodhouse | MicroAsphalt | Beaumanor Gardens from jnc Forest Road to ends | To be scheduled | Completed
Charnwood | Woodhouse Eaves | Surface Dressing | BRAND LANE from bridleway at stream to SD joint at Main Street Swithland | 2018-04-25 | Completed
North West Leicestershire | Worthington | Heat Damage - Retexturing | Breedon Lane | To be scheduled
North West Leicestershire | Worthington | Heat Damage - Retexturing | Main Street | To be scheduled
North West Leicestershire | Worthington | Heat Damage - Resurfacing | Newbold Lane | To be scheduled
North West Leicestershire | worthington | Patching | rempstone road - REMEDIAL | 2018-05-31 | Completed
North West Leicestershire | Worthington | Surface Dressing | REMPSTONE ROAD from surfacing joint near jnc Elder Lane to 40mph past Cunneries Farm | 2018-04-24 | Completed
North West Leicestershire | Worthington | Surface Dressing | TOP BRAND from surfacing joint near Brand House Farm to Breedon Brand, Breedon | 2018-05-18 | Completed
Charnwood | Wymeswold | Surface Dressing | BURTON LANE from jnc Hoton Road to 30mph at Wymeswold village sign | 2018-05-21 | Completed
Charnwood | Wymeswold | Heat Damage - Retexturing | East Road | To be scheduled
Charnwood | Wymeswold | Patching | Far street | 2018-06-30 | Completed
Charnwood | Wymeswold | Patching | Far street | 2018-06-30 | Completed
Charnwood | Wymeswold | Surface Dressing | WIDE LANE from surfacing joint near Hades Lane to SD joint at bend near Ellas Farm | 2018-05-21 | Completed
Melton | Wymondham | Heat Damage - Surfacing / Retread | "From B676 to Butt Lane" | To be scheduled
Melton | Wymondham | Patching | CORDHILL LANE | 2018-08-31 | Completed
Melton | Wymondham | Patching | EDMONDTHORPE MERE | 2018-08-31 | Completed
Melton | Wymondham | Patching | glebe rd to station rd | 2018-08-31 | Completed
Melton | Wymondham | Patching | Sewstern Lane | 2018-05-31 | Completed
Melton | Wymondham | Surface Dressing | SEWSTERN ROAD from Wymondham Road at Buckminster Lodge to jnc Wymondham Main Street | 2018-05-31 | Completed
Melton | Wymondham | Surface Dressing | THE DRIFT ROAD from SD joint near Edmondthorpe Drift to surfacing joint at bend at old railway bridge | 2018-05-24 | Completed
North West Leicestershire |  | Flood Alleviation Scheme | Drome Close | To be scheduled | N/A

## Sheet2
District | Location | Scheme | Details | Other | Planned Completion Date | Complete
Blaby | Glen Parva | Bridge Repairs | Glen Parva, Blaby Bridge (A426) |  | To be scheduled | N/A
Charnwood | Loughborough | Bridge Repairs | Loughborough, Shakespeare Street |  | To be scheduled | N/A
Hinckley & Bosworth | Markfield | Bridge Repairs | Markfield, A50 |  | To be scheduled | N/A
Charnwood | Quorndon | Bridge Repairs | Quorn, Barrow Road |  | To be scheduled | N/A
North West Leicestershire | Whitwick | Bridge Repairs | Whitwick, City of Three Waters |  | To be scheduled | N/A
Hinckley & Bosworth | Bilestone | Bridge Replacement | Bilstone, Gibbet Lane |  | To be scheduled | N/A
Hinckley & Bosworth | Orton on the Hill | Bridge Replacement | Orton on the Hill, Sheepy Lane |  | To be scheduled | N/A
North West Leicestershire | Ashby de la Zouch | Crossing Renewal | Ashby de la Zouch, Market Street |  | To be scheduled | N/A
Hinckley & Bosworth | Hinckley | Crossing Renewal | Hinckley, Castle Street |  | To be scheduled | N/A
Harborough | Billesdon | Flood Alleviation Scheme | Billesdon, Brook Lane |  | To be scheduled | N/A
Harborough | Billesdon | Flood Alleviation Scheme | Billesdon, Great Easton |  | To be scheduled | N/A
Hinckley & Bosworth | Burbage | Flood Alleviation Scheme | Burbage, Sketchley Road |  | To be scheduled | N/A
Melton | Long Clawson | Flood Alleviation Scheme | Long Clawson, Stand Pit Lane |  | To be scheduled | N/A
Charnwood | Loughborough | Flood Alleviation Scheme | Loughborough, Windsor Road |  | To be scheduled | N/A
Charnwood | Rothley | Flood Alleviation Scheme | Rothley, Welsic Lane |  | To be scheduled | N/A
Charnwood | Swithland | Flood Alleviation Scheme | Swithland, Main Street |  | To be scheduled | N/A
North West Leicestershire | Whitwick | Flood Alleviation Scheme | Whitwick, Breedon |  | To be scheduled | N/A
North West Leicestershire | Whitwick | Flood Alleviation Scheme | Whitwick, Grace dieu Road |  | To be scheduled | N/A
North West Leicestershire |  | Flood Alleviation Scheme | Drome Close |  | To be scheduled | N/A
Harborough | Lubenham | Footbridge Replacement | Lubenham, Scoborugh Road |  | To be scheduled | N/A
Harborough | Dunton Bassett | Junction Renewal | Dunton Basset, A4626/Coopers Lane |  | To be scheduled | N/A
Blaby | Enderby | Junction Renewal | Braunstone, Osiers Bridge (top) |  | To be scheduled | N/A
Hinckley & Bosworth | Groby | Junction Renewal | Groby, A50/Lena Drive |  | To be scheduled | N/A
Charnwood | Loughborough | Junction Renewal | Loughborough, A6 (Bishops Meadow) |  | To be scheduled | N/A
Charnwood | Loughborough | Junction Renewal | Loughborough, Belton Road / Jubilee Drive |  | To be scheduled | N/A
Blaby | Blaby | Resurfacing | Winchester Avenue |  | To be scheduled | N/A
Blaby | Leicester Forest East, | Resurfacing | Leicester Forest East, Hinckley Road A47 |  | To be scheduled | N/A
Blaby | Glen Parva | Safety Scheme | Glen Parva, A426 Leicester Road junction with Little Glen Road |  | To be scheduled | N/A
Charnwood | Loughborough | Safety Scheme | Loughborough, A6 Loughborough Road junction with Beeches Road |  | To be scheduled | N/A
Charnwood | Loughborough | Safety Scheme | Loughborough, Leicester Road junction with Shelthorpe Road |  | To be scheduled | N/A
Charnwood | Ulverscroft | Safety Scheme | Ulverscroft, Shepshed Road junction with Beacon Road |  | To be scheduled | N/A
Oadby and Wigston | Wigston | Safety Scheme | Wigston, Leicester Road junction with Carlton Drive |  | To be scheduled | N/A
Oadby and Wigston | Wigston | Safety Scheme | Wigston, Saffron Road junction with Gloucester Crescent |  | To be scheduled | N/A
Harborough | Kibworth | Traffic Signal Investigation | Kibworth, Warwick Road |  | To be scheduled | N/A
Harborough | Blaston | Vehicle Restraint Systems | Blaston Road |  | 43418 | N/A
Blaby | Enderby | Vehicle Restraint Systems | Narborough Rd South |  | 43418 | N/A
Charnwood | Prestwold | Vehicle Restraint Systems | Barrow Road |  | 43418 | N/A