## Sheet1
District | Locality | Street | Nature of Works | Indicative start date if available | Indicative finish date if available
Charnwood | Quorn | Chaveney Road | Highway Flood Alleviation | 2021-05-04 | 2021-06-25
Blaby | Whetstone | Cambridge Road | Highway Flood Alleviation | Complete
Harborough | Shearsby | Back Lane | Highway Flood Alleviation | 2021-07-05 | 2021-08-30
Harborough | Saddington | Fleckney Road | Highway Flood Alleviation | 2021-07-05 | 2021-08-06
Hinckley & Bosworth | Groby | A50 Markfield Rd / Lena Drive | Traffic Signals Renewal | 2021-08-01
Harborough | Mkt Harborough | Kettering Road | Replacement of temp signals with permanent | 2021-07-12
Charnwood | Loughborough | Nottingham Rd/Queens Rd | Traffic Signals Renewal | 2021-08-16 | 2021-08-20
Charnwood | Loughborough | Ashby Rd/Bastard Gate | Traffic Signals Renewal | 2021-07-26 | 2021-08-11
Blaby | Enderby | Desford Rd/Beggars Ln/Next | Traffic Signals Renewal | 2021-07-17 | 2021-07-26
Oadby and Wigston | South Wigston | Blaby Rd/St Thomas Rd | Traffic Signals Renewal | 2021-07-19 | 2021-07-28
North West Leics | Ibstock | Melbourne Road/Central Avenue | Traffic Signals Renewal | 2021-08-09 | 2021-08-13
Blaby | Huncote | Main Street (ST0678) | Bridge maintenance (Phase 2) | 2021-06-21 | 2021-07-02
Charnwood | Syston | Melton Road (ST0273) | Bridge maintenance | TBC
Charnwood | Loughborough | Nottingham Road (ST0203) | Bridge maintenance | TBC
Charnwood | Loughborough | Nottingham Road (ST0204) | Bridge maintenance | TBC
Harborough | Market Harborough | Welland Park Road (ST0542) | Bridge maintenance | TBC
Harborough | Glooston | Cranoe Road (ST9082) | New retaining wall | 2022-01-01 | 2022-03-31
Melton | Harby | Langar Bridge, Langar Lane (ST0780) | Bridge maintenance | TBC
North West Leics | Belton | Ashby Road (ST0256) | Bridge maintenance | 2021-06-01 | 2021-07-02
Harborough | Little Bowden | Kettering Road | Patching | 2021-04-01
Harborough | Cold Newton | Skeg Hill | Patching | 2021-04-01
Charnwood | Rearsby | Gaddesby Lane | Patching | 2021-04-01
Harborough | Wistow | Fleckney Road | Patching | 2021-04-01
Hinckley & Bosworth | Bagworth | Heath Road | Patching | 2021-04-01
North West Leics | Coleorton | Ashby Road | Patching | 2021-04-01
Melton | Redmile | Sutton Road | Patching | 2021-04-01
North West Leics | Measham | Swepstone Road | Patching | 2021-04-01
Hinckley & Bosworth | Congerstone | Bilstone Road | Patching | 2021-04-01
Hinckley & Bosworth | Desford | Manor Rd Service | Patching | 2021-04-01
Hinckley & Bosworth | Desford | Cottage Lane | Patching | 2021-04-01
Blaby | Stoney Stanton | Nock Verges | Patching | 2021-04-01
Charnwood | Barrow | High Street | Patching | 2021-04-01
Hinckley & Bosworth | Hinckley | Coventry Road | Patching | 2021-04-01
Charnwood | Birstall | Heathcote Close | Patching | 2021-05-01
Charnwood | Queniborough | Syston northern bypass | Patching | 2021-05-01
Charnwood | Queniborough | Syston northern bypass | Patching | 2021-05-01
Blaby | Whetstone | Dog and Gun Lane | Patching | 2021-05-01
Charnwood | Thurmaston | Highways Road | Patching | 2021-05-01
Blaby | Braunstone | Braunstaone Lane | Patching | 2021-05-01
Charnwood | Rearsby | Church Lane | Patching | 2021-05-01
Charnwood | Thurmaston | Humberstone Lane | Patching | 2021-05-01
Charnwood | Thurmaston | Humberstone Lane | Patching | 2021-05-01
Harborough | Scraptoft | Covert Lane | Patching | 2021-06-01
Harborough | Skeffington | Uppinhgam Road | Patching | 2021-06-01
Harborough | Skeffington | Uppinhgam Road | Patching | 2021-06-01
Blaby | Whetstone | Dog and Gun Lane | Patching | 2021-06-01
Harborough | Market Harborough | Coventry Road | Patching | 2021-06-01
Harborough | Foxton | Lamgton Road | Patching | 2021-06-01
Harborough | Foxton | From Gumley rd to Theddingworth Rd | Patching | 2021-06-01
Harborough | Skeffington | Glebe Road | Patching | 2021-06-01
Blaby | Cosby | Main Street | Patching | 2021-06-01
Blaby | Glenfield | Station Road | Patching | 2021-06-01
Harborough | Saddington | Kibworth Road | Patching | 2021-06-01
North West Leics | Coalville | Interlink Way Easy | Patching | 2021-07-01
Melton | Melton | Wilton Road | Patching | 2021-07-01
North West Leics | Swannington | Main Street | Patching | 2021-07-01
Harborough | Stoughton | Gartree Road | Patching | 2021-07-01
Charnwood | Barkby | Beeby Road | Patching | 2021-07-01
Oadby and Wigston | Oadby | Wigston Road | Patching | 2021-08-01
Blaby | Sharnford | Leicester Road | Patching | 2021-08-01
Hinckley & Bosworth | Fenny Drayton | Fenns Lane | Patching | 2021-08-01
Blaby | Wigston | Blaby Road | Patching | 2021-08-01
Hinckley & Bosworth | Hinckley | Drake Road | Patching | 2021-08-01
Charnwood | Mountsorrel | Leicester Road | Patching | 2021-09-01
Charnwood | Mountsorrel | Hawcliffe Road | Patching | 2021-09-01
Charnwood | Quorn | Station Road | Patching | 2021-09-01
Charnwood | Cotes | Nottingham Road | Patching | 2021-09-01
North West Leics | Charley | Copt Oak Road | Patching | 2021-09-01
Hinckley & Bosworth | Thorton | Church Lane | Patching | 2021-09-01
Hinckley & Bosworth | Markfield | Stanton Lane | Patching | 2021-09-01
Hinckley & Bosworth | Hinckley | Harrowbrook Road | Patching | 2021-09-01
Harborough | Walcote | Gilmorton Road | Patching | 2021-10-01
Hinckley & Bosworth | Burbage | Lutterworth Road | Patching | 2021-10-01
Hinckley & Bosworth | Broughton Astley | Cottage Lane | Patching | 2021-10-01
Harborough | Theddingworth | Mowsley Road | Patching | 2021-10-01
Hinckley & Bosworth | Hinckley | Brodick Road | Patching | 2021-10-01
Blaby | Blaby | Southway | Patching | 2021-10-01
Charnwood | loughborough | Station Road | Patching | 2021-11-01
Harborough | Thurnby | Uppingham Rd Service Rd | Patching | 2021-12-01
Harborough | Kings Norton | Great Glen Road | Patching | 2021-12-01
Harborough | Gumley | Mowsley Rd to Gumley Rd | Patching | 2021-12-01
Harborough | Frolesworth | Main Street | Patching | 2021-12-01
Hinckley & Bosworth | Nailstone | Carlton Road | Patching | 2022-02-01
Hinckley & Bosworth | Barwell | Shilton Road | Patching | 2022-02-01
Hinckley & Bosworth | Hinckley | Brookdale | Patching | 2022-02-01
Hinckley & Bosworth | Burbage | The Fairway | Patching | 2022-02-01
Harborough | Illston on the Hill | Nosely Road | Patching | 2022-02-01
Harborough | Laughton | Mowsley Lane | Patching | 2022-02-01
Harborough | Upper Bruntingthorpe | Mere Road | Patching | 2022-02-01
Harborough | Burton Overy | Mayns Lane | Patching | 2022-02-01
Hinckley & Bosworth | sapcote | hinckley road | Patching | 2022-02-01
Hinckley & Bosworth | Higham on the Hill | Basin Bridge Lane | Patching | 2022-02-01
Hinckley & Bosworth | Groby | A50 markfield Road | Carraigeway resurfacing scheme | 2021-09-01 | 0ct 2021
Blaby | Sapcote | B4669 (junction with M69) | Carraigeway resurfacing scheme | 2021-07-01 | 2021-08-01
North West Leics | Ellistown | B585 Beveridge Lane | Carraigeway resurfacing scheme | 2021-07-01
Melton | Kirby Bellars | A607 Leicester Road | Carraigeway resurfacing scheme | 2021-09-01 | 2021-10-01
Melton | Melton Mowbray | A606 Nottingham Road | Carraigeway resurfacing scheme | 2021-09-01 | 2021-10-01
North West Leics | Castle Donnigton | A453 | Carraigeway resurfacing scheme | TBC
Charnwood | Loughborough | Woodgate | Carraigeway resurfacing scheme | TBC
Hinckley & Bosworth | Hinckley | A47 Normandy Way | Carraigeway resurfacing scheme | 2021-05-01 | 2021-05-01
Hinckley & Bosworth | Hinckley | A47 Dodwells Road | Carrigeway, footways and bridge maintenance scheme | 2021-06-01 | 2021-10-01
Charnwood | Loughborough | Bottleacre Lane | Footway resurfacing scheme | 2021-10-01
Blaby | Glenfield | Oakfield Avenue | Footway resurfacing scheme | 2021-08-01
Oadby and Wigston | Wigston | Castleton Road | Footway resurfacing scheme | 2021-06-01